## Overview
Job #2016 · Natural & Built Sedona Apartments
Cortex JCR Summary • Natural & Built Environments • Seattle, WA (8512 20th Ave NE) • 64-unit 6-story multifamily apartment building • Nov 2013 – Dec 2014 (~14 months)
PROJECT OVERVIEW
Project Job # | 2016
Project Name: | Natural & Built Sedona Apartments
General Contractor | Natural & Built Environments
Location | Seattle, WA (8512 20th Ave NE)
Project Duration | Nov 2013 – Dec 2014 (~14 months)
Total Unique Documents | Sedona folder: Contract, Billings, Invoices, PO_s, Permits
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$341,805 |  | $100,795 |  | $241,010 |  | 4,773
Original $336,500 + $5,305 COs |  | 29.5% margin |  | 70.5% of revenue |  | 28 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 74865 | 97891.25 | -23026.25 | 130.8% | 40.62%
Material | 123043 | 90495.62 | 32547.38 | 73.55% | 37.55%
Overhead | 3900 | 2699 | 1201 | 69.21% | 1.12%
Burden | 38181.17 | 49924.59 | -11743.42 | 130.8% | 20.71%
TOTAL | 239989.17 | 241010.46 | -1021.29 | 100.4% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 80 | Water Closets | 80 | Kitchen Sinks | 64
Total Fixtures | 267 | Lavatories | 80 | Dishwashers | 64
Fixtures / Unit | 3.34 | Tubs | 64 | Auto Washers | 64
Floors | 6 | Stacks | 16 | Duration | 14 mo
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 4980 | 5130 | 2769 | 2361 | 53.98%
101 | Takeoff & Purchase Labor | 4980 | 4980 | 3124 | 1856 | 62.73%
110 | Underground Labor | 2800 | 2800 | 1126 | 1674 | 40.21%
111 | Garage Labor | 0 | 0 | 416 | -416 | 0%
112 | Canout Labor | 1700 | 1700 | 765 | 935 | 45%
120 | Roughin Labor | 28845 | 30595 | 65392.75 | -34797.75 | 213.7%
130 | Finish Labor | 9520 | 9800 | 9310.5 | 489.5 | 95.01%
141 | Water Main/Insulation Lab | 8300 | 8300 | 4656 | 3644 | 56.1%
142 | Mech Room Labor | 4000 | 4000 | 1032 | 2968 | 25.8%
145 | Tub/Shower Labor | 7560 | 7560 | 9300 | -1740 | 123%
MATERIAL
210 | Underground Material | 2700 | 2700 | 1463.57 | 1236.43 | 54.21%
211 | Garage Material | 0 | 0 | 479.89 | -479.89 | 0%
212 | Canout Material | 2550 | 2550 | 2042.61 | 507.39 | 80.1%
220 | Roughin Material | 24300 | 24315 | 26087.05 | -1772.05 | 107.3%
230 | Finish Material | 81800 | 82478 | 56499.81 | 25978.19 | 68.5%
240 | Gas Material | 0 | 0 | 23.51 | -23.51 | 0%
241 | Water Main/Insulation Mat | 8000 | 8000 | 604.14 | 7395.86 | 7.552%
242 | Mech Room Material | 3000 | 3000 | 2702.93 | 297.07 | 90.1%
245 | Tub/Shower Material | 0 | 0 | 592.11 | -592.11 | 0%
OVERHEAD
600 | Subcontractor | 700 | 700 | 50 | 650 | 7.143%
603 | Permits & Licenses | 3200 | 3200 | 2649 | 551 | 82.78%
BURDEN
995 | Payroll Burden | 31508.95 | 32453.99 | 42435.92 | -9981.93 | 130.8%
998 | Payroll Taxes | 5560.4 | 5727.18 | 7488.67 | -1761.49 | 130.8%
TOTAL | Direct Cost | 236004.35 | 239989.17 | 241010.46 | -1021.29 | 100.4%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 10 | 74865 | 97891.25 | -23026.25 | 130.8% | 40.62% | 1223.6406
Material | 9 | 123043 | 90495.62 | 32547.38 | 73.55% | 37.55% | 1131.1952
Overhead | 2 | 3900 | 2699 | 1201 | 69.21% | 1.12% | 33.7375
Burden | 2 | 38181.17 | 49924.59 | -11743.42 | 130.8% | 20.71% | 624.0574
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 30595 | 65392.75 | 34797.75 | 113.7%
995 | Payroll Burden | 32453.99 | 42435.92 | 9981.93 | 30.76%
220 | Roughin Material | 24315 | 26087.05 | 1772.05 | 7.288%
998 | Payroll Taxes | 5727.18 | 7488.67 | 1761.49 | 30.76%
145 | Tub/Shower Labor | 7560 | 9300 | 1740 | 23.02%
245 | Tub/Shower Material | 0 | 592.11 | 592.11 | 0%
211 | Garage Material | 0 | 479.89 | 479.89 | 0%
111 | Garage Labor | 0 | 416 | 416 | 0%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 82478 | 56499.81 | 25978.19 | 31.5%
241 | Water Main/Insulation Mat | 8000 | 604.14 | 7395.86 | 92.45%
141 | Water Main/Insulation Lab | 8300 | 4656 | 3644 | 43.9%
142 | Mech Room Labor | 4000 | 1032 | 2968 | 74.2%
100 | Supervision | 5130 | 2769 | 2361 | 46.02%
101 | Takeoff & Purchase Labor | 4980 | 3124 | 1856 | 37.27%
110 | Underground Labor | 2800 | 1126 | 1674 | 59.79%
210 | Underground Material | 2700 | 1463.57 | 1236.43 | 45.79%
112 | Canout Labor | 1700 | 765 | 935 | 55%
600 | Subcontractor | 700 | 50 | 650 | 92.86%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Material
Material Spend Analysis
9 material cost codes • $90,496 JDR material • 9 AP vendors • $106,353 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
210 | Underground Material | 2700 | 1463.57 | 1236.43 | 54.21% | 1.617% | 18.2946
211 | Garage Material | 0 | 479.89 | -479.89 | 0% | 0.5303% | 5.9986
212 | Canout Material | 2550 | 2042.61 | 507.39 | 80.1% | 2.257% | 25.5326
220 | Roughin Material | 24315 | 26087.05 | -1772.05 | 107.3% | 28.83% | 326.0881
230 | Finish Material | 82478 | 56499.81 | 25978.19 | 68.5% | 62.43% | 706.2476
240 | Gas Material | 0 | 23.51 | -23.51 | 0% | 0.02598% | 0.29387
241 | Water Main/Insulation Mat | 8000 | 604.14 | 7395.86 | 7.552% | 0.6676% | 7.5518
242 | Mech Room Material | 3000 | 2702.93 | 297.07 | 90.1% | 2.987% | 33.7866
245 | Tub/Shower Material | 0 | 592.11 | -592.11 | 0% | 0.6543% | 7.4014
TOTAL | All Material | 123043 | 90495.62 | 32547.38 | 73.55% | 100% | 1131.1952
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Keller Supply Company | 22 | 74948.84 | 70.47% |  |  |  | 3406.7655
Ferguson Enterprises, Inc. | 21 | 14095.11 | 13.25% |  |  |  | 671.1957
Rosen Supply Company, Inc. | 25 | 11376.96 | 10.7% |  |  |  | 455.0784
Bank of America CC | 3 | 2649 | 2.491% |  |  |  | 883
Consolidated Supply Co. | 7 | 1086.17 | 1.021% |  |  |  | 155.1671
Mechanical Sales, Inc. | 1 | 1044 | 0.9816% |  |  |  | 1044
Rosen Supply Kirkland | 2 | 897.2 | 0.8436% |  |  |  | 448.6
Capital One Credit Card | 3 | 205.27 | 0.193% |  |  |  | 68.4233
R.A. Brown Backflow Testing | 1 | 50 | 0.04701% |  |  |  | 50
TOTAL | 85 | 106352.55 | 100%
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
Vendor AP ties to JDR 'by Source: AP' line (106,352.55)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Lima Romero, Melvin A | 664 | 13280 | 20 | Mid
Castro Hernandez, Carlos E | 644 | 18032 | 28 | Mid
Rivera, Jorge A | 485 | 8730 | 18 | Mid
Gonzalez Hernandez, Josue | 472 | 6608 | 14 | Apprentice
Quintanilla, Esteban R | 464 | 14848 | 32 | Senior
Reyes Cruz, Denis A | 456 | 5560 | 12.193 | Apprentice
Ramos Garcia, Jose M | 232 | 3016 | 13 | Apprentice
Rivera, Eli P | 214 | 2782 | 13 | Apprentice
Gerard, Jeffrey S | 192.5 | 7356 | 38.213 | Senior
Ramos Banegas, Noel O | 192 | 2496 | 13 | Apprentice
Castro Hernandez, Jose A | 176 | 2992 | 17 | Apprentice
Sanders, Allen O | 171 | 5022.5 | 29.3713 | Mid
Kinssies, Jr, John E | 129.5 | 2007 | 15.4981 | Apprentice
Soto Serna, Cesar E | 39 | 507 | 13 | Apprentice
Vaughan, Tyler J | 36.5 | 584 | 16 | Apprentice
Lopez Martinez, Abimael | 32 | 416 | 13 | Apprentice
Arreola, Israel A | 24 | 408 | 17 | Apprentice
Cortes Mendiola, Victor H | 24 | 624 | 26 | Mid
McCabe, Thomas C | 23 | 414 | 18 | Mid
Anderson, Richard P | 16.5 | 462 | 28 | Mid
Montenegro, Carlos E | 16 | 208 | 13 | Apprentice
Soto Cruz, Jovani | 8 | 128 | 16 | Apprentice
Paco Leyva, Orlando | 8 | 136 | 17 | Apprentice
Veley, Nathaniel S | 8 | 232 | 29 | Mid
Reyes, Robert J | 8 | 104 | 13 | Apprentice
Salazar, Hajdar L | 8 | 120 | 15 | Apprentice
Castaneda Juarez, Edgar D | 8 | 116 | 14.5 | Apprentice
Gerard, Mitchell J | 3.5 | 42 | 12 | Apprentice
TOTAL (28 workers) | 4754.5 | 97230.5 | 20.4502
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 656.5 | 22204 | 13.81%
Mid | 8 | 2035.5 | 46796.5 | 42.81%
Apprentice | 18 | 2062.5 | 28230 | 43.38%
B. WAGE STATISTICS
Blended Gross Wage | 20.4502 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 31.0897 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5203 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12 |  |  | Cheapest apprentice hour
Max Worker Rate | 38.213 |  |  | Most expensive foreman hour
Avg Hours / Worker | 169.8036 |  |  | Crew continuity indicator
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 72 | 1.508% | 0.9
Takeoff & Purchasing | 101 | 82 | 1.718% | 1.025
Underground | 110 | 37 | 0.7752% | 0.4625
Garage | 111 | 32 | 0.6704% | 0.4
Canout | 112 | 29.5 | 0.6181% | 0.36875
Roughin | 120 | 3260.5 | 68.31% | 40.7563
Finish | 130 | 420.5 | 8.81% | 5.2562
Water Main / Insulation | 141 | 251 | 5.259% | 3.1375
Mech Room | 142 | 48 | 1.006% | 0.6
Tub / Shower | 145 | 540.5 | 11.32% | 6.7562
TOTAL |  | 4773 | 100% | 59.6625
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 59.6625 | hrs |  | Labor hours per residential unit
Hours / Fixture | 17.8764 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 71.6122 | $ |  | Top-line per labor hour
Profit / Hour | 21.1176 | $ |  | Bottom-line per labor hour
Units / Month | 5.7143 | units |  | Build velocity
Fixtures / Month | 19.0714 | fix |  | Fixture install pace
Hours / Month | 340.9286 | hrs |  | Monthly labor burn
Revenue / Month | 24414.6429 | $ |  | Monthly billing rate
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## PO Commitments
Purchase Order Commitments
33 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $90,496
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 4 | 12.12%
31 | 120+220 Roughin | 6 | 18.18%
32 | 130+230 Trim/Finish | 2 | 6.061%
40 | 141+241 Water Main/Ins | 1 | 3.03%
OTHER | Unclassified | 20 | 60.61%
TOTAL |  | 33 | 100% | 90495.62
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 16 | 48.48%
FEI | 10 | 30.3%
OTHER | 3 | 9.091%
CONSOLIDATED | 2 | 6.061%
KELLER | 1 | 3.03%
MECH SALES | 1 | 3.03%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 90495.62
Unique PO Count |  |  | 33
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
8 pay applications • Original $336,500 + $5,305 COs = $341,805
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 336500
Change Orders (net) |  |  |  |  | 5305
Final Contract Value |  |  |  |  | 341805
Retainage (5%) |  |  |  |  | 17090
Net Paid to OWP |  |  |  |  | 324715
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2013-11-19 | 38400 | 1920 | 36480 | 40128 | 11.74%
2 | 2014-02-20 | 2223 | 111.15 | 2111.85 | 42451.04 | 12.42%
3 | 2014-04-24 | 94500 | 4725 | 89775 | 141203.54 | 41.31%
4 | 2014-05-22 | 77456 | 3872.8 | 73583.2 | 222145.06 | 64.99%
5 | 2014-06-24 | 68553 | 3427.65 | 65125.35 | 293782.95 | 85.95%
6 | 2014-07-24 | 15675 | 783.75 | 14891.25 | 310163.33 | 90.74%
7 | 2014-09-25 | 27898 | 1394.9 | 26503.1 | 339316.74 | 99.27%
8 | 2014-10-25 | 17100 | 855 | 16245 | 357186.24 | 104.5%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 341805 | 341805 | 0 | TIES
Retainage | 17090 | 17090 | 0 | TIES
Direct Cost | 241010.46 | 241010 | 0.46 | TIES
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Insights
Key Insights — Job #2016 Natural & Built Sedona Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $100,795 on $341,805 revenue = 29.5% gross margin. Direct cost $241,010 absorbs 70.5% of revenue.
VENDOR CONCENTRATION | Keller Supply Company alone = $74,949 (70% of all AP) across 22 invoices. Total 9 AP vendors, $106,353 total AP spend.
CREW PROFILE | 28 workers for 4,773 hours = 170 avg hrs/worker. Top 3 workers logged 1,793 hrs combined (38% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 3,260 hrs (68% of all labor) and $65,393 actual. Code 230 Finish Material = $56,500 — 23% of total direct cost.
BUDGET DELIVERY | Revised budget was $239,989; actual direct cost $241,010 → $-1,021 variance (-0.4% under revised budget).
CONTRACT GROWTH | Contract grew from $336,500 to $341,805 — net +$5,305 (1.6%). Retainage of $17,090 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $49,925 on $97,891 labor base = 51.0%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 80 units · 267 fixtures · 14 months. Revenue/unit $4,273, hours/unit 59.7, profit/unit $1,260.
PRODUCTIVITY | Blended labor rate $20.51/hr. Revenue/hour $72. Profit/hour $21. 341 hrs/month burn rate.
FIXTURE DENSITY | 267 fixtures ÷ 80 units = 3.34 fixtures/unit. Material/fixture $339, labor/fixture $367.
BIGGEST QUESTION
How does this job's 29.5% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2016 | Profile | OWP job ID
Job Name | job_name | Natural & Built Sedona Apartments | Profile
General Contractor | general_contractor | Natural & Built Environments | Profile
Location | location | Seattle, WA (8512 20th Ave NE) | Profile
Project Type | project_type | 64-unit 6-story multifamily apartment building | Profile
Duration (months) | duration_months | 14 | Profile | Nov 2013 – Dec 2014 (~14 months)
Unit Count | unit_count | 80 | Profile
Total Fixtures | total_fixtures | 267 | Profile
Fixtures per Unit | fixtures_per_unit | 3.3375 | Profile
Contract Value (Orig) | contract_original | 336500 | Financial
Contract Value (Final) | contract_final | 341805 | Financial | After change orders
Change Orders ($) | change_orders | 5305 | Financial
Revenue | revenue | 341805 | Financial
Net Profit | net_profit | 100794.54 | Financial
Gross Margin | gross_margin | 0.29489 | Financial
Direct Cost | direct_cost | 241010.46 | Financial
Labor Cost | labor_cost | 97891.25 | Labor | Sum of 10 labor codes
Material Cost | material_cost | 90495.62 | Material | Sum of 9 material codes
Overhead Cost | overhead_cost | 2699 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 49924.59 | Financial | Codes 995+998
Retainage | retainage | 17090 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 4272.5625 | Financial
Profit per Unit | profit_per_unit | 1259.9317 | Financial
Direct Cost per Unit | cost_per_unit | 3012.6307 | Financial
Labor Cost per Unit | labor_per_unit | 1223.6406 | Labor
Material Cost per Unit | material_per_unit | 1131.1952 | Material
Revenue per Fixture | revenue_per_fixture | 1280.1685 | Financial
Profit per Fixture | profit_per_fixture | 377.5076 | Financial
Cost per Fixture | cost_per_fixture | 902.6609 | Financial
Labor per Fixture | labor_per_fixture | 366.6339 | Labor
Material per Fixture | material_per_fixture | 338.9349 | Material
Total Labor Hours | total_hours | 4773 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 28 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 2037% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3097% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5203 | Labor
Hours per Unit | hours_per_unit | 5966% | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 1788% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 7161% | Productivity
Profit per Hour | profit_per_hour | 2112% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.2864 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.26476 | Cost Mix
Revenue per Month | revenue_per_month | 24414.6429 | Productivity
Hours per Month | hours_per_month | 340.9286 | Productivity
Units per Month | units_per_month | 5.7143 | Productivity
Total Vendors | total_vendors | 9 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 74948.84 | Material | Keller Supply Company
Top Vendor Concentration | top_vendor_pct | 0.70472 | Material
Total POs | total_pos | 33 | Material | Unique POs by filename
Change Order % | co_pct | 0.015765 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 7161% | Productivity
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (10 codes) | 97891.25 | 97891.25 | 0 | TIES
Material subtotal (9 codes) | 90495.62 | 90495.62 | 0 | TIES
Overhead subtotal (2 codes) | 2699 | 2699 | 0 | TIES
Burden subtotal (2 codes) | 49924.59 | 49924.59 | 0 | TIES
Direct Cost (all categories) | 241010.46 | 241010.46 | 0 | TIES
Revenue (code 999) | 341805 | 341805 | 0 | TIES
Net Profit (Revenue - Expenses) | 100794.54 | 100794.54 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 4773 | 4773 | 0 | TIES
Per-worker hours (sum of PR Regular) | 4754.5 | 4773 | -18.5 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 341805 | 341805 | 0 | TIES
Retainage | 17090 | 17090 | 0 | TIES
Direct Cost | 241010.46 | 241010 | 0.46 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 106352.55 | 86915 | 19437.55 | OFF
SOURCES
Job #2016 — Natural & Built Sedona Apartments • GC: Natural & Built Environments • Seattle, WA
Canonical source: 2016 Job Detail Report.pdf (45 pages, OWP Sage Timberline export)
Cost codes parsed: 24 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 64 via 5 per-level Keller trim invoices (L2:16 L3:8 L4:16 L5:16 L6:8)
Fixture count: 267 from King County Plumbing Permit #5101400394
Billing: SEDONA AGGREGATE BILLING.xlsx (8 pay apps, Nov 2013 – Oct 2014)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2016
Vendors | 9 |  | Top vendor | Keller Supply Company
Invoices | 85 |  | Top 3 share | 94.42%
Total AP | 106352.55 |  | Source | 2016 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1251.2065
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Keller Supply Company |  | 22 | 74948.84 | 70.47% | 3406.7655
2 | Ferguson Enterprises, Inc. |  | 21 | 14095.11 | 13.25% | 671.1957
3 | Rosen Supply Company, Inc. |  | 25 | 11376.96 | 10.7% | 455.0784
4 | Bank of America CC |  | 3 | 2649 | 2.491% | 883
5 | Consolidated Supply Co. |  | 7 | 1086.17 | 1.021% | 155.1671
6 | Mechanical Sales, Inc. |  | 1 | 1044 | 0.9816% | 1044
7 | Rosen Supply Kirkland |  | 2 | 897.2 | 0.8436% | 448.6
8 | Capital One Credit Card |  | 3 | 205.27 | 0.193% | 68.4233
9 | R.A. Brown Backflow Testing |  | 1 | 50 | 0.04701% | 50
| TOTAL |  | 85 | 106352.55 | 100% | 1251.2065