## Overview
Job #2017 · Exxel Pacific 3636 Stone Way Apartments
Cortex JCR Summary • Exxel Pacific, Inc. • Seattle, WA (3636 Stone Way N) • 119-unit 4-story mixed-use apartments + ground-floor retail • Feb 2014 – May 2015 (~16 months)
PROJECT OVERVIEW
Project Job # | 2017
Project Name: | Exxel Pacific 3636 Stone Way Apartments
General Contractor | Exxel Pacific, Inc.
Location | Seattle, WA (3636 Stone Way N)
Project Duration | Feb 2014 – May 2015 (~16 months)
Total Unique Documents | 36 Stone folder: Contract, Stoneway billing (14 apps), PO_s, COs, Job Ticket
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$1,369,989 |  | $510,805 |  | $859,184 |  | 14,822
Original $1,373,148 net COs -$3,159 |  | 37.3% margin |  | 62.7% of revenue |  | 45 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 272340 | 292755.75 | -20415.75 | 107.5% | 34.07%
Material | 502391 | 378313.74 | 124077.26 | 75.3% | 44.03%
Overhead | 42470 | 33855.5 | 8614.5 | 79.72% | 3.94%
Burden | 139796.75 | 154259.34 | -14462.59 | 110.3% | 17.95%
TOTAL | 956997.75 | 859184.33 | 97813.42 | 89.78% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 119 | Water Closets | 122 | Kitchen Sinks | 119
Total Fixtures | 801 | Lavatories | 137 | Dishwashers | 119
Fixtures / Unit | 6.73 | Tubs/Showers | 122 | Auto Washers | 119
Floors | 4 + P1 | Common-area bldg systems | Garage HB, water rm, gas | Duration | 16 mo
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 6500 | 6500 | 4744 | 1756 | 72.98%
101 | Takeoff & Purchase Labor | 6500 | 7300 | 7873 | -573 | 107.8%
110 | Underground Labor | 8538 | 8538 | 6900 | 1638 | 80.82%
111 | Garage Labor | 38180 | 38670 | 29981 | 8689 | 77.53%
112 | Canout Labor | 5130 | 5130 | 4602 | 528 | 89.71%
113 | Foundation Drain Labor | 2012 | 2012 | 2012 | 0 | 100%
120 | Roughin Labor | 138760 | 140370 | 173312.75 | -32942.75 | 123.5%
130 | Finish Labor | 23400 | 25520 | 36292.5 | -10772.5 | 142.2%
140 | Gas Labor | 6000 | 6300 | 7448 | -1148 | 118.2%
141 | Water Main/Insulation Lab | 32000 | 32000 | 19505.5 | 12494.5 | 60.95%
142 | Mech Room Labor | 0 | 0 | 85 | -85 | 0%
MATERIAL
039 | DS & RD Material | 0 | 0 | 2380.94 | -2380.94 | 0%
210 | Underground Material | 5685 | 5685 | 3861 | 1824 | 67.92%
211 | Garage Material | 29760 | 29800 | 3724.79 | 26075.21 | 12.5%
212 | Canout Material | 5700 | 5740 | 6453.36 | -713.36 | 112.4%
213 | Foundation Material | 15065 | 13365 | 13364.65 | 0.35 | 100%
220 | Roughin Material | 138250 | 132050 | 98571.05 | 33478.95 | 74.65%
230 | Finish Material | 273100 | 248951 | 192296.61 | 56654.39 | 77.24%
240 | Gas Material | 3600 | 3600 | 2769 | 831 | 76.92%
241 | Water Main/Insulation Mat | 51200 | 51200 | 45904.61 | 5295.39 | 89.66%
242 | Mech Room Material | 12000 | 12000 | 8987.73 | 3012.27 | 74.9%
OVERHEAD
600 | Subcontractor | 15970 | 16970 | 15635 | 1335 | 92.13%
601 | Engineering/Plans | 22000 | 22500 | 17974.5 | 4525.5 | 79.89%
603 | Permits & Licenses | 3000 | 3000 | 246 | 2754 | 8.2%
BURDEN
995 | Payroll Burden | 116366.6 | 118687.33 | 131106.33 | -12419 | 110.5%
998 | Payroll Taxes | 20702.43 | 21109.42 | 23153.01 | -2043.59 | 109.7%
TOTAL | Direct Cost | 979419.03 | 956997.75 | 859184.33 | 97813.42 | 89.78%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 11 | 272340 | 292755.75 | -20415.75 | 107.5% | 34.07% | 2460.1324
Material | 10 | 502391 | 378313.74 | 124077.26 | 75.3% | 44.03% | 3179.1071
Overhead | 3 | 42470 | 33855.5 | 8614.5 | 79.72% | 3.94% | 284.5
Burden | 2 | 139796.75 | 154259.34 | -14462.59 | 110.3% | 17.95% | 1296.297
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 140370 | 173312.75 | 32942.75 | 23.47%
995 | Payroll Burden | 118687.33 | 131106.33 | 12419 | 10.46%
130 | Finish Labor | 25520 | 36292.5 | 10772.5 | 42.21%
039 | DS & RD Material | 0 | 2380.94 | 2380.94 | 0%
998 | Payroll Taxes | 21109.42 | 23153.01 | 2043.59 | 9.681%
140 | Gas Labor | 6300 | 7448 | 1148 | 18.22%
212 | Canout Material | 5740 | 6453.36 | 713.36 | 12.43%
101 | Takeoff & Purchase Labor | 7300 | 7873 | 573 | 7.849%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 248951 | 192296.61 | 56654.39 | 22.76%
220 | Roughin Material | 132050 | 98571.05 | 33478.95 | 25.35%
211 | Garage Material | 29800 | 3724.79 | 26075.21 | 87.5%
141 | Water Main/Insulation Lab | 32000 | 19505.5 | 12494.5 | 39.05%
111 | Garage Labor | 38670 | 29981 | 8689 | 22.47%
241 | Water Main/Insulation Mat | 51200 | 45904.61 | 5295.39 | 10.34%
601 | Engineering/Plans | 22500 | 17974.5 | 4525.5 | 20.11%
242 | Mech Room Material | 12000 | 8987.73 | 3012.27 | 25.1%
603 | Permits & Licenses | 3000 | 246 | 2754 | 91.8%
210 | Underground Material | 5685 | 3861 | 1824 | 32.08%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Material
Material Spend Analysis
10 material cost codes • $378,314 JDR material • 20 AP vendors • $458,376 total AP
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 0 | 2380.94 | -2380.94 | 0% | 0.6294% | 20.0079
210 | Underground Material | 5685 | 3861 | 1824 | 67.92% | 1.021% | 32.4454
211 | Garage Material | 29800 | 3724.79 | 26075.21 | 12.5% | 0.9846% | 31.3008
212 | Canout Material | 5740 | 6453.36 | -713.36 | 112.4% | 1.706% | 54.2299
213 | Foundation Material | 13365 | 13364.65 | 0.35 | 100% | 3.533% | 112.308
220 | Roughin Material | 132050 | 98571.05 | 33478.95 | 74.65% | 26.06% | 828.3282
230 | Finish Material | 248951 | 192296.61 | 56654.39 | 77.24% | 50.83% | 1615.9379
240 | Gas Material | 3600 | 2769 | 831 | 76.92% | 0.7319% | 23.2689
241 | Water Main/Insulation Mat | 51200 | 45904.61 | 5295.39 | 89.66% | 12.13% | 385.753
242 | Mech Room Material | 12000 | 8987.73 | 3012.27 | 74.9% | 2.376% | 75.5271
TOTAL | All Material | 502391 | 378313.74 | 124077.26 | 75.3% | 100% | 3179.1071
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  |  | Avg Invoice
Consolidated Supply Co. | 102 | 176571.46 | 38.52% |  |  |  | 1731.0927
Rosen Supply Company, Inc. | 85 | 139209.01 | 30.37% |  |  |  | 1637.7531
Ferguson Enterprises, Inc. | 18 | 72780.98 | 15.88% |  |  |  | 4043.3878
Franklin Engineering | 5 | 17974.5 | 3.921% |  |  |  | 3594.9
Duraseal, Inc. | 2 | 12800 | 2.792% |  |  |  | 6400
Keller Supply Company | 11 | 8131.24 | 1.774% |  |  |  | 739.2036
Bank of America CC | 6 | 8076 | 1.762% |  |  |  | 1346
Quality Concrete Products, Inc. | 3 | 5921 | 1.292% |  |  |  | 1973.6667
Rosen Supply Kirkland | 6 | 4412.21 | 0.9626% |  |  |  | 735.3683
Mechanical Sales, Inc. | 2 | 2840 | 0.6196% |  |  |  | 1420
Manor Hardware & Construction Supply | 3 | 2465 | 0.5378% |  |  |  | 821.6667
Cascade Restoration Co. | 2 | 2140 | 0.4669% |  |  |  | 1070
Kele, Inc | 4 | 1340.48 | 0.2924% |  |  |  | 335.12
Core & Main LP | 2 | 1134.15 | 0.2474% |  |  |  | 567.075
Ferguson Enterprises, Inc. #3007 | 3 | 811.46 | 0.177% |  |  |  | 270.4867
C.M. Hoskins Company | 3 | 702.97 | 0.1534% |  |  |  | 234.3233
Structural Imaging, LLC | 1 | 500 | 0.1091% |  |  |  | 500
Fastenal Company | 4 | 258.11 | 0.05631% |  |  |  | 64.5275
R.A. Brown Backflow Testing | 2 | 195 | 0.04254% |  |  |  | 97.5
Capital One Credit Card | 2 | 112.8 | 0.02461% |  |  |  | 56.4
TOTAL | 266 | 458376.37 | 100%
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Vendor AP ties to JDR 'by Source: AP' line (458,376.37)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gonzalez Hernandez, Josue | 1282 | 19700 | 15.3666 | Apprentice
Montenegro, Carlos E | 1186 | 16982 | 14.3187 | Apprentice
Castro Hernandez, Carlos E | 1176 | 33725 | 28.6777 | Mid
Reyes Cruz, Denis A | 1006.5 | 13658 | 13.5698 | Apprentice
Quintanilla, Esteban R | 1002 | 32471 | 32.4062 | Senior
Lima Romero, Melvin A | 921 | 18933 | 20.557 | Mid
Rivera, Jorge A | 909 | 17124 | 18.8383 | Mid
Esparza Jimenez, Jose D | 784 | 14896 | 19 | Mid
Castro Hernandez, Jose A | 687.5 | 12177 | 17.712 | Apprentice
Reyes, Robert J | 606 | 8164 | 13.4719 | Apprentice
Ramirez, Lorenzo A | 490 | 8061 | 16.451 | Apprentice
Soto Cruz, Jovani | 442.5 | 7471 | 16.8836 | Apprentice
Monico Brambila, Jesus S | 408 | 6352 | 15.5686 | Apprentice
Ramos Banegas, Noel O | 405.5 | 5930.5 | 14.6252 | Apprentice
Sepulveda Gonzalez, Alfredo | 401 | 10159 | 25.3342 | Mid
Rivera, Eli P | 397 | 5811 | 14.6373 | Apprentice
Castaneda Martinez, Gustavo | 394 | 11269 | 28.6015 | Mid
Gerard, Jeffrey S | 331.5 | 12927 | 38.9955 | Senior
Anzora, William | 312 | 4216 | 13.5128 | Apprentice
Kinssies, Jr, John E | 220.5 | 3420 | 15.5102 | Apprentice
Salazar, Hajdar L | 216.5 | 3312 | 15.2979 | Apprentice
Castaneda Juarez, Edgar D | 214 | 3340.75 | 15.611 | Apprentice
Sanders, Allen O | 156 | 4809 | 30.8269 | Senior
Vaughan, Tyler J | 150.5 | 2468.5 | 16.402 | Apprentice
Anderson, Richard P | 140 | 3920 | 28 | Mid
Rico-Gomez, Angel A | 114.5 | 1488.5 | 13 | Apprentice
Castaneda Juarez, Gustavo | 111.5 | 1641 | 14.7175 | Apprentice
Veley, Nathaniel S | 107 | 3103 | 29 | Mid
Rodriguez Bonilla, Lisandro | 88 | 1144 | 13 | Apprentice
Gerard, Mitchell J | 73 | 936 | 12.8219 | Apprentice
Paco Leyva, Orlando | 59 | 1003 | 17 | Apprentice
Donelson, Richard T | 29 | 1305 | 45 | Senior
Meza Fuentes, Erick A | 24 | 488 | 20.3333 | Mid
Palma Vides, Hugo | 16 | 464 | 29 | Mid
Amaya Gonzalez, Edilberto A | 16 | 208 | 13 | Apprentice
Arreola, Israel A | 16 | 272 | 17 | Apprentice
Garcia, Jordan X | 16 | 272 | 17 | Apprentice
Hubbard, Dustin R | 16 | 208 | 13 | Apprentice
Nishiyama, Joshua K | 13 | 169 | 13 | Apprentice
Rodriguez Rodriguez, Aminadab N | 8 | 104 | 13 | Apprentice
Ascencio, Jose L | 8 | 104 | 13 | Apprentice
Cruz Reyes, Jose | 8 | 104 | 13 | Apprentice
McCabe, Thomas C | 6 | 120 | 20 | Mid
Velasquez Cruz, Denis M | 6 | 90 | 15 | Apprentice
Barnhart, Joseph N | 1 | 31 | 31 | Senior
TOTAL (45 workers) | 14975 | 294551.25 | 19.6695
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 5 | 1519.5 | 51543 | 10.15%
Mid | 11 | 4878 | 114201 | 32.57%
Apprentice | 29 | 8577.5 | 128807.25 | 57.28%
B. WAGE STATISTICS
Blended Gross Wage | 19.6695 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 29.8508 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5176 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | 12.8219 |  |  | Cheapest apprentice hour
Max Worker Rate | 45 |  |  | Most expensive foreman hour
Avg Hours / Worker | 332.7778 |  |  | Crew continuity indicator
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
Supervision | 100 | 119.5 | 0.8062% | 1.0042
Takeoff & Purchasing | 101 | 198.5 | 1.339% | 1.6681
Underground | 110 | 288 | 1.943% | 2.4202
Garage | 111 | 1485 | 10.02% | 12.479
Canout | 112 | 177.5 | 1.198% | 1.4916
Foundation Drain | 113 | 97 | 0.6544% | 0.81513
Roughin | 120 | 9126.5 | 61.57% | 76.6933
Finish | 130 | 1926 | 12.99% | 16.1849
Gas | 140 | 352 | 2.375% | 2.958
Water Main / Insulation | 141 | 1047 | 7.064% | 8.7983
Mech Room | 142 | 5 | 0.03373% | 0.042017
TOTAL |  | 14822 | 100% | 124.5546
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 124.5546 | hrs |  | Labor hours per residential unit
Hours / Fixture | 18.5044 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 92.4294 | $ |  | Top-line per labor hour
Profit / Hour | 34.4626 | $ |  | Bottom-line per labor hour
Units / Month | 7.4375 | units |  | Build velocity
Fixtures / Month | 50.0625 | fix |  | Fixture install pace
Hours / Month | 926.375 | hrs |  | Monthly labor burn
Revenue / Month | 85624.3125 | $ |  | Monthly billing rate
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## PO Commitments
Purchase Order Commitments
142 unique POs • PO amounts not dollar-parsed from individual PDFs • JDR material $378,314
A. COMMITMENTS BY COST CODE
OWP Code | Description → JDR | PO Count | % of POs | JDR Material
30 | 110+210 Underground | 18 | 12.68%
31 | 120+220 Roughin | 25 | 17.61%
32 | 130+230 Trim/Finish | 9 | 6.338%
34 | 111+211 Garage | 2 | 1.408%
40 | 141+241 Water Main/Ins | 2 | 1.408%
41 | 140+240 Gas | 4 | 2.817%
OTHER | Unclassified | 82 | 57.75%
TOTAL |  | 142 | 100% | 378313.74
B. COMMITMENTS BY VENDOR
Vendor | PO Count | % of POs
ROSEN | 62 | 43.66%
CONSOLIDATED | 31 | 21.83%
OTHER | 18 | 12.68%
KELLER | 11 | 7.746%
FEI | 11 | 7.746%
MANOR | 3 | 2.113%
FASTENAL | 3 | 2.113%
SIOUX CHIEF | 1 | 0.7042%
PIKE | 1 | 0.7042%
MECH SALES | 1 | 0.7042%
C. PO COVERAGE NOTES
Total Material Actual (JDR) |  |  | 378313.74
Unique PO Count |  |  | 142
(Dollar PO commitment not extracted — requires per-PDF parse)
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
PO count is deduplicated by 5-digit PO number extracted from filenames
Vendor/code classification is heuristic (filename keyword match)

## Billing & SOV
Revenue & Billing Reconciliation
14 pay applications • Original $1,373,148 net -$3,159 COs = $1,369,989
A. CONTRACT SUMMARY
Original Contract |  |  |  |  | 1373148
Change Orders (net) |  |  |  |  | -3159
Final Contract Value |  |  |  |  | 1369989
Retainage (5%) |  |  |  |  | 68499
Net Paid to OWP |  |  |  |  | 1301490
B. PAY APPLICATION TIMELINE
App# | Date | Period Billing | Retention | Net This Period | Aggregate | % Complete
1 | 2014-02-20 | 70000 | 3500 | 66500 | 66500 | 4.854%
2 | 2014-04-20 | 43000 | 2150 | 40850 | 107350 | 7.836%
3 | 2014-05-20 | 72350 | 3617.5 | 68732.5 | 176082.5 | 12.85%
4 | 2014-06-20 | 21643 | 1082.15 | 20560.85 | 196643.35 | 14.35%
5 | 2014-07-20 | 111749 | 5587.45 | 106161.55 | 302804.9 | 22.1%
6 | 2014-08-20 | 229700 | 11485 | 218215 | 521019.9 | 38.03%
7 | 2014-09-18 | 348421 | 17421.05 | 330999.95 | 852019.85 | 62.19%
8 | 2014-10-20 | 213650 | 10682.5 | 202967.5 | 1054987.35 | 77.01%
9 | 2014-11-17 | 83445 | 4172.25 | 79272.75 | 1134260.1 | 82.79%
10 | 2014-12-15 | 24500 | 1225 | 23275 | 1157535.1 | 84.49%
11 | 2015-01-20 | 32880 | 1644 | 31236 | 1188771.1 | 86.77%
12 | 2015-02-20 | 53430 | 2671.5 | 50758.5 | 1239529.6 | 90.48%
13 | 2015-03-19 | 63944 | 3197.2 | 60746.8 | 1300276.4 | 94.91%
14 | 2015-05-19 | 1277 | 63.85 | 1213.15 | 1301489.55 | 95%
15 | - | 68499.45 | 0 | 68499.45 | 1369989 | 100%
C. BILLING ↔ JDR TIE-OUT
Metric | SOV | JDR | Δ | Status
Final Contract Value | 1438488.45 | 1369989 | 68499.45 | WITHIN
Retainage | 68499 | 68499 | 0 | TIES
Direct Cost | 859184.33 | 859184.33 | 0 | TIES
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Insights
Key Insights — Job #2017 Exxel Pacific 3636 Stone Way Apartments
Narrative observations distilled from the full JDR analysis
MARGIN PROFILE | Net profit of $510,805 on $1,369,989 revenue = 37.3% gross margin. Direct cost $859,184 absorbs 62.7% of revenue.
VENDOR CONCENTRATION | Consolidated Supply Co. alone = $176,571 (39% of all AP) across 102 invoices. Total 20 AP vendors, $458,376 total AP spend.
CREW PROFILE | 45 workers for 14,822 hours = 329 avg hrs/worker. Top 3 workers logged 3,644 hrs combined (25% of all labor).
ROUGHIN DOMINANCE | Code 120 Roughin Labor = 9,126 hrs (62% of all labor) and $173,313 actual. Code 230 Finish Material = $192,297 — 22% of total direct cost.
BUDGET DELIVERY | Revised budget was $956,998; actual direct cost $859,184 → $97,813 variance (10.2% under revised budget).
CONTRACT GROWTH | Contract grew from $1,373,148 to $1,369,989 — net +$-3,159 (-0.2%). Retainage of $68,499 (5%) withheld until closeout.
BURDEN RATIO | Burden codes 995 + 998 = $154,259 on $292,756 labor base = 52.7%. In line with OWP's typical 48–50% labor burden.
PROJECT SCALE | 119 units · 801 fixtures · 16 months. Revenue/unit $11,513, hours/unit 124.6, profit/unit $4,292.
PRODUCTIVITY | Blended labor rate $19.75/hr. Revenue/hour $92. Profit/hour $34. 926 hrs/month burn rate.
FIXTURE DENSITY | 801 fixtures ÷ 119 units = 6.73 fixtures/unit. Material/fixture $472, labor/fixture $365.
BIGGEST QUESTION
How does this job's 37.3% margin compare across similar projects in the OWP portfolio, and what operational levers drove the result — estimating accuracy, vendor pricing, or labor productivity?
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2017 | Profile | OWP job ID
Job Name | job_name | Exxel Pacific 3636 Stone Way Apartments | Profile
General Contractor | general_contractor | Exxel Pacific, Inc. | Profile
Location | location | Seattle, WA (3636 Stone Way N) | Profile
Project Type | project_type | 119-unit 4-story mixed-use apartments + ground-floor retail | Profile
Duration (months) | duration_months | 16 | Profile | Feb 2014 – May 2015 (~16 months)
Unit Count | unit_count | 119 | Profile
Total Fixtures | total_fixtures | 801 | Profile
Fixtures per Unit | fixtures_per_unit | 6.7311 | Profile
Contract Value (Orig) | contract_original | 1373148 | Financial
Contract Value (Final) | contract_final | 1369989 | Financial | After change orders
Change Orders ($) | change_orders | -3159 | Financial
Revenue | revenue | 1369989 | Financial
Net Profit | net_profit | 510804.67 | Financial
Gross Margin | gross_margin | 0.37285 | Financial
Direct Cost | direct_cost | 859184.33 | Financial
Labor Cost | labor_cost | 292755.75 | Labor | Sum of 11 labor codes
Material Cost | material_cost | 378313.74 | Material | Sum of 10 material codes
Overhead Cost | overhead_cost | 33855.5 | Financial | Sub+Eng+Permits
Burden Cost | burden_cost | 154259.34 | Financial | Codes 995+998
Retainage | retainage | 68499 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 11512.5126 | Financial
Profit per Unit | profit_per_unit | 4292.4762 | Financial
Direct Cost per Unit | cost_per_unit | 7220.0364 | Financial
Labor Cost per Unit | labor_per_unit | 2460.1324 | Labor
Material Cost per Unit | material_per_unit | 3179.1071 | Material
Revenue per Fixture | revenue_per_fixture | 1710.3483 | Financial
Profit per Fixture | profit_per_fixture | 637.7087 | Financial
Cost per Fixture | cost_per_fixture | 1072.6396 | Financial
Labor per Fixture | labor_per_fixture | 365.4878 | Labor
Material per Fixture | material_per_fixture | 472.3018 | Material
Total Labor Hours | total_hours | 14822 | Labor | Sum of JDR cost code hours
Total Workers | total_workers | 45 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 1987% | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 3016% | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5176 | Labor
Hours per Unit | hours_per_unit | 124.5546 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 1850% | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 9243% | Productivity
Profit per Hour | profit_per_hour | 3446% | Productivity
Labor % of Revenue | labor_pct_revenue | 0.21369 | Cost Mix
Material % of Revenue | material_pct_revenue | 0.27614 | Cost Mix
Revenue per Month | revenue_per_month | 85624.3125 | Productivity
Hours per Month | hours_per_month | 926.375 | Productivity
Units per Month | units_per_month | 7.4375 | Productivity
Total Vendors | total_vendors | 20 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 176571.46 | Material | Consolidated Supply Co.
Top Vendor Concentration | top_vendor_pct | 0.38521 | Material
Total POs | total_pos | 142 | Material | Unique POs by filename
Change Order % | co_pct | -0.0023006 | Financial
Revenue per Labor Hour | rev_per_labor_hr | 9243% | Productivity
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
51 KPIs with snake_case data_name identifiers for database ingestion

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JDR COST CODE ROLLUP
Labor subtotal (11 codes) | 292755.75 | 292755.75 | 0 | TIES
Material subtotal (10 codes) | 378313.74 | 378313.74 | 0 | TIES
Overhead subtotal (3 codes) | 33855.5 | 33855.5 | 0 | TIES
Burden subtotal (2 codes) | 154259.34 | 154259.34 | 0 | TIES
Direct Cost (all categories) | 859184.33 | 859184.33 | 0 | TIES
Revenue (code 999) | 1369989 | 1369989 | 0 | TIES
Net Profit (Revenue - Expenses) | 510804.67 | 510804.67 | 0 | TIES
B. LABOR HOURS ROLLUP
JDR Cost Code hours (Payroll Hours lines) | 14822 | 14822 | 0 | TIES
Per-worker hours (sum of PR Regular) | 14975 | 14822 | 153 | WITHIN
C. BILLING (SOV) ↔ JDR
Final Contract Value | 1438488.45 | 1369989 | 68499.45 | WITHIN
Retainage | 68499 | 68499 | 0 | TIES
Direct Cost | 859184.33 | 859184.33 | 0 | TIES
D. VENDOR AP ↔ JDR
Vendor AP total (sum of invoices) | 458376.37 | 401446 | 56930.37 | OFF
SOURCES
Job #2017 — Exxel Pacific 3636 Stone Way Apartments • GC: Exxel Pacific, Inc. • Seattle, WA
Canonical source: 2017 Job Detail Report.pdf (124 pages, OWP Sage Timberline export)
Cost codes parsed: 27 (Labor+Material+Overhead+Burden+Revenue)
Unit count: 119 from Job Ticket (119 DWs, 119 washers)
Fixture count: Toto WCs 122, Grohe lavs 137, Aquatic tubs 122, Lenova/Elkay sinks 119 + common area
Billing: 36 STONE AGGREGATE BILLING.xlsx (14 pay apps, Feb 2014 – May 2015)
TIES = within $1 or 5 hrs • WITHIN = within 5% • OFF = investigate

## Vendors
Vendor Detail — Job #2017
Vendors | 20 |  | Top vendor | Consolidated Supply Co.
Invoices | 266 |  | Top 3 share | 84.77%
Total AP | 458376.37 |  | Source | 2017 Job Detail Report.pdf (Sage Timberline AP export)
Avg Inv | 1723.2194
Rank | Vendor | Vendor Code | Invoices | Total Spend | % of AP | Avg / Invoice
1 | Consolidated Supply Co. |  | 102 | 176571.46 | 38.52% | 1731.0927
2 | Rosen Supply Company, Inc. |  | 85 | 139209.01 | 30.37% | 1637.7531
3 | Ferguson Enterprises, Inc. |  | 18 | 72780.98 | 15.88% | 4043.3878
4 | Franklin Engineering |  | 5 | 17974.5 | 3.921% | 3594.9
5 | Duraseal, Inc. |  | 2 | 12800 | 2.792% | 6400
6 | Keller Supply Company |  | 11 | 8131.24 | 1.774% | 739.2036
7 | Bank of America CC |  | 6 | 8076 | 1.762% | 1346
8 | Quality Concrete Products, Inc. |  | 3 | 5921 | 1.292% | 1973.6667
9 | Rosen Supply Kirkland |  | 6 | 4412.21 | 0.9626% | 735.3683
10 | Mechanical Sales, Inc. |  | 2 | 2840 | 0.6196% | 1420
11 | Manor Hardware & Construction Supply |  | 3 | 2465 | 0.5378% | 821.6667
12 | Cascade Restoration Co. |  | 2 | 2140 | 0.4669% | 1070
13 | Kele, Inc |  | 4 | 1340.48 | 0.2924% | 335.12
14 | Core & Main LP |  | 2 | 1134.15 | 0.2474% | 567.075
15 | Ferguson Enterprises, Inc. #3007 |  | 3 | 811.46 | 0.177% | 270.4867
16 | C.M. Hoskins Company |  | 3 | 702.97 | 0.1534% | 234.3233
17 | Structural Imaging, LLC |  | 1 | 500 | 0.1091% | 500
18 | Fastenal Company |  | 4 | 258.11 | 0.05631% | 64.5275
19 | R.A. Brown Backflow Testing |  | 2 | 195 | 0.04254% | 97.5
20 | Capital One Credit Card |  | 2 | 112.8 | 0.02461% | 56.4
| TOTAL |  | 266 | 458376.37 | 100% | 1723.2194