## Match Summary
JCR TEST LABELS — JOB 2107 · MATCH SCORE
Generated 2026-04-27. Live project (no Sam-authored gold version exists). Score is structural completeness against the v2 JCR Cortex workbook + internal data shape. Higher % = richer Test Labels output.
Tab | TL Rows | V2 Rows / Source | Field Coverage | Match % | Notes
Report Record | 21 | Sage JDR identity block | 11 / 21 | 52.4% | 11 project fields populated. 10 are TBD or pending project-attribute input.
Line Items | 9997 | JDR transactions | 9997 / 9997 | 100.0% | 9997 parsed transactions. Full per-transaction granularity available.
Cost Code Summaries | 27 | v2 JCR has 27 codes | 351 / 351 | 100.0% | All 27 cost codes ported with full 13-field schema (code/description/category/budgets/actual/net_due/retainage/REG/OT/DT/Other hours).
Worker Wages | 33 | v2 Crew Roster: 33 workers | 297 / 297 | 100.0% | 33 workers. Schema: name/REG/OT/DT/Other hrs · REG/OT amount · nominal rate · tier.
Derived Fields | 36 | data['derived_fields'] | 36 / 36 | 100.0% | 36 derived calculations available.
Reconciliation | 27 | v2 Reconciliation tab | 27 / 27 | 100.0% | 27 explicit recon rows. Synthesized from cost_code_summaries on build for codes without explicit reconciliation entries.
Reconciliation Log | 1 | (synthesized) | 1 / 1 | 100.0% | 1 synthesized 'initial parse' entry. Future re-parses or reconciliation events would extend this log.
OVERALL ASSESSMENT
Job #2107 — 68th & Roosevelt (Chinn Construction, LLC) — Live project, no Sam-authored gold version. Test Labels output structurally complete vs v2 JCR workbook for cost codes, workers, line items. Project-attribute fields (start date, contract amounts, etc.) populated wherever JDR provides them; pre-construction projects will show TBD where activation hasn't created data yet.

## Cost Code Detail
COST CODE SUMMARIES — Field-by-Field Coverage (27 codes)
Code | Description | Orig Budget | Curr Budget | Plus/Minus | Actual | Net Due | Retain | REG hrs | OT hrs | DT hrs | Other hrs | Match
011 | DS & RD Labor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
100 | Supervision | 12200 | 12700 | -3343 | 9357 | 0 | 0 | 136 | 0 | 0 | 0 | 10 / 10
101 | Takeoff & Purchase Labor | 40260 | 45160 | 2955.5 | 48115.5 | 0 | 0 | 763 | 0 | 0 | 0 | 10 / 10
110 | Underground Labor | 28400 | 30400 | 1075 | 31475 | 0 | 0 | 708 | 0 | 0 | 0 | 10 / 10
111 | Garage Labor | 74554 | 90954 | 62819.75 | 153773.75 | 0 | 0 | 3508.75 | 0 | 0 | 0 | 10 / 10
112 | Canout Labor | 59715 | 59715 | 6691.5 | 66406.5 | 0 | 0 | 1455.5 | 0 | 0 | 0 | 10 / 10
120 | Roughin Labor | 542930 | 565930 | 80380.26 | 646310.26 | 0 | 0 | 14995.5 | 2.5 | 0 | 0 | 10 / 10
130 | Finish Labor | 135784 | 135784 | -135719 | 65 | 0 | 0 | 1 | 0 | 0 | 0 | 10 / 10
140 | Gas Labor | 5400 | 11400 | -3752.25 | 7647.75 | 0 | 0 | 211.75 | 0 | 0 | 0 | 10 / 10
141 | Water Main/Insulation Lab | 172570 | 184270 | -76172.25 | 108097.75 | 0 | 0 | 2553 | 0 | 0 | 0 | 10 / 10
142 | Mech Room Labor | 122400 | 122250 | -93280 | 28970 | 0 | 0 | 642.25 | 0 | 0 | 0 | 10 / 10
210 | Underground Material | 28700 | 29000 | -15142.93 | 13857.07 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
211 | Garage Material | 68005 | 78105 | -23375.93 | 54729.07 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
212 | Canout Material | 51753 | 51753 | -3919.07 | 47833.93 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
220 | Roughin Material | 381860 | 392310 | -182622.58 | 209687.42 | 7489.13 | 0 | 0 | 0 | 0 | 0 | 10 / 10
230 | Finish Material | 1068397 | 1055804 | -509025.35 | 546778.65 | 11744.38 | 0 | 0 | 0 | 0 | 0 | 10 / 10
240 | Gas Material | 5400 | 8500 | -1295.49 | 7204.51 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
241 | Water Main/Insulation Mat | 180900 | 189150 | -51180.74 | 137969.26 | 3746.93 | 0 | 0 | 0 | 0 | 0 | 10 / 10
242 | Mech Room Material | 126000 | 125800 | -43482.64 | 82317.36 | 66602.18 | 0 | 0 | 0 | 0 | 0 | 10 / 10
600 | Subcontractor | 29625 | 34125 | -31852.9 | 2272.1 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
601 | Engineering/Plans | 79300 | 79300 | -69943.75 | 9356.25 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
602 | Rental Equipment | 12000 | 14700 | 485.12 | 15185.12 | 2069.67 | 0 | 0 | 0 | 0 | 0 | 10 / 10
603 | Permits & Licenses | 8000 | 24887 | -8610 | 16277 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
607 | Other Expenses | 15000 | 59817 | -1234.2 | 58582.8 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
995 | Payroll Burden | 487836.01 | 514607.79 | 18195.53 | 532803.32 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
998 | Payroll Taxes | 91357.29 | 96280.07 | -12068.69 | 84211.38 | 0 | 0 | 0 | 0 | 0 | 0 | 10 / 10
999 | Sales | -4671538 | -4889866 | -467655 | -4422211 | -525324.55 | -245731 | 0 | 0 | 0 | 0 | 10 / 10

## Worker Detail
WORKER WAGES — Field-by-Field (33 workers)
Worker | Tier | REG hrs | OT hrs | DT hrs | Other hrs | REG amt | OT amt | Rate ($/hr) | Match
Nunez Bravo, Jose L | JOURNEYMAN | 820.75 | 0 | 0 | 0 | 19698 | 0 | 24 | 9 / 9
Melgar Moz, Brandon | JOURNEYMAN | 1612.25 | 0 | 0 | 0 | 39483.5 | 0 | 24.4897 | 9 / 9
Zuniga Avilez, Eduar A | JOURNEYMAN | 871.25 | 0 | 0 | 0 | 21620 | 0 | 24.8149 | 9 / 9
Suniga Aviles, Kelvin A | JOURNEYMAN | 802.5 | 0 | 0 | 0 | 20130 | 0 | 25.0841 | 9 / 9
Gomez Aguirre, Exequiel | JOURNEYMAN | 239.25 | 0 | 0 | 0 | 6603 | 0 | 27.5987 | 9 / 9
Guerrero Espinoza, Mario | JOURNEYMAN | 87 | 0 | 0 | 0 | 2610 | 0 | 30 | 9 / 9
Cruz, Azael S | JOURNEYMAN | 315.5 | 0 | 0 | 0 | 10096 | 0 | 32 | 9 / 9
Lopez, Maslin A | JOURNEYMAN | 319.5 | 0 | 0 | 0 | 10543.5 | 0 | 33 | 9 / 9
Romero Garza, Jesus I | JOURNEYMAN | 224.75 | 0 | 0 | 0 | 7416.75 | 0 | 33 | 9 / 9
Del Villar, Flabio | JOURNEYMAN | 667.5 | 0 | 0 | 0 | 22430 | 0 | 33.603 | 9 / 9
Chevez, Herson G | LEAD/SUPERVISOR | 833 | 0 | 0 | 0 | 31558 | 0 | 37.8848 | 9 / 9
Jimenez Alvarenga, Gerson M | LEAD/SUPERVISOR | 1253 | 0 | 0 | 0 | 49280 | 0 | 39.3296 | 9 / 9
Mendoza Morales, Jesus A | LEAD/SUPERVISOR | 1175.5 | 0 | 0 | 0 | 48878.5 | 0 | 41.581 | 9 / 9
Hernandez Gonzalez, Osbaldo | LEAD/SUPERVISOR | 1470 | 0 | 0 | 0 | 62225 | 0 | 42.3299 | 9 / 9
Ascencio, Jose L | LEAD/SUPERVISOR | 1465.25 | 0.25 | 0 | 0 | 62033.75 | 15.75 | 42.3366 | 9 / 9
Galdamez, Dagoberto A | LEAD/SUPERVISOR | 1462.5 | 0.25 | 0 | 0 | 61918.25 | 15.75 | 42.3373 | 9 / 9
Martinez Reyes, Juan C | LEAD/SUPERVISOR | 1746 | 0 | 0 | 0 | 76824 | 0 | 44 | 9 / 9
Lima Romero, Melvin A | LEAD/SUPERVISOR | 711 | 0 | 0 | 0 | 31284 | 0 | 44 | 9 / 9
Countryman, Matthew K | LEAD/SUPERVISOR | 1465.5 | 0 | 0 | 0 | 74229.5 | 0 | 50.6513 | 9 / 9
Mackey, Cole J | LEAD/SUPERVISOR | 883 | 0 | 0 | 0 | 45310 | 0 | 51.3137 | 9 / 9
Toscano, Esteban | LEAD/SUPERVISOR | 817.5 | 0 | 0 | 0 | 42050.25 | 0 | 51.4376 | 9 / 9
Cruz Guzman, Joel A | LEAD/SUPERVISOR | 919.5 | 0 | 0 | 0 | 47309 | 0 | 51.4508 | 9 / 9
Johnson, Jake E | LEAD/SUPERVISOR | 168 | 0 | 0 | 0 | 8736 | 0 | 52 | 9 / 9
Taylor, Evan R | LEAD/SUPERVISOR | 184 | 0 | 0 | 0 | 9568 | 0 | 52 | 9 / 9
Castro Hernandez, Jose A | LEAD/SUPERVISOR | 140.5 | 0 | 0 | 0 | 7587 | 0 | 54 | 9 / 9
Draves, Steven W | LEAD/SUPERVISOR | 290.5 | 0 | 0 | 0 | 15977.5 | 0 | 55 | 9 / 9
Eisenhauer, Tommy J | LEAD/SUPERVISOR | 61.25 | 0 | 0 | 0 | 3491.25 | 0 | 57 | 9 / 9
Gerard, Jordan E | LEAD/SUPERVISOR | 179 | 0 | 0 | 0 | 10722.5 | 0 | 59.9022 | 9 / 9
Gerard, Mitchell J | LEAD/SUPERVISOR | 10.5 | 0 | 0 | 0 | 644 | 0 | 61.3333 | 9 / 9
Paco Leyva, Orlando | LEAD/SUPERVISOR | 1309 | 0 | 0 | 0 | 80771.5 | 0 | 61.7047 | 9 / 9
Anderson, Richard P | LEAD/SUPERVISOR | 1884.75 | 2 | 0 | 0 | 118174.25 | 199.51 | 62.7002 | 9 / 9
Barnhart, Joseph N | LEAD/SUPERVISOR | 267.25 | 0 | 0 | 0 | 18378.5 | 0 | 68.7689 | 9 / 9
Gerard, Jeffrey S | LEAD/SUPERVISOR | 478 | 0 | 0 | 0 | 32982 | 0 | 69 | 9 / 9