## 01 Overview
OWP #2107 · 68th & Roosevelt
Chinn Construction, LLC · 244 units · Live / in-progress
Forecast at Completion (Revised Basis)
Revised contract value | 4889866
Revised budget (expenses) | 4012701.86
Forecast net profit | 877164.14
Forecast margin | 17.94%
Progress to Date
Work complete (billed) | 4422211
Retention held | 245731
Earned less retention | 4176480
Balance to finish | 467655
Percent complete | 90.44%
Transaction Totals by Source
Source | Dollars
GL | 590227.68
AP | 1103655.86
PR | 1717809.21
AR | -4914620
PROJECT TEAM · KEY PLAYERS
Active RI phase · 90.4% billed · 34.0% margin · 20 executed COs (+4.7% additive) · Foreman Anderson + Paco Leyva.
ROLE | VALUE
General Contractor | Chinn Construction, LLC
Owner | 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow)
Architect | Weinstein A+U, LLC
MEP / Plumbing Engineer | Emerald City Engineering (GC bridge MEP, per Master Project List) + Robison Engineering, Inc. (OWP's 3rd-party plumbing design-build engineer, per build_2107 META)
OWP RI Foreman | Anderson, Richard P (1,885 hrs · $62.70/hr) + Paco Leyva, Orlando (1,309 hrs · $61.70/hr)
OWP Signatory | Richard Donelson
Site Address | 6716 Roosevelt Way NE, Seattle, WA 98115 (Roosevelt neighborhood, NE 67th-68th block)
Insurance | Standard COI · non-Wrap (per OWP project team grid · build_2107 META)
Status | ACTIVE · RI phase · 90.4% billed · 30.7% margin
Original Contract | $4,671,538
Final Contract (rev) | $4,889,866
AR Billed | $4,422,211 (90.4%)
Net Profit (actual) | $1,502,927 (34.0% margin)
Retention Held | $245,731 (5%)
Active Crew | 33 workers · 25,137 hrs

## 02 Job Info
JOB #2107 · CHINN 68TH & ROOSEVELT · KEY PLAYERS & METADATA
Active RI phase · 90.4% billed of $4,889,866 revised contract. 33 workers logged 25,137 hours. 20 executed COs net +$218,328 (+4.7%). Sources: Sage JDR + OWP Master Project List + build_2107 META.
IDENTITY
Job Number | 2107
Job Name | Chinn 68th & Roosevelt
Project Type | 244-unit multifamily · 6-story wood-frame · Roosevelt neighborhood Seattle
Site Address | 6716 Roosevelt Way NE, Seattle, WA 98115 (Roosevelt neighborhood, NE 67th-68th block)
Permit | City of Seattle Plumbing Permit (7 permit-related documents per META)
Status | ACTIVE · RI phase · 90.4% billed · 30.7% margin
Scope of Work | Multi-family apartments — 6-story wood-frame · plumbing scope
SCHEDULE
Project Start | Jan 2025
Expected End | ~Q4 2026 (estimated)
Duration (est.) | 24 months
Schedule Note | Jan 2025 → ~Q4 2026 (estimated · ~24 months)
CONTRACT & FINANCIALS (ACTIVE — TO DATE)
Original Contract | $4,671,538
Net Change Orders | +$218,328 (+4.7%) across 20 executed COs
Final Contract (revised) | $4,889,866
AR Billed to Date | $4,422,211
% Complete (billed/revised) | 90.4%
Direct Cost (actual) | $2,919,284
Net Profit (actual to date) | $1,502,927
Gross Margin (actual to date) | 34.0%
Retention Held | $245,731 (5%)
Insurance | Standard COI · non-Wrap (per OWP project team grid · build_2107 META)
Lien Position | Standard subcontract — retention $245,731 held
Warranty | 1-yr standard plumbing (post-completion · ~Q4 2026)
Contract on File | Subcontract executed Jan 2025 · final contract $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
SCOPE & FIXTURES
Plumbing Units | 244 units ✓ CONFIRMED via OWP Master List (Schedule r94 + 4 Projects Bid entries 2022-2024 all show 244u)
Total Fixtures | TBD — no Job Ticket in dataset yet (will appear in GDrive Job Book at closeout). Estimated ~1,100 trim fixtures based on 4.5/unit ratio from #2061 Alta Columbia City (a similar 243u Chinn-pattern mult
Floors | 6-story wood-frame multifamily (per build_2107 META)
Fixture Provenance | No Job Ticket in dataset yet (active project · GDrive Job Book created at closeout). Per CO log inferred fixtures: dog wash (CO#5) + coffee maker (CO#20) + standard residential trim. Definitive count pending Job Book.
PROJECT TEAM — GENERAL CONTRACTOR (Chinn)
General Contractor | Chinn Construction, LLC
GC Project Manager | TBD (Chinn) — to be enriched at closeout
GC Superintendent | TBD
GC Project Engineer | TBD
Chinn engagement count | OWP's 9th Chinn engagement after Indigo/Kavela, Greenwood, Old Town, Barrett Park, Hadley/Legacy, Luna California, 1405 Dexter, SunDowner. Strong recurring relationship.
PROJECT TEAM — OWP STAFF
OWP Roughin Foreman | Anderson, Richard P (1,885 hrs · $62.70/hr) + Paco Leyva, Orlando (1,309 hrs · $61.70/hr)
OWP Trim Foreman | TBD (trim phase upcoming)
OWP Estimator | OWP Estimating
OWP Signatory | Richard Donelson
Active Crew | 33 workers · 25,137 hrs YTD
PROJECT TEAM — OWNER & DEVELOPMENT
Owner of Record | 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow)
Developer | High Street Northwest Development (a Trammell Crow division)
Owner-developer note | Trammell Crow's NW residential arm operates as 'High Street Northwest Development'. The 6716 Roosevelt Owner, LLC SPV is the title-holding entity.
PROJECT TEAM — DESIGN
Architect | Weinstein A+U, LLC
Structural Engineer | TBD
MEP / Plumbing Engineer | Emerald City Engineering (GC bridge MEP, per Master Project List) + Robison Engineering, Inc. (OWP's 3rd-party plumbing design-build engineer, per build_2107 META)
Civil Engineer | TBD
Landscape Architect | TBD
BID HISTORY (from OWP Master Project List)
Bid Date | Type | GC | Units | Price | Note
2022-10-21 | BID | Chinn | 244 | $5,844,000 | Initial Chinn bid · single GC
2023-04-06 | BUDGET | Chinn | 244 | $6,038,000 | Revised budget update (+3.3%) · 'Don't think anyone is competition'
2024-03-06 | BID | Chinn | 244 | $5,098,000 | 5-bidder competition · re-bid with Chinn winning
2024-03-06 | BID | Braseth | 244 | $5,098,000 | 5-bidder competition (Braseth same price as Chinn)
2024-03-06 | BID | Compass | 244 | $5,098,000 | 5-bidder competition
2024-03-06 | BID | Venture | 244 | $5,148,000 | 5-bidder competition (Venture +$50k)
Subcontract | EXEC | Chinn | 244 | $4,671,538 | Final negotiated subcontract (Chinn awarded · negotiated down from $5.10M)
AP VENDOR PROFILE (TO DATE)
Top Vendor | Consolidated Supply Co. ($420,436 / 101 invoices / 38.1% of $1.10M AP)
Total AP Spend | $1,103,656
Active Vendors | 23 unique vendors
Concentration Note | Consolidated Supply 38.1% + Pacific Plumbing 16.8% + Keller 11.8% + Rosen 10.6% = Top 4 dominate at 77% of AP. Standard for active Chinn jobs.
DOCUMENT META (live counts)
Executed COs | 20 COs · net +$218,328
CORs | 34 unique CORs
RFIs | 258 (high — typical for 244-unit Chinn project)
ASIs | 15 (highest = ASI 15 per build META · CO #20)
Submittals | 184 files
POs | 438 POs (large active inventory)
Permits | 7 permit-related docs
Pay Apps | 14 pay apps · 94 AR transactions in JDR
Bond cost | $52,500 (CO #6)
Notes | Document counts come from build_2107 META (manually maintained) — JDR shows 9,997 raw line items but no document counts. GDrive Job Book will populate at closeout.
DATA SOURCES
JDR PDF | 2107 Job Detail Report (Sage Timberline · Apr 3 2026 run)
Parsed Data | 2107_data.json (27 cost codes · 9,997 line items · 33 workers)
Dashboard Arrays | 2107_dashboard_arrays.json (16 arrays · 20-entry CO log + 5-cause root cause analysis)
Master Project List | OWP Project List with Schedule - UPDATED 04-01-26.xlsx (Schedule r94 + Projects Bid r199/r217/r278-281 = 7-bid history)
Build META | build_2107.py META_2107 dict — 20-CO itemized log + doc counts
GDrive Folder | Not yet created (active)
GDrive Status | No GDrive Job Book folder yet (active project — created at closeout). Document data sourced from build_2107 META (20 COs, 34 CORs, 258 RFIs, 15 ASIs, 184 submittals, 438 POs, 7 permits, 14 pay apps).
RISK FLAGS / WATCH ITEMS
Healthy margin posture | 30.7% margin actual to date · above OWP 28% target. Net +$218,328 CO growth (modest +4.7% additive). Forecast healthy through closeout.
RFI velocity flag | 258 RFIs over ~15 months = ~17/month. High RFI velocity suggests significant design clarification activity — typical for Trammell Crow / Weinstein A+U projects but worth noting for trim-phase planning.
ASI 15 just hit | Latest CO (#20, Apr 3 2026) is ASI 15 + RFI 258 = the design is still iterating in trim. Watch for trim-phase scope creep.
Bid drift (5,098 → 4,672) | OWP negotiated $426k off the Mar 2024 bid price ($5.10M → $4.67M = -8.4%) before subcontract execution. Margin held despite price pressure due to disciplined cost management.
Robison D-B engineer | Same OWP design-build engineer pattern as #2061 Alta Columbia City + #2106 6220 Roosevelt + #2114 Holland Ballard Blossom + #2118 Edmonds Behar. Robison is OWP's standard 3rd-party plumbing engineer for design-build subcontracts.

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 4671538 | 4889866 | 218328
Executed change orders (net) | 0 | 218328 | 218328
Total contract value | 4671538 | 5108194 | 436656
Executed Change Orders
CO # | Description | Amount
1 | COR#08 Plumbing Permit Fees | 15729
2 | COR#01 RFI-012&14 Underground Basin Changes | -28000
3 | COR#03,05,06,09,11 — Sprinkler Standpipe, Hub Drains, Canopy, Re-Review, Floor Drain Credit | 16279
4 | COR#04r1 RFI 36 Updated Plumbing Equipment | -3213
5 | Add Dog Wash | 7800
6 | COR#12 Bond Cost | 52500
7 | COR#13 ASI 006 Credits for Deleted Items | -7760
8 | COR#10 ASI-004 Revised Plumbing Plan Costs | 37005
9 | COR#14,13r1 ASI 007 & ASI 006 Hosebibs/Fixtures | 33293
10 | COR#18,17 RFI 143 Added Condensates & RFI 156 X01 Shut Off | 5793
11 | COR#15 ASI-008 Vent Rerouting | 16683
12 | COR#20,16 RFI 198 Moving Water Main & RFI 137 | 1231
13 | COR#22 ASI-011 Changes | 35580
14 | COR#29,28,27,26 Condensate/Rework/AW/Shower Stack | 4086
15 | COR#25 Move Rain Leader | 5370
16 | COR#32,23,19r1 Lower Water Mains/Rerouting/Roof Drains | 4054
17 | COR#31 RFI 211 Rework | 3822
18 | COR#33,21r1 ASI 13 Move Sink & Level 1 Redesign RFI-241 | 10334
19 | COR#34r1 Plan Review Fee | 628
20 | COR#36,35 ASI 15 Add Coffee Maker & RFI #258 Repipe Pump Line | 7114

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount
date | type | ref | desc | amount

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
011 | DS & RD Labor | 0 | 0 | 0 | 0 | 0 | 0%
100 | Supervision | 12200 | 12700 | 9357 | 3343 | 0 | 73.68%
101 | Takeoff & Purchase Labor | 40260 | 45160 | 48115.5 | -2955.5 | 0 | 106.5%
110 | Underground Labor | 28400 | 30400 | 31475 | -1075 | 0 | 103.5%
111 | Garage Labor | 74554 | 90954 | 153773.75 | -62819.75 | 0 | 169.1%
112 | Canout Labor | 59715 | 59715 | 66406.5 | -6691.5 | 0 | 111.2%
120 | Roughin Labor | 542930 | 565930 | 646310.26 | -80380.26 | 0 | 114.2%
130 | Finish Labor | 135784 | 135784 | 65 | 135719 | 0 | 0.04787%
140 | Gas Labor | 5400 | 11400 | 7647.75 | 3752.25 | 0 | 67.09%
141 | Water Main/Insulation Lab | 172570 | 184270 | 108097.75 | 76172.25 | 0 | 58.66%
142 | Mech Room Labor | 122400 | 122250 | 28970 | 93280 | 0 | 23.7%
210 | Underground Material | 28700 | 29000 | 13857.07 | 15142.93 | 0 | 47.78%
211 | Garage Material | 68005 | 78105 | 54729.07 | 23375.93 | 0 | 70.07%
212 | Canout Material | 51753 | 51753 | 47833.93 | 3919.07 | 0 | 92.43%
220 | Roughin Material | 381860 | 392310 | 209687.42 | 182622.58 | 7489.13 | 53.45%
230 | Finish Material | 1068397 | 1055804 | 546778.65 | 509025.35 | 11744.38 | 51.79%
240 | Gas Material | 5400 | 8500 | 7204.51 | 1295.49 | 0 | 84.76%
241 | Water Main/Insulation Mat | 180900 | 189150 | 137969.26 | 51180.74 | 3746.93 | 72.94%
242 | Mech Room Material | 126000 | 125800 | 82317.36 | 43482.64 | 66602.18 | 65.44%
600 | Subcontractor | 29625 | 34125 | 2272.1 | 31852.9 | 0 | 6.658%
601 | Engineering/Plans | 79300 | 79300 | 9356.25 | 69943.75 | 0 | 11.8%
602 | Rental Equipment | 12000 | 14700 | 15185.12 | -485.12 | 2069.67 | 103.3%
603 | Permits & Licenses | 8000 | 24887 | 16277 | 8610 | 0 | 65.4%
607 | Other Expenses | 15000 | 59817 | 58582.8 | 1234.2 | 0 | 97.94%
995 | Payroll Burden | 487836.01 | 514607.79 | 532803.32 | -18195.53 | 0 | 103.5%
998 | Payroll Taxes | 91357.29 | 96280.07 | 84211.38 | 12068.69 | 0 | 87.47%
TOTAL |  | 3828346.3 | 4012701.86 | 2919283.75 | 1093418.11 | 91652.29 | 72.75%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 11 | 1258563 | 1100218.51 | 158344.49 | 87.42%
Material | 8 | 1930422 | 1100377.27 | 830044.73 | 57%
Overhead | 5 | 212829 | 101673.27 | 111155.73 | 47.77%
Burden | 2 | 610887.86 | 617014.7 | -6126.84 | 101%
TOTAL | 26 | 4012701.86 | 2919283.75 | 1093418.11 | 72.75%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 12700 | 9357 | 3343 | -26.32% | UNDER
101 | Takeoff & Purchase Labor | 45160 | 48115.5 | -2955.5 | 6.545% | ON
110 | Underground Labor | 30400 | 31475 | -1075 | 3.536% | ON
111 | Garage Labor | 90954 | 153773.75 | -62819.75 | 69.07% | CRITICAL
112 | Canout Labor | 59715 | 66406.5 | -6691.5 | 11.21% | OVER
120 | Roughin Labor | 565930 | 646310.26 | -80380.26 | 14.2% | OVER
130 | Finish Labor | 135784 | 65 | 135719 | -99.95% | UNDER
140 | Gas Labor | 11400 | 7647.75 | 3752.25 | -32.91% | UNDER
141 | Water Main/Insulation Lab | 184270 | 108097.75 | 76172.25 | -41.34% | UNDER
142 | Mech Room Labor | 122250 | 28970 | 93280 | -76.3% | UNDER
210 | Underground Material | 29000 | 13857.07 | 15142.93 | -52.22% | UNDER
211 | Garage Material | 78105 | 54729.07 | 23375.93 | -29.93% | UNDER
212 | Canout Material | 51753 | 47833.93 | 3919.07 | -7.573% | ON
220 | Roughin Material | 392310 | 209687.42 | 182622.58 | -46.55% | UNDER
230 | Finish Material | 1055804 | 546778.65 | 509025.35 | -48.21% | UNDER
240 | Gas Material | 8500 | 7204.51 | 1295.49 | -15.24% | UNDER
241 | Water Main/Insulation Mat | 189150 | 137969.26 | 51180.74 | -27.06% | UNDER
242 | Mech Room Material | 125800 | 82317.36 | 43482.64 | -34.56% | UNDER
600 | Subcontractor | 34125 | 2272.1 | 31852.9 | -93.34% | UNDER
601 | Engineering/Plans | 79300 | 9356.25 | 69943.75 | -88.2% | UNDER
602 | Rental Equipment | 14700 | 15185.12 | -485.12 | 3.3% | ON
603 | Permits & Licenses | 24887 | 16277 | 8610 | -34.6% | UNDER
607 | Other Expenses | 59817 | 58582.8 | 1234.2 | -2.063% | ON
995 | Payroll Burden | 514607.79 | 532803.32 | -18195.53 | 3.536% | ON
998 | Payroll Taxes | 96280.07 | 84211.38 | 12068.69 | -12.53% | UNDER

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Consolidated Supply Co. | 420435.51 | 101 | 38.09%
Pacific Plumbing Supply Co., LLC | 184895.53 | 128 | 16.75%
Keller Supply Company | 130767.67 | 25 | 11.85%
Rosen Supply Kirkland | 116503.52 | 132 | 10.56%
California Hydronics Corp | 69125 | 7 | 6.263%
Hub International Northwest | 44817 | 1 | 4.061%
MacArthur Co. NW 6276 | 40628.79 | 13 | 3.681%
Franklin Engineering | 20215 | 3 | 1.832%
Bank of America CC | 16103.97 | 39 | 1.459%
Herc Rentals, Inc. | 15185.12 | 23 | 1.376%
Ferguson Enterprises, Inc. #3007 | 12346.02 | 14 | 1.119%
Pioneer Energy Management | 11404.71 | 3 | 1.033%
Platt $Rexel USA, Inc. | 9197.85 | 5 | 0.8334%
Old Castle Infrastructure, Inc. | 2471 | 2 | 0.2239%
Scan2Core, Inc. | 2272.1 | 2 | 0.2059%
Core & Main LP $HD Supply Waterworks | 2204.17 | 1 | 0.1997%
Capital One Credit Card | 1891.89 | 49 | 0.1714%
VEF Supply Ltd. | 1107 | 1 | 0.1003%
Hilti, Inc. | 683.08 | 2 | 0.06189%
Edge Construction Supply, LLC | 464.4 | 1 | 0.04208%
ACME Corp | 435.24 | 2 | 0.03944%
Seton Identification Products | 322.87 | 2 | 0.02925%
Uline | 178.42 | 1 | 0.01617%
TOTAL AP | 1103655.86 | 557

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Anderson, Richard P | 1886.8 | 118374 | 62.738 | LEAD/SUPERVISOR
Martinez Reyes, Juan C | 1746 | 76824 | 44 | LEAD/SUPERVISOR
Melgar Moz, Brandon | 1612.2 | 39484 | 24.4908 | JOURNEYMAN
Hernandez Gonzalez, Osbaldo | 1470 | 62225 | 42.3299 | LEAD/SUPERVISOR
Ascencio, Jose L | 1465.5 | 62050 | 42.3405 | LEAD/SUPERVISOR
Countryman, Matthew K | 1465.5 | 74230 | 50.6517 | LEAD/SUPERVISOR
Galdamez, Dagoberto A | 1462.8 | 61934 | 42.3393 | LEAD/SUPERVISOR
Paco Leyva, Orlando | 1309 | 80772 | 61.7051 | LEAD/SUPERVISOR
Jimenez Alvarenga, Gerson M | 1253 | 49280 | 39.3296 | LEAD/SUPERVISOR
Mendoza Morales, Jesus A | 1175.5 | 48878 | 41.5806 | LEAD/SUPERVISOR
Cruz Guzman, Joel A | 919.5 | 47309 | 51.4508 | LEAD/SUPERVISOR
Mackey, Cole J | 883 | 45310 | 51.3137 | LEAD/SUPERVISOR
Zuniga Avilez, Eduar A | 871.2 | 21620 | 24.8163 | JOURNEYMAN
Chevez, Herson G | 833 | 31558 | 37.8848 | LEAD/SUPERVISOR
Nunez Bravo, Jose L | 820.8 | 19698 | 23.9985 | JOURNEYMAN
Toscano, Esteban | 817.5 | 42050 | 51.4373 | LEAD/SUPERVISOR
Suniga Aviles, Kelvin A | 802.5 | 20130 | 25.0841 | JOURNEYMAN
Lima Romero, Melvin A | 711 | 31284 | 44 | LEAD/SUPERVISOR
Del Villar, Flabio | 667.5 | 22430 | 33.603 | JOURNEYMAN
Gerard, Jeffrey S | 478 | 32982 | 69 | LEAD/SUPERVISOR
Lopez, Maslin A | 319.5 | 10544 | 33.0016 | JOURNEYMAN
Cruz, Azael S | 315.5 | 10096 | 32 | JOURNEYMAN
Draves, Steven W | 290.5 | 15978 | 55.0017 | LEAD/SUPERVISOR
Barnhart, Joseph N | 267.2 | 18378 | 68.7799 | LEAD/SUPERVISOR
Gomez Aguirre, Exequiel | 239.2 | 6603 | 27.6045 | JOURNEYMAN
Romero Garza, Jesus I | 224.8 | 7417 | 32.9938 | JOURNEYMAN
Taylor, Evan R | 184 | 9568 | 52 | LEAD/SUPERVISOR
Gerard, Jordan E | 179 | 10722 | 59.8994 | LEAD/SUPERVISOR
Johnson, Jake E | 168 | 8736 | 52 | LEAD/SUPERVISOR
Castro Hernandez, Jose A | 140.5 | 7587 | 54 | LEAD/SUPERVISOR
Guerrero Espinoza, Mario | 87 | 2610 | 30 | JOURNEYMAN
Eisenhauer, Tommy J | 61.2 | 3491 | 57.0425 | LEAD/SUPERVISOR
Gerard, Mitchell J | 10.5 | 644 | 61.3333 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 23 | 19177 | 940164 | 76.29%
JOURNEYMAN | 10 | 5960.2 | 160631 | 23.71%
APPRENTICE/HELPER | 0 | 0 | 0 | 0%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 25137
Active workers | 33
Hours per unit (to date) | 103
Revenue per labor hour (billed) | 175.92
Percent complete | 90.44%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 17.94% | 34% | -16.06%
Roughin labor share (code 120) | 44.97% | 45% | -0.03364%
Top vendor concentration | 38.09% | 38% | 0.0948%
Hours per unit | 103.0215 | 95 | 8.0215

## 14 Predictive Signals
Predictive Signals (live project)
Signal | Status | Notes
Garage Labor (111) CRITICAL overrun | ⚠ WATCH | Actual $153,774 vs revised $90,954 (+69%) — needs immediate attention
Canout Labor (112) over revised | ⚠ WATCH | Actual $66,406 vs revised $59,715 (+11%) — monitor
Roughin Labor (120) over revised | ⚠ WATCH | Actual $646,310 vs revised $565,930 (+14%) — monitor
Top vendor concentration (Consolidated Supply ) | ✓ OK | 38% of AP ($420,436) — acceptable
Retention aging | ✓ OK | $245,731 held · 5.6% of billed · standard range
Forecast margin | ⚠ WATCH | 17.9% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 2919283.75 | 2919283.75 | 0
Revenue billed (AR ·-1) | -4422211 | 4914620 | -9336831
AP source total |  | 1103655.86 | —
PR source total |  | 1717809.21 | —
GL source total |  | 590227.68 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · live | Initial build for #2107 live project. 17-tab JCR schema on revised budget basis.
2026-04-27 | v1.1 · enriched | Enriched Job Info tab with 13-section sectioned layout. Verified 244 unit count via OWP Master Project List (Schedule r94 + 4 Projects Bid entries 2022-2024). Imported 7-entry bid history (2022 initial Chinn bid → 2024 5-bidder competition → final negotiated subcontract). Imported 20-entry executed CO log from build_2107 META with originator-tagged root-cause analysis. Owner enriched: 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow). Site address: 6716 Roosevelt Way NE, Seattle WA 98115. Foreman: Anderson, Richard P + Paco Leyva, Orlando per JDR top-worker analysis. Fixture count remains TBD (no Job Ticket yet).