## Overview
Job #2107 · Chinn 68th & Roosevelt
Cortex JCR Summary • Chinn Construction, LLC (Owner: 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow))
PROJECT OVERVIEW
Project Job # | 2107
Project Name: | Chinn 68th & Roosevelt
General Contractor | Chinn Construction, LLC (Owner: 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow))
Location | 6716 Roosevelt Way NE, Seattle, WA 98115
Project Duration | Jan 2025 – Q4 2026 (estimated) (~24 months · active RI phase)
Status | ACTIVE · RI phase · 90.4% billed · 30.7% margin
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$4,889,866 |  | $1,970,582 |  | $2,919,284 |  | 25,137
$4,671,538 orig + $218,328 COs |  | 40.3% margin |  | 59.7% of revenue |  | 33 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 1258562 | 1100219 | 158343 | 0.87419 | 0.37688
Material | 1922036 | 1100377 | 821659 | 0.57251 | 0.37693
Overhead | 212829 | 101673 | 111156 | 0.47772 | 0.034828
Burden | 610888 | 617015 | -6127 | 1.01 | 0.21136
TOTAL | 4004315 | 2919284 | 1085031 | 0.72903 | 1
PROJECT PROFILE
Plumbing Units | 244 | Total Fixtures | TBD (no Job Ticket yet) | Fixtures / Unit | Estimated ~4.5 (per #2061 Chinn-pattern benchmark)
GC | Chinn Construction, LLC | Owner | 6716 Roosevelt Owner, LLC / High Street Northwest Development (Trammell Crow) | Insurance | Standard COI
Status | ACTIVE · RI phase · 90.4% billed · 30.7% margin | Duration | ~24 months · active RI phase | Permit | City of Seattle Plumbing Permit (7 docs in build META)
NARRATIVE
Active RI-phase project in Seattle's Roosevelt corridor. 244-unit multifamily for High Street Northwest Development (Trammell Crow's NW residential arm). Won via 5-bidder competition Mar 2024 (Chinn, Braseth, Compass, Venture, +1 unnamed all bid $5,098,000) — Chinn negotiated down to final $4,671,538 subcontract. To date OWP has billed $4,422,211 (90.4% complete) with $1,502,927 net profit = 30.7% margin actual — above the 28% target. 20 executed COs net +$218,328 (+4.7% additive — modest, healthy posture). 258 RFIs (high — typical Trammell Crow / Weinstein A+U pattern) + 15 ASIs + 34 CORs. Foreman Anderson, Richard P (1,885 hrs at $62.70/hr) + Paco Leyva, Orlando (1,309 hrs at $61.70/hr). 33 workers logged 25,137 hrs. Top vendor Consolidated Supply 38.1% of $1.10M AP. OWP's 9th Chinn engagement. Robison Engineering is the 3rd-party plumbing design-build engineer (recurring with Chinn jobs).
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 0 | 0 | 0 | 0 | 0
100 | Supervision | 12700 | 12700 | 9357 | 3343 | 0.73677
101 | Takeoff & Purchase Labor | 45160 | 45160 | 48116 | -2956 | 1.0655
110 | Underground Labor | 30400 | 30400 | 31475 | -1075 | 1.0354
111 | Garage Labor | 90954 | 90954 | 153774 | -62820 | 1.6907
112 | Canout Labor | 59715 | 59715 | 66406 | -6691 | 1.112
120 | Roughin Labor | 565930 | 565930 | 646310 | -80380 | 1.142
130 | Finish Labor | 135784 | 135784 | 65 | 135719 | 0.0004787
140 | Gas Labor | 11400 | 11400 | 7648 | 3752 | 0.67088
141 | Water Main/Insulation Lab | 184270 | 184270 | 108098 | 76172 | 0.58663
142 | Mech Room Labor | 122250 | 122250 | 28970 | 93280 | 0.23697
MATERIAL
210 | Underground Material | 29000 | 29000 | 13857 | 15143 | 0.47783
211 | Garage Material | 78105 | 78105 | 54729 | 23376 | 0.70071
212 | Canout Material | 51753 | 51753 | 47834 | 3919 | 0.92427
220 | Roughin Material | 392310 | 392310 | 209687 | 182623 | 0.53449
230 | Finish Material | 1055804 | 1055804 | 546779 | 509025 | 0.51788
240 | Gas Material | 8500 | 8500 | 7205 | 1295 | 0.84765
241 | Water Main/Insulation Mat | 189150 | 189150 | 137969 | 51181 | 0.72942
242 | Mech Room Material | 125800 | 125800 | 82317 | 43483 | 0.65435
OVERHEAD
600 | Subcontractor | 34125 | 34125 | 2272 | 31853 | 0.066579
601 | Engineering/Plans | 79300 | 79300 | 9356 | 69944 | 0.11798
602 | Rental Equipment | 14700 | 14700 | 15185 | -485 | 1.033
603 | Permits & Licenses | 24887 | 24887 | 16277 | 8610 | 0.65404
607 | Other Expenses | 59817 | 59817 | 58583 | 1234 | 0.97937
BURDEN
995 | Payroll Burden | 514608 | 514608 | 532803 | -18195 | 1.0354
998 | Payroll Taxes | 96280 | 96280 | 84211 | 12069 | 0.87465
TOTAL Direct Cost |  | 2919284 | 2919284 | 2919284
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 11 | 1258563 | 1100219 | 158344 | 0.87419 | 0.37688
Material | 8 | 1930422 | 1100377 | 830045 | 0.57002 | 0.37693
Overhead | 5 | 212829 | 101673 | 111156 | 0.47772 | 0.034828
Burden | 2 | 610888 | 617015 | -6127 | 1.01 | 0.21136
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 565930 | 646310 | 80380 | 0.14203
111 | Garage Labor | 90954 | 153774 | 62820 | 0.69068
995 | Payroll Burden | 514608 | 532803 | 18195 | 0.035357
112 | Canout Labor | 59715 | 66406 | 6691 | 0.11205
101 | Takeoff & Purchase Labor | 45160 | 48116 | 2956 | 0.065456
110 | Underground Labor | 30400 | 31475 | 1075 | 0.035362
602 | Rental Equipment | 14700 | 15185 | 485 | 0.032993
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 1055804 | 546779 | 509025 | 0.48212
220 | Roughin Material | 392310 | 209687 | 182623 | 0.46551
130 | Finish Labor | 135784 | 65 | 135719 | 0.99952
142 | Mech Room Labor | 122250 | 28970 | 93280 | 0.76303
141 | Water Main/Insulation Lab | 184270 | 108098 | 76172 | 0.41337
601 | Engineering/Plans | 79300 | 9356 | 69944 | 0.88202
241 | Water Main/Insulation Mat | 189150 | 137969 | 51181 | 0.27058
242 | Mech Room Material | 125800 | 82317 | 43483 | 0.34565
600 | Subcontractor | 34125 | 2272 | 31853 | 0.93342
211 | Garage Material | 78105 | 54729 | 23376 | 0.29929
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Material
Material Spend Analysis
8 material cost codes • $1,100,377 JDR material • 23 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
210 | Underground Material | 29000 | 13857 | 15143 | 0.47783 | 0.012593
211 | Garage Material | 78105 | 54729 | 23376 | 0.70071 | 0.049737
212 | Canout Material | 51753 | 47834 | 3919 | 0.92427 | 0.043471
220 | Roughin Material | 392310 | 209687 | 182623 | 0.53449 | 0.19056
230 | Finish Material | 1055804 | 546779 | 509025 | 0.51788 | 0.4969
240 | Gas Material | 8500 | 7205 | 1295 | 0.84765 | 0.0065478
241 | Water Main/Insulation Mat | 189150 | 137969 | 51181 | 0.72942 | 0.12538
242 | Mech Room Material | 125800 | 82317 | 43483 | 0.65435 | 0.074808
TOTAL | All Material | 1930422 | 1100377 | 830045 | 0.57002 | 1
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Consolidated Supply Co. | 101 | 420436 | 0.38095
Pacific Plumbing Supply Co., LLC | 128 | 184896 | 0.16753
Keller Supply Company | 25 | 130768 | 0.11849
Rosen Supply Kirkland | 132 | 116504 | 0.10556
California Hydronics Corp | 7 | 69125 | 0.062633
Hub International Northwest | 1 | 44817 | 0.040608
MacArthur Co. NW 6276 | 13 | 40629 | 0.036813
Franklin Engineering | 3 | 20215 | 0.018316
Bank of America CC | 39 | 16104 | 0.014591
Herc Rentals, Inc. | 23 | 15185 | 0.013759
Ferguson Enterprises, Inc. #3007 | 14 | 12346 | 0.011186
Pioneer Energy Management | 3 | 11405 | 0.010334
Platt $Rexel USA, Inc. | 5 | 9198 | 0.0083341
Old Castle Infrastructure, Inc. | 2 | 2471 | 0.0022389
Scan2Core, Inc. | 2 | 2272 | 0.0020586
Core & Main LP $HD Supply Waterworks | 1 | 2204 | 0.001997
Capital One Credit Card | 49 | 1892 | 0.0017143
VEF Supply Ltd. | 1 | 1107 | 0.001003
Hilti, Inc. | 2 | 683 | 0.00061885
Edge Construction Supply, LLC | 1 | 464 | 0.00042042
ACME Corp | 2 | 435 | 0.00039414
Seton Identification Products | 2 | 323 | 0.00029266
Uline | 1 | 178 | 0.00016128
TOTAL | 557 | 1103657 | 1
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Anderson, Richard P | 1886.8 | 118374 | 62.738 | Senior
Martinez Reyes, Juan C | 1746 | 76824 | 44 | Mid
Melgar Moz, Brandon | 1612.2 | 39484 | 24.4908 | Apprentice
Hernandez Gonzalez, Osbaldo | 1470 | 62225 | 42.3299 | Mid
Countryman, Matthew K | 1465.5 | 74230 | 50.6517 | Senior
Ascencio, Jose L | 1465.5 | 62050 | 42.3405 | Mid
Galdamez, Dagoberto A | 1462.8 | 61934 | 42.3393 | Mid
Paco Leyva, Orlando | 1309 | 80772 | 61.7051 | Senior
Jimenez Alvarenga, Gerson M | 1253 | 49280 | 39.3296 | Mid
Mendoza Morales, Jesus A | 1175.5 | 48878 | 41.5806 | Mid
Cruz Guzman, Joel A | 919.5 | 47309 | 51.4508 | Senior
Mackey, Cole J | 883 | 45310 | 51.3137 | Senior
Zuniga Avilez, Eduar A | 871.2 | 21620 | 24.8163 | Apprentice
Chevez, Herson G | 833 | 31558 | 37.8848 | Mid
Nunez Bravo, Jose L | 820.8 | 19698 | 23.9985 | Apprentice
Toscano, Esteban | 817.5 | 42050 | 51.4373 | Senior
Suniga Aviles, Kelvin A | 802.5 | 20130 | 25.0841 | Apprentice
Lima Romero, Melvin A | 711 | 31284 | 44 | Mid
Del Villar, Flabio | 667.5 | 22430 | 33.603 | Mid
Gerard, Jeffrey S | 478 | 32982 | 69 | Senior
Lopez, Maslin A | 319.5 | 10544 | 33.0016 | Mid
Cruz, Azael S | 315.5 | 10096 | 32 | Mid
Draves, Steven W | 290.5 | 15978 | 55.0017 | Senior
Barnhart, Joseph N | 267.2 | 18378 | 68.7799 | Senior
Gomez Aguirre, Exequiel | 239.2 | 6603 | 27.6045 | Apprentice
Romero Garza, Jesus I | 224.8 | 7417 | 32.9938 | Mid
Taylor, Evan R | 184 | 9568 | 52 | Senior
Gerard, Jordan E | 179 | 10722 | 59.8994 | Senior
Johnson, Jake E | 168 | 8736 | 52 | Senior
Castro Hernandez, Jose A | 140.5 | 7587 | 54 | Senior
Guerrero Espinoza, Mario | 87 | 2610 | 30 | Mid
Eisenhauer, Tommy J | 61.2 | 3491 | 57.0425 | Senior
Gerard, Mitchell J | 10.5 | 644 | 61.3333 | Senior
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 15 | 9060.2 | 516131 | 36.0%
Mid | 13 | 11731.1 | 477130 | 46.7%
Apprentice | 5 | 4345.9 | 107535 | 17.3%
B. WAGE STATISTICS
Blended labor rate ($/hr) | 43.79
Foreman labor rate ($/hr) | 69
Burden multiplier | 1
Min wage ($/hr) | 24
Max wage ($/hr) | 69
Avg hours per worker | 761.7
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
Supervision | 100 | 136 | 0.5% | 0.56
Takeoff & Purchasing | 101 | 763 | 3.1% | 3.13
Underground | 110 | 708 | 2.8% | 2.9
Garage | 111 | 3508.8 | 14.0% | 14.38
Canout | 112 | 1455.5 | 5.8% | 5.97
Roughin | 120 | 14998 | 60.1% | 61.47
Finish | 130 | 1 | 0.0% | 0
Gas | 140 | 211.8 | 0.8% | 0.87
Water Main/Insulation | 141 | 2553 | 10.2% | 10.46
Mech Room | 142 | 642.2 | 2.6% | 2.63
TOTAL |  | 24977.3
PRODUCTIVITY RATIOS
Revenue per unit | $20,040
Direct cost per unit | $11,964
Hours per unit | 102.37
Revenue per hour | $196
Profit per hour | $79
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Consolidated Supply Co. | 101 | 420436 | 38.1% | Top 5
2 | Pacific Plumbing Supply Co., LLC | 128 | 184896 | 16.8% | Top 5
3 | Keller Supply Company | 25 | 130768 | 11.8% | Top 5
4 | Rosen Supply Kirkland | 132 | 116504 | 10.6% | Top 5
5 | California Hydronics Corp | 7 | 69125 | 6.3% | Top 5
6 | Hub International Northwest | 1 | 44817 | 4.1% | Top 10
7 | MacArthur Co. NW 6276 | 13 | 40629 | 3.7% | Top 10
8 | Franklin Engineering | 3 | 20215 | 1.8% | Top 10
9 | Bank of America CC | 39 | 16104 | 1.5% | Top 10
10 | Herc Rentals, Inc. | 23 | 15185 | 1.4% | Top 10
11 | Ferguson Enterprises, Inc. #3007 | 14 | 12346 | 1.1% | Long tail
12 | Pioneer Energy Management | 3 | 11405 | 1.0% | Long tail
13 | Platt $Rexel USA, Inc. | 5 | 9198 | 0.8% | Long tail
14 | Old Castle Infrastructure, Inc. | 2 | 2471 | 0.2% | Long tail
15 | Scan2Core, Inc. | 2 | 2272 | 0.2% | Long tail
16 | Core & Main LP $HD Supply Waterworks | 1 | 2204 | 0.2% | Long tail
17 | Capital One Credit Card | 49 | 1892 | 0.2% | Long tail
18 | VEF Supply Ltd. | 1 | 1107 | 0.1% | Long tail
19 | Hilti, Inc. | 2 | 683 | 0.1% | Long tail
20 | Edge Construction Supply, LLC | 1 | 464 | 0.0% | Long tail
21 | ACME Corp | 2 | 435 | 0.0% | Long tail
22 | Seton Identification Products | 2 | 323 | 0.0% | Long tail
23 | Uline | 1 | 178 | 0.0% | Long tail
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $0
Net Change Orders | $0
Final Contract | $0
Retainage Held | $0
Net Paid to OWP | $4,422,211
PAY APPLICATION HISTORY
Pay App # | Date | This Period | Retainage | Net | Cumulative | % Contract
1 | 01/20/26 | 31040 | -1552 | 31040 | 31040 | 0.7%
2 | 01/20/26 | 142000 | -7100 | 142000 | 173040 | 3.9%
3 | 01/20/26 | 6120 | -306 | 6120 | 179160 | 4.0%
4 | 01/20/26 | 35470 | -1774 | 35470 | 214630 | 4.9%
5 | 01/20/26 | 106410 | -5320 | 106410 | 321040 | 7.3%
6 | 01/20/26 | 70940 | -3547 | 70940 | 391980 | 8.9%
7 | 01/20/26 | 27300 | -1365 | 27300 | 419280 | 9.5%
8 | 01/20/26 | 3213 | 161 | 3213 | 422493 | 9.6%
9 | 01/20/26 | 7760 | 388 | 7760 | 430253 | 9.7%
10 | 01/20/26 | 6467 | -323 | 6467 | 436720 | 9.9%
11 | 01/20/26 | 5400 | -270 | 5400 | 442120 | 10.0%
12 | 01/20/26 | 6351 | 318 | 6351 | 448471 | 10.1%
13 | 01/20/26 | 6035 | -302 | 6035 | 454506 | 10.3%
14 | 01/20/26 | 608 | -30 | 608 | 455114 | 10.3%
15 | 01/20/26 | 28464 | -1423 | 28464 | 483578 | 10.9%
16 | 01/20/26 | 4054 | -203 | 4054 | 487632 | 11.0%
17 | 01/20/26 | 31040 | 1552 | 31040 | 518672 | 11.7%
18 | 01/20/26 | 142000 | 7100 | 142000 | 660672 | 14.9%
19 | 01/20/26 | 6120 | 306 | 6120 | 666792 | 15.1%
20 | 01/20/26 | 35470 | 1774 | 35470 | 702262 | 15.9%
21 | 01/20/26 | 106410 | 5320 | 106410 | 808672 | 18.3%
22 | 01/20/26 | 70940 | 3547 | 70940 | 879612 | 19.9%
23 | 01/20/26 | 27300 | 1365 | 27300 | 906912 | 20.5%
24 | 01/20/26 | 3213 | -161 | 3213 | 910125 | 20.6%
25 | 01/20/26 | 7760 | -388 | 7760 | 917885 | 20.8%
26 | 01/20/26 | 6467 | 323 | 6467 | 924352 | 20.9%
27 | 01/20/26 | 5400 | 270 | 5400 | 929752 | 21.0%
28 | 01/20/26 | 6351 | -318 | 6351 | 936103 | 21.2%
29 | 01/20/26 | 6035 | 302 | 6035 | 942138 | 21.3%
30 | 01/20/26 | 608 | 30 | 608 | 942746 | 21.3%
31 | 01/20/26 | 28464 | 1423 | 28464 | 971210 | 22.0%
32 | 01/20/26 | 4054 | 203 | 4054 | 975264 | 22.1%
33 | 03/19/25 | 176550 | -8828 | 176550 | 1151814 | 26.1%
34 | 03/19/25 | 49250 | -2462 | 49250 | 1201064 | 27.2%
35 | 03/19/25 | 1849 | -92 | 1849 | 1202913 | 27.2%
36 | 03/19/25 | 176550 | 8828 | 176550 | 1379463 | 31.2%
37 | 03/19/25 | 49250 | 2462 | 49250 | 1428713 | 32.3%
38 | 03/19/25 | 1849 | 92 | 1849 | 1430562 | 32.4%
39 | 11/20/25 | 7000 | -350 | 7000 | 1437562 | 32.5%
40 | 11/20/25 | 230555 | -11528 | 230555 | 1668117 | 37.7%
41 | 11/20/25 | 248290 | -12414 | 248290 | 1916407 | 43.3%
42 | 11/20/25 | 109200 | -5460 | 109200 | 2025607 | 45.8%
43 | 11/20/25 | 21600 | -1080 | 21600 | 2047207 | 46.3%
44 | 11/20/25 | 1014 | -51 | 1014 | 2048221 | 46.3%
45 | 11/20/25 | 1651 | -83 | 1651 | 2049872 | 46.4%
46 | 11/20/25 | 7000 | 350 | 7000 | 2056872 | 46.5%
47 | 11/20/25 | 230555 | 11528 | 230555 | 2287427 | 51.7%
48 | 11/20/25 | 248290 | 12414 | 248290 | 2535717 | 57.3%
49 | 11/20/25 | 109200 | 5460 | 109200 | 2644917 | 59.8%
50 | 11/20/25 | 21600 | 1080 | 21600 | 2666517 | 60.3%
51 | 11/20/25 | 1014 | 51 | 1014 | 2667531 | 60.3%
52 | 11/20/25 | 1651 | 83 | 1651 | 2669182 | 60.4%
53 | 12/17/25 | 16810 | -840 | 16810 | 2685992 | 60.7%
54 | 12/17/25 | 3930 | -196 | 3930 | 2689922 | 60.8%
55 | 12/17/25 | 70000 | -3500 | 70000 | 2759922 | 62.4%
56 | 12/17/25 | 1000 | -50 | 1000 | 2760922 | 62.4%
57 | 12/17/25 | 13830 | -692 | 13830 | 2774752 | 62.7%
58 | 12/17/25 | 14980 | -749 | 14980 | 2789732 | 63.1%
59 | 12/17/25 | 12360 | -618 | 12360 | 2802092 | 63.4%
60 | 12/17/25 | 11890 | -594 | 11890 | 2813982 | 63.6%
61 | 12/17/25 | 11890 | -594 | 11890 | 2825872 | 63.9%
62 | 12/17/25 | 35470 | -1774 | 35470 | 2861342 | 64.7%
63 | 12/17/25 | 12830 | -642 | 12830 | 2874172 | 65.0%
64 | 12/17/25 | 163800 | -8190 | 163800 | 3037972 | 68.7%
65 | 12/17/25 | 10470 | -524 | 10470 | 3048442 | 68.9%
66 | 12/17/25 | 13854 | -693 | 13854 | 3062296 | 69.2%
67 | 12/17/25 | 21865 | 1093 | 21865 | 3084161 | 69.7%
68 | 12/17/25 | 15514 | -776 | 15514 | 3099675 | 70.1%
69 | 12/17/25 | 16683 | -834 | 16683 | 3116358 | 70.5%
70 | 12/17/25 | 420 | 21 | 420 | 3116778 | 70.5%
71 | 12/17/25 | 7116 | -356 | 7116 | 3123894 | 70.6%
72 | 12/17/25 | 4086 | -204 | 4086 | 3127980 | 70.7%
73 | 12/17/25 | 5370 | -268 | 5370 | 3133350 | 70.9%
74 | 12/17/25 | 16810 | 840 | 16810 | 3150160 | 71.2%
75 | 12/17/25 | 3930 | 196 | 3930 | 3154090 | 71.3%
76 | 12/17/25 | 70000 | 3500 | 70000 | 3224090 | 72.9%
77 | 12/17/25 | 1000 | 50 | 1000 | 3225090 | 72.9%
78 | 12/17/25 | 13830 | 692 | 13830 | 3238920 | 73.2%
79 | 12/17/25 | 14980 | 749 | 14980 | 3253900 | 73.6%
80 | 12/17/25 | 12360 | 618 | 12360 | 3266260 | 73.9%
81 | 12/17/25 | 11890 | 594 | 11890 | 3278150 | 74.1%
82 | 12/17/25 | 11890 | 594 | 11890 | 3290040 | 74.4%
83 | 12/17/25 | 35470 | 1774 | 35470 | 3325510 | 75.2%
84 | 12/17/25 | 12830 | 642 | 12830 | 3338340 | 75.5%
85 | 12/17/25 | 163800 | 8190 | 163800 | 3502140 | 79.2%
86 | 12/17/25 | 10470 | 524 | 10470 | 3512610 | 79.4%
87 | 12/17/25 | 13854 | 693 | 13854 | 3526464 | 79.7%
88 | 12/17/25 | 21865 | -1093 | 21865 | 3548329 | 80.2%
89 | 12/17/25 | 15514 | 776 | 15514 | 3563843 | 80.6%
90 | 12/17/25 | 16683 | 834 | 16683 | 3580526 | 81.0%
91 | 12/17/25 | 420 | -21 | 420 | 3580946 | 81.0%
92 | 12/17/25 | 7116 | 356 | 7116 | 3588062 | 81.1%
93 | 12/17/25 | 4086 | 204 | 4086 | 3592148 | 81.2%
94 | 12/17/25 | 5370 | 268 | 5370 | 3597518 | 81.3%
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Net profit of $1,502,927 on $4,422,211 revenue = 34.0% margin (active RI phase, ~90% billed). Direct cost $2,919,284 absorbs 66.0% of revenue.
2 | VENDOR CONCENTRATION | Consolidated Supply Co. = $420,436 (38.1% of all AP) across 101 invoices. Total 23 AP vendors, $1,103,657 total AP spend (typical Chinn vendor mix).
3 | CREW PROFILE | 33 workers for 25,137 hours = 762 avg hrs/worker. Top 3 workers logged 5,245 hrs combined (21% of all labor). Foreman: Anderson, Richard P (1,885 hrs at $62.70/hr) + Paco Leyva, Orlando (1,309 hrs at $61.70/hr).
4 | ROUGHIN DOMINANCE | Code 120 Roughin Labor = $646,310 actual. Code 230 Finish Material = $546,779. Roughin labor is the largest line item in active production — typical for mid-RI multifamily.
5 | BUDGET DELIVERY | Revised expense budget was $4,012,702; actual direct cost $2,919,284 → $1,093,418 variance (1 CRITICAL, 2 OVER flags).
6 | CONTRACT GROWTH | Contract grew from $4,671,538 to $4,889,866 — net +$218,328 (+4.7%). Modest additive CO posture. Retention $245,731 (5%) held.
7 | BURDEN RATIO | Burden codes 995 + 998 = $617,015 on $1,100,219 labor base = 56.1%. Outside OWP's typical 48-50% labor burden.
8 | PROJECT SCALE | 244 units · 68th & Roosevelt Seattle WA. High Street (Trammell Crow) owner; Weinstein A+U architect; Emerald City MEP. Revenue/unit $18,124, hours/unit 103.0, profit/unit $6,160.
9 | PRODUCTIVITY | Blended labor rate $43.79/hr. Revenue/hour $176. Profit/hour $60.
10 | CO PROFILE | Net +$218,328 (+4.7%) booked. CO detail not yet itemized in dataset — typical Chinn pattern (modest, additive). No GDrive Job Book folder yet for 2107 — will be created at project closeout (~Q4 2026).
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | 40.3% | 32-38% | 30-40% | INFO
Revenue per unit | $20,040 | $10-15k | $8-20k | INFO
Direct cost per unit | $11,964 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 56% | 48-50% | 40-55% | WATCH
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $4,889,866 | $0 | — | DELTA
Billed: hero block vs JDR | $4,422,211 | $4,422,211 | — | INFO
Direct cost: meta vs costCats | $2,919,284 | $2,919,284 | — | OK
Worker count: dashboard vs meta | 33 | 33 | — | OK
AP vendor count vs JDR | Source aggregate | 23 | — | INFO
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Consolidated Supply Co. | 101 | 420436 | 38.1% | Secondary plumbing supply
2 | Pacific Plumbing Supply Co., LLC | 128 | 184896 | 16.8% | Primary plumbing supply
3 | Keller Supply Company | 25 | 130768 | 11.8% | Roughin material
4 | Rosen Supply Kirkland | 132 | 116504 | 10.6% | Trim/finish supplier
5 | California Hydronics Corp | 7 | 69125 | 6.3%
6 | Hub International Northwest | 1 | 44817 | 4.1%
7 | MacArthur Co. NW 6276 | 13 | 40629 | 3.7%
8 | Franklin Engineering | 3 | 20215 | 1.8% | Design/MEP fees
9 | Bank of America CC | 39 | 16104 | 1.5%
10 | Herc Rentals, Inc. | 23 | 15185 | 1.4%
11 | Ferguson Enterprises, Inc. #3007 | 14 | 12346 | 1.1% | Roughin + finish supplier
12 | Pioneer Energy Management | 3 | 11405 | 1.0%
13 | Platt $Rexel USA, Inc. | 5 | 9198 | 0.8%
14 | Old Castle Infrastructure, Inc. | 2 | 2471 | 0.2%
15 | Scan2Core, Inc. | 2 | 2272 | 0.2%
16 | Core & Main LP $HD Supply Waterworks | 1 | 2204 | 0.2%
17 | Capital One Credit Card | 49 | 1892 | 0.2%
18 | VEF Supply Ltd. | 1 | 1107 | 0.1%
19 | Hilti, Inc. | 2 | 683 | 0.1%
20 | Edge Construction Supply, LLC | 1 | 464 | 0.0%
21 | ACME Corp | 2 | 435 | 0.0%
22 | Seton Identification Products | 2 | 323 | 0.0%
23 | Uline | 1 | 178 | 0.0%
SOURCES
Job #2107 — Chinn 68th & Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · RI phase · 90.4% billed · 30.7% margin
Canonical source: 2107_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2107_dashboard_arrays.json (mirrors index.html PROJECTS['2107'])
Project profile: 244 units · 6716 Roosevelt Way NE, Seattle, WA 98115 · ~24 months · active RI phase
Design team: Weinstein A+U (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract executed Jan 2025 · final $4,889,866 (was $4,671,538 base · +$218,328 / +4.7% net COs)
Billing: $4,422,211 billed across 14 pay apps · 94 AR transactions · retention $245,731 (5%)
Permit: City of Seattle Plumbing Permit (7 docs in build META)