## CGC BP
[7 empty] | PROJECT: | 2024 BALLARD MERRILL GARDENS
[7 empty] | DATE: | 2015-12-09
[7 empty] | RFI/ASI: | ASI-039
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
DELETE IMC/Teddy ASFT-2436-SG floor trough drain - OLD ITEM 66
| FLOOR TROUGH SUPPLY |  |  |  |  | -1 | EA | 1326 | -1326
| FLOOR TROUGH INSTALLATION | -2 | HRS | 60.5 | -121
| WASTE PIPING | -1 | HRS | 60.5 | -60.5 | -1 | LOT | 45 | -45
DELETE WATER PIPING FOR TILTING STEAM KETTLE - OLD ITEM 67
| HOT & COLD WATER CONNECTIONS | -1 | HRS | 60.5 | -60.5 | -2 | LOT | 18 | -36
GAS IS A WASH - OLD 67 VERSUS NEW 66
ADD WATER, GAS & INDIRECT DRAIN FOR CONVECTION STEAMER - NEW ITEM 68
| THREE COLD WATER CONNECTIONS (TWO FOR UNIT, ONE FOR TEMPERED DRAIN CONNECTION) | 2 | HRS | 60.5 | 121 | 3 | LOT | 18 | 54
| TEMPERED DRAIN VALVE | 2 | HRS | 60.5 | 121 | 1 | EA | 268 | 268
| WATTS LF007 BACKFLOW | 3 | HRS | 60.5 | 181.5 | 1 | EA | 254 | 254
| BACKFLOW PERMIT | 1 | HRS | 60.5 | 60.5 | 1 | EA | 75 | 75
| BACKFLOW INSPECTION | 1 | HRS | 60.5 | 60.5 | 1 | EA | 48 | 48
| INDIRECT DRAIN CONNECTION FOR STEAMER - COPPER | 2 | HRS | 60.5 | 121 | 1 | LOT | 60 | 60
| INDIRECT DRAIN FOR BACKFLOW - COPPER | 2 | HRS | 60.5 | 121 | 1 | LOT | 60 | 60
| GAS PIPING | 2 | HRS | 60.5 | 121 | 1 | LOT | 34 | 34
| GAS CONNECTOR KIT - ITEM 69 |  |  |  |  | 1 | EA | 264 | 264
| TRIM | 2 | HRS | 60.5 | 121
EXCLUDES FLUE GAS EXHAUST VENT CONNECTION
DELETE WATER FOR COMBINATION OVEN-STEAMER AND CONVECTION OVEN - NEW ITEM 70
| WATER CONNECTION | -1 | HRS | 60.5 | -60.5 | -1 | LOT | 18 | -18
EXCLUDES DRAFT EXHAUST VENT CONNECTION
ITEM 71 IS A WASH
POT FILLER FAUCET - ITEM 72
| HOT & COLD WATER CONNECTIONS | 1 | HRS | 60.5 | 60.5 | 2 | LOT | 18 | 36
| T&S BRASS FAUCET SUPPLY |  |  |  |  | 1 | EA | 349 | 349
| INSTALL BACKING AND SUPPORT FOR FAUCET | 2 | HRS | 60.5 | 121
| T&S BRASS FAUCET INSTALL | 2 | HRS | 60.5 | 121
| CHANGE MANAGEMENT | 3 | HRS | 80 | 240
| Subtotals |  |  |  | 1268.5 |  |  |  | 77 |  | 0
| OH & Profit |  |  | 10% | 126.85 |  |  | 10% | 7.7 | 10% | 0
| Subtotal |  |  |  | 1395.35 |  |  |  | 84.7 |  | 0
TOTAL
1480.05