## CGC BP
[7 empty] | PROJECT: | 2024 BALLARD MERRILL GARDENS
[7 empty] | DATE: | 2016-02-15
[7 empty] | RFI/ASI: | RFI-175
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
| MOEN G221944 SINK |  |  |  |  | 1 | EA | 55 | 55
| DELTA 300-DST FAUCET |  |  |  |  | 1 | EA | 72 | 72
| DEARBORN 14 STRAINER |  |  |  |  | 1 | EA | 5 | 5
| P-TRAP/INSULATION/ANGLE STOPS/ETC |  |  |  |  | 1 | LOT | 36 | 36
| FITTINGS/PIPE/HANGERS/SUPPORTS |  |  |  |  | 1 | LS | 35 | 35
| WASTE & VENT ROUGH-IN LABOR | 3 | HRS | 75 | 225
| WATER ROUGH-IN LABOR | 2 | HRS | 75 | 150
| TRIM LABOR | 2 | HRS | 75 | 150
| SUPERVISION | 1 | HRS | 80 | 80
| AS-BUILTING | 0.5 | HRS | 80 | 40
| Subtotals |  |  |  | 645 |  |  |  | 203 |  | 0
| OH & Profit |  |  | 10% | 64.5 |  |  | 10% | 20.3 | 10% | 0
| Subtotal |  |  |  | 709.5 |  |  |  | 223.3 |  | 0
TOTAL
932.8
ADD SINK PER RFI-175