## CGC BP
[7 empty] | PROJECT: | 2024 BALLARD MERRILL GARDENS
[7 empty] | DATE: | 2016-02-10
RFI/ASI:
DESCRIPTION OF CHANGE/WORK PERFORMED
|  | Labor |  |  |  | Material/Equipment |  |  |  | SUB TIER
Item | Description | Quan | UOM | Unit Cost | Total | Quan | UOM | Unit Cost | Total | UOM | Total
UNIT 713
WASTE DEMO
| DEMO TOILET & RISER | 2 | HRS | 60.5 | 121
| DEMO SHOWER | 8 | HRS | 60.5 | 484
| DEMO LAV SINK | 3 | HRS | 60.5 | 181.5
| DEMO WASHER X 2 | 6 | HRS | 60.5 | 363
| PARTIAL DEMO VENTING IN CEILING | 3 | HRS | 60.5 | 181.5
| DEMO KITCHEN SINK X 2 | 6 | HRS | 60.5 | 363
WATER DEMO
| DEMO TOILET | 1 | HRS | 60.5 | 60.5
| DEMO SHOWER | 1 | HRS | 60.5 | 60.5
| DEMO LAV SINK | 1 | HRS | 60.5 | 60.5
| DEMO WASHER X 2 | 2 | HRS | 60.5 | 121
| DEMO KITCHEN SINK X 2 | 2 | HRS | 60.5 | 121
INSTALL NEW PLUMBING
| LAYOUT | 5 | HRS | 60.5 | 302.5
| DRILL | 8 | HRS | 60.5 | 484
| STOCK UNIT | 2 | HRS | 60.5 | 121
| WASTE/STORM/VENT | 8 | HRS | 60.5 | 484
| WATER | 8 | HRS | 60.5 | 484
| WATER MAIN TO UNIT SHUTOFFS | 7 | HRS | 60.5 | 423.5
| SET VALVES | 6 | HRS | 60.5 | 363
| SET SHOWER | 8 | HRS | 60.5 | 484
| CLEANING | 2 | HRS | 60.5 | 121
| NAIL PLATE, QC | 2 | HRS | 60.5 | 121
| TESTING | 8 | HRS | 60.5 | 484
| INSPECTIONS | 3 | HRS | 60.5 | 181.5
UNIT 715
WASTE DEMO
| DEMO TOILET & RISER | 2 | HRS | 60.5 | 121
| DEMO SHOWER | 8 | HRS | 60.5 | 484
| DEMO LAV SINK | 3 | HRS | 60.5 | 181.5
| DEMO WASHER X 2 | 6 | HRS | 60.5 | 363
| PARTIAL DEMO VENTING IN CEILING | 3 | HRS | 60.5 | 181.5
| DEMO KITCHEN SINK X 2 | 6 | HRS | 60.5 | 363
WATER DEMO
| DEMO TOILET | 1 | HRS | 60.5 | 60.5
| DEMO SHOWER | 1 | HRS | 60.5 | 60.5
| DEMO LAV SINK | 1 | HRS | 60.5 | 60.5
| DEMO WASHER X 2 | 2 | HRS | 60.5 | 121
| DEMO KITCHEN SINK X 2 | 2 | HRS | 60.5 | 121
INSTALL NEW PLUMBING
| LAYOUT | 5 | HRS | 60.5 | 302.5
| DRILL | 8 | HRS | 60.5 | 484
| STOCK UNIT | 2 | HRS | 60.5 | 121
| WASTE/STORM/VENT | 8 | HRS | 60.5 | 484
| WATER | 8 | HRS | 60.5 | 484
| WATER MAIN TO UNIT SHUTOFFS | 7 | HRS | 60.5 | 423.5
| SET VALVES | 6 | HRS | 60.5 | 363
| SET SHOWER | 8 | HRS | 60.5 | 484
| CLEANING | 2 | HRS | 60.5 | 121
| NAIL PLATE, QC | 2 | HRS | 60.5 | 121
| TESTING | 8 | HRS | 60.5 | 484
| INSPECTIONS | 3 | HRS | 60.5 | 181.5
| POTENTIALLY MOVE GAS | 16 | HRS | 60.5 | 968
| WASTE MATERIAL |  |  |  |  | 1 | LS | 500 | 500
| WATER MATERIAL |  |  |  |  | 1 | LS | 500 | 500
| GUSTAVO | 16 | HRS | 80 | 1280
| BOB | 16 | HRS | 80 | 1280
| JEFF | 8 | HRS | 95 | 760
| RICH | 8 | HRS | 95 | 760
| BRETT/MIKE | 4 | HRS | 115 | 460
| Subtotals |  |  |  | 17850 |  |  |  | 1000 |  | 0
| OH & Profit |  |  | 15% | 2677.5 |  |  | 15% | 150 | 10% | 0
| Subtotal |  |  |  | 20527.5 |  |  |  | 1150 |  | 0
TOTAL
21677.5
COMBINE UNITS ON L7 INTO LUXURY UNITS