## Overview - common
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
OVERALL | Window screens / cranks missing
Threshold missing
Bipass stops for closet
Bipass doors
ISTA Meters to be installed
Electrical panel, ISTA panel, VTAC doors to be painted
All Bifold doors will be replaced
All pantry top cabinets missing shelf
All 4,3,and 2 East LUT will be repolished
All stove anti-tip elements not installed correctly
All or Most of butt joints on flooring puckered up
Big Roller bed doors in studio/ 1 bedroom can be heard from below when moved
Pull hinge stops off all future projects
1/4 x 2 1/2" thresholds all new constructions Brush sweep
Check all istametal cabinets for sharp edges where cut back
Bifold doors pull on wrong side - add 2nd handle
All stoves 3/4" high - to counter top

## 2nd floor
2nd Floor
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
203 | Blinds are missing valance | Accountable
204 | Blinds are missing valance | Accountable
205 | Blinds are missing valance | Accountable
206 | Final Clean needed | Accountable
207 | Blinds are missing valance | Accountable
208 | Blinds are missing valance | Accountable
209 | Final Clean needed | Accountable
209 | Blinds are missing valance | Accountable
210 | Final Clean needed | Accountable
210 | Blinds are missing valance | Accountable
211 | Final Clean needed | Accountable
211 | Blinds are missing valance | Accountable
242 | Blinds are missing valance | Accountable
244 | Blinds are missing valance | Accountable
245 | Blinds are missing valance | Accountable
247 | Blinds are missing valance | Accountable
247 | Patio door covered | Accountable
248 | Patio door blinds missing | Accountable
248 | Blinds are missing valance | Accountable
249 | Patio door missing blinds | Accountable
250 | Missing blinds in bedroom | Accountable
252 | Blinds are missing valance | Accountable
205 | Bedroom ceiling repair near light | B230
242 | Wall repair needed at ISTA box | B230
242 | THIS APT WILL NEED RE-PUNCHED | B230
243 | Wall repair needed at ISTA box | B230
244 | Wall repair needed at ISTA box | B230
245 | Wall repair needed at ISTA box | B230
246 | Wall repair needed at ISTA box | B230
247 | Wall repair needed at ISTA box | B230
249 | Wall repair needed at ISTA box | B230
250 | Wall repair needed at ISTA box | B230
252 | Wall repair needed at ISTA box | B230
210 | Bathroom backsplash at countertop has pink discoloration | Color Marble
250 | Bathroom vanity backsplash has a low spot in countertop. Backsplash needs caulked all the way around. | Color Marble
202 | Bathroom floor/tub caulking is poor | commercial Int
205 | Caulk cabinet in kitchen at floor end of unit | commercial int
206 | Kitchen end cabinet to floor needs caulking | commercial int
208 | Caulk vanity and floor in bathroom | commercial int
208 | Caulking at kitchen end cabinet and floor | commercial int
209 | Caulking at kitchen end cabinet and floor | commercial int
210 | Flooring at vanity left side needs caulking | commercial int
245 | Vanity floor needs caulked | commercial int
251 | Kitchen end cabinet to floor needs caulk - overspray at floor | commercial int
201 | Kitchen end cabinet to floor needs caulking/overspray at floor | Commercial Int / Greens
211 | Shower door not sealing to glass wall square | Courtesy Glass
202 | Closet sprinkler head | FPS
249 | Sprinkler head missing in coat closet | FPS
201 | Bathroom door not latching | Frontier
202 | Pocket door rubbing/hard to open | Frontier
203 | Bathroom door not latching | Frontier
203 | Bedroom glass doors are difficult to roll | Frontier
205 | Bedroom glass doors are difficult to roll | Frontier
205 | Bipass closet doors noisy | Frontier
206 | Large sliding glass doors are difficult to roll | Frontier
207 | Bed door drags on floor | Frontier
208 | Both towel hook and vanity loose | Frontier
211 | Transom and trim above master bed door not completed | Frontier
242 | Bathroom door not latching | Frontier
247 | Towel hook at bathroom vanity off | Frontier
249 | Bathroom door hits jamb and won't close | Frontier
250 | Bedroom door missing | Frontier
250 | Master bath door not latching | Frontier
208 | Disposal very noisy | GE
242 | Washer dryer not installed | GE
243 | Washer dryer not installed | ge
243 | Dishwasher missing | ge
244 | Washer dryer not installed | GE
245 | Washer dryer not installed | GE
245 | Dishwasher missing | GE
246 | Washer dryer not installed | GE
247 | Washer dryer not installed | GE
248 | Washer dryer not installed | GE
250 | Stove not installed | GE
250 | Hood vent not installed | GE
252 | Washer dryer not installed | ge
201 | Paint touch up bathroom ceiling at fan | Greens
202 | Paint touch up at door handle inside bathroom | Greens
203 | Paint touch up in living room at ponywall sill | Greens
205 | Paint / texture at bathroom light switch left side | Greens
205 | Paint touch at towel bar and Robe hook | Greens
205 | Paint touch up on top of pony wall sill | Greens
207 | Paint touch at towel bar and Robe hook | Greens
207 | Caulk/overspray at kitchen cabinet end | Greens
207 | Paint at kitchen bar trim needs 2nd coat. | Greens
210 | Kitchen end cabinet at floor has overspray and needs caulk | Greens
211 | Paint above cabinet doors upper left side of sink | Greens
211 | Paint touch up in master closet needed at shelf | Greens
242 | White paint touchup throughout | Greens
242 | Paint above kitchen sink | Greens
243 | Den needs paint touch ups at data jack | Greens
243 | Paint touch at VTAC | Greens
243 | White paint touchup throughout | Greens
246 | Paint touch up needed on top of pantry | Greens
246 | Bedroom paint touchup on walls needed | Greens
247 | Paint touch up needed at kitchen sink wall | Greens
248 | Bathroom backsplash needs caulking | Greens
249 | Paint touch up at top of pantry | Greens
251 | Paint touch up in bathroom ceiling at fan needed | Greens
243 | Patio door not latching, dead bolt not latching | NWI
247 | Patio slider door not locking | NWI
249 | Trickle vent at patio door broken | NWI
204 | No showerhead | OWP
207 | Dishwasher not installed | OWP
207 | Tub in master bathroom has low water pressure | OWP
208 | Sink in kitchen missing plug for drain | OWP
210 | Tub has plunkers putty at drain | OWP
211 | Dishwasher not hooked up | OWP
211 | Shower has black marks at soap dish in master bath | OWP
242 | No hot water at kitchen sink | owp
250 | Master toilet runs | OWP
252 | Tub doesn't drain properly | OWP
201 | Blank plate in bathroom needs white screws | Robs
202 | Blank plate in bathroom needs white screws | Robs
203 | Blank plate in bathroom needs white screws | Robs
204 | Blank plate in bathroom needs white screws | Robs
205 | Blank plate in bathroom needs white screws | Robs
206 | Blank plate in bathroom needs white screws | Robs
207 | Master bath Blank plate in bathroom needs white screws | Robs
209 | Blank plate in bathroom needs white screws | Robs
210 | Blank plate in bathroom needs white screws | Robs
210 | Light out above vanity | Robs
211 | Master bath Blank plate in bathroom needs white screws | Robs
211 | Bathroom blank plate needs white screws | Robs
242 | Bathroom wall plate | Robs
242 | Bathroom outlet pulled from wall | Robs
243 | Bedroom outlet cover at VTAC needed | Robs
243 | Blank plate in bathroom needs white screws | Robs
244 | Blank plate in bathroom needs white screws | Robs
245 | Blank plate in bathroom needs white screws | Robs
246 | Blank plate in bathroom needs white screws | Robs
247 | Blank plate in bathroom needs white screws | Robs
248 | Patio light out | Robs
248 | Blank plate in bathroom needs white screws | Robs
249 | Blank plate in bathroom needs white screws | Robs
249 | Kitchen cabinet doors hit light fixture | Robs
250 | Blank plate in bathroom needs white screws and in master bath | Robs
251 | Blank plate in bathroom needs white screws | Robs
252 | Blank plate in bathroom needs white screws | Robs
206 | HVAC non operable | US MECH
208 | VTAC cover missing screw | US MECH
211 | AC not working | US MECH
246 | Vent cover missing in living room ceiling | US MECH
247 | HVAC non operable | US MECH
250 | HVAC non operable | US MECH
243 | Vanity above toilet loose on wall | vbw
248 | Kitchen bar is missing | vbw
250 | Hardware missing at bathroom vanity | vbw
250 | Master bath vanity hardware missing | vbw

## 3rd floor
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
301 | Blinds missing | Accountable
302 | Blinds missing | Accountable
303 | Blinds missing from patio | Accountable
304 | Valence missing on blinds | Accountable
305 | Left window blinds are missing | Accountable
306 | Blinds missing for patio door and windows | Accountable
307 | Blinds missing valances | Accountable
308 | Valence missing on blinds | Accountable
310 | Valence missing on living room blinds | Accountable
342 | Blinds are missing valance | Accountable
343 | Blinds not installed | Accountable
344 | Blinds valance are missing | Accountable
345 | Blind valance are missing | Accountable
347 | Blind valance are missing | Accountable
348 | Patio door blinds missing | Accountable
349 | Door to patio missing blinds | Accountable
350 | Blind valance are missing | Accountable
351 | Blind valance are missing | Accountable
352 | Blind valance are missing | Accountable
353 | Blind valance are missing | accountable
301 | Water value access door wall needs repair | B230
307 | Hole in wall at towel hanger -master bathroom vanity | B230
308 | Wall repair/paint at TV/data jack near VTAC | B230
349 | Wall repair at water meter access | B230
343 | 6th plank row from front door (floor) is defective | commercial int
350 | Evoke floor at kitchen lower cabinet near dishwasher not cut straight | commercial int
311 | Sprinkler escutcheon missing in master bedroom | FPS
343 | Patio missing sprinkler head | FPS
345 | Patio sprinkler heads are missing | FPS
347 | Patio missing sprinkler head | FPS
348 | Patio missing sprinkler head | FPS
349 | Exterior patio sprinkler heads missing - both sides | FPS
301 | Large rolling doors to bed rolling hard and heavy | Frontier
303 | Bathroom door not latching | Frontier
304 | Base missing at VTAC | Frontier
304 | Closet bipass in bedroom bottom glide too low | Frontier
305 | Bed bipass doors dragging on carpet, missing floor glide | Frontier
307 | Master closet rod on back wall bracket bent/loose. Needs bracket in middle. | Frontier
307 | Master bedroom door dragging on carpet | Frontier
307 | Master bedroom door not latching | Frontier
307 | Bathroom door not latching | Frontier
307 | Coat closet at laundry missing end bracket right side | Frontier
310 | Bathroom door not latching | Frontier
311 | Bathroom door not latching | Frontier
342 | Shower curtain rod not installed | Frontier
346 | Base behind toilet incomplete | Frontier
350 | Robe hook missing | Frontier
350 | Coat closet door not latching | Frontier
350 | Master bed door dragging on carpet | Frontier
351 | Door stop missing to bedroom door | Frontier
352 | Pocket door dragging at closing | Frontier
306 | Washer not plugged in | GE
307 | Disposal inoperable | GE
310 | Dent in side of fridge at sink/upper cabinet | GE
343 | Anti-tip for stove not set correctly | GE
343 | Dishwasher is missing | GE
345 | Disposal inoperable | GE
345 | Dishwasher is missing | GE
346 | Washer not plugged in | GE
350 | Stove not installed | GE
350 | Range hood/vent not operable. | GE
352 | Range missing | GE
353 | Disposal inoperable | GE
353 | Anti-tip for stove not set correctly | GE
301 | Wall texture paint touch up left side of fridge | Greens
301 | Paint on cabinet upper kitchen | Greens
301 | Paint touch up on wall in living room Base cabinet side in living room (lots of overspray) | Greens
302 | Paint touch at heat timer in bathroom | Greens
304 | Paint touch up needed at TV/Data jack near VTAC | Greens
305 | Paint touch up left side wall at large sliding doors | Greens
306 | Paint touch up at disposal switch | Greens
307 | Paint touch at blank plate in bathroom above toilet | Greens
312 | Paint touch up at shower curtain rod on right side needed | Greens
312 | Paint touch up ceiling living area at corner opposite VTAC | Greens
312 | Paint touch up in corner opposite VTAC between window and kitchen | Greens
343 | Living room wall opposite kitchen needs painted | Greens
345 | Paint touch up wall left side of fridge | Greens
348 | Paint touch up in bathroom at GFI | Greens
349 | Paint on back edge of pantry at living room wall | Greens
350 | Bathroom paint touch up at fiberglass shower tub insert | Greens
352 | Overspray on both door hinges | Greens
353 | Paint touch up right corner of fridge at wall | Greens
353 | Paint touch up on wall opposite of fridge | Greens
305 | Left window lock hard to lock | NWI
345 | Patio door sticking/not latching | NWI
345 | Patio door dead bolt not engaging | NWI
303 | Tub hot/cold knobs are backwards | OWP
304 | Tub hot/cold knobs are backwards | OWP
305 | Tub hot/cold knobs are backwards | OWP
307 | Master bath - Tub hot/cold knobs are backwards | OWP
308 | No water in tub/shower | OWP
308 | Tub hot/cold knobs are backwards | OWP
311 | Tub hot/cold knobs are backwards in master bedroom | OWP
312 | No water pressure in tub/shower | OWP
343 | Tub hot/cold knobs are backwards | OWP
343 | Toilet constantly runs | OWP
344 | Tub hot/cold knobs are backwards | OWP
345 | Tub hot/cold knobs are backwards | OWP
346 | Shower not complete - needs trim installed | OWP
346 | Tub hot/cold knobs are backwards | OWP
347 | Tub hot/cold knobs are backwards | OWP
348 | Tub slow to drain | OWP
348 | Toilet constantly runs | OWP
349 | Tub hot/cold knobs are backwards | OWP
349 | Toilet constantly runs | OWP
350 | Tub hot/cold knobs are backwards in master bedroom | OWP
351 | Tub hot/cold knobs are backwards | OWP
352 | Tub hot/cold knobs are backwards | OWP
353 | Tub hot/cold knobs are backwards | OWP
301 | Blank plate in bathroom needs white screws | Robs
302 | Blank plate in bathroom needs white screws | Robs
302 | Under cabinet light at sink not working | Robs
303 | Screw missing from smartbox | Robs
304 | Blank plate in bathroom needs white screws | Robs
305 | Blank plate in bathroom needs white screws | Robs
307 | Blank plate in bathroom needs white screws, master bath | Robs
307 | Outlet plate cover below VTAC not set correctly | Robs
307 | Breaker panel not latching | Robs
307 | Bathroom missing switch plate cover | Robs
308 | Light out above kitchen | Robs
310 | Blank plate in bathroom needs white screws | Robs
310 | Short in microwave circuit | Robs
342 | Blank plate in bathroom needs white screws | Robs
343 | Breaker panel not latching | Robs
343 | Blank plate in bathroom needs white screws | Robs
345 | Blank plate in bathroom needs white screws | Robs
346 | Blank plate in bathroom needs white screws | Robs
347 | Blank plate in bathroom needs white screws | Robs
348 | GFI in bathroom is bad | Robs
348 | Blank plate in bathroom needs white screws | Robs
349 | Blank plate in bathroom needs white screws | Robs
350 | Blank plate in bathroom needs white screws | Robs
350 | Plate cover missing in kitchen | Robs
350 | master bath blank plate needs white screws | Robs
351 | Blank plate in bathroom needs white screws | Robs
352 | Outlet in living room at windows missing | Robs
352 | Data/TU jack pulled from wall in living room | Robs
352 | Blank plate in bathroom needs white screws | Robs
307 | Screw stripped at VTAC lower left screw | US MECH
311 | No HVAC | US MECH
346 | VTAC / bed vent missing in living room ceiling | US MECH
301 | Cabinet door above microwave rubbing microwave | VBW
304 | Kitchen cabinet corner door hitting sink base | VBW
304 | Top Drawer left of dishwasher edge bond peeling | VBW
343 | Lower cabinet kitchen corner door hitting sink base | VBW
346 | Corner cabinet lower kitchen door hitting sink base | VBW
347 | Kitchen corner cabinet lower door hits sink base | VBW
349 | Upper cabinet in kitchen right of sink door rubbing pantry | VBW
350 | Both drawer pulls not installed | VBW
350 | Vanity cabinet above toilet chips in laminate left of door. | VBW
350 | Toe kick missing in kitchen | VBW
351 | Corner cabinet lower kitchen door hitting sink base | VBW
352 | Bottom kitchen drawer by fridge not gliding correctly | VBW
352 | Kitchen lower cabinet missing laminate end | VBW
352 | Bathroom vanity end by toilet missing laminate | VBW

## 4th floor
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
403 | Patio Blinds incorrect | Accountable
404 | Final clean needed | Accountable
405 | Final clean needed | Accountable
407 | Final clean needed | Accountable
407 | Patio blinds to be replaced with correct ones | Accountable
407 | Master bed missing blind in top window | Accountable
445 | Final clean needed | Accountable
446 | Final clean needed | Accountable
447 | Final clean needed | Accountable
448 | Bedroom blinds midway on the right side are too wide | Accountable
448 | Final clean needed | Accountable
449 | Blinds at living room | Accountable
449 | Final clean needed | Accountable
450 | Master bedroom blinds missing | Accountable
450 | Blinds missing in living room | Accountable
451 | Final clean needed | Accountable
452 | Final clean needed | Accountable
453 | Final clean needed | Accountable
401 | Hole at ISTA meter in wall | B230
404 | Holes in wall at ISTA meter | B230
405 | Holes in wall at ISTA meter | B230
407 | Holes in wall at ISTA meter | B230
412 | Living room missing window cranks | B230
442 | Holes in wall at ISTA meter | B230
446 | Holes in wall at ISTA meter | B230
448 | Washer and dryer too close to sprinkler head -18" needed (?) Currently 4" | B230
448 | Wall repair at ISTA meter | B230
449 | Holes in wall at ISTA meter | B230
401 | Caulking at floor/cabinet side needed | Commercial Int
402 | Tub/Floor needs caulked | Commercial Int
403 | Tub/Floor needs caulked | Commercial Int
403 | Caulking at kitchen cabinet side/floor | Commercial Int
404 | Caulk needed at tub floor | Commercial Int
405 | Tub/Floor needs caulked | Commercial Int
406 | Tub/Floor needs caulked, especially at transition | Commercial Int
407 | Floor refinished | Commercial Int
407 | Tub/Floor needs caulked, especially at transition | Commercial Int
409 | Tub/Floor needs caulked, especially at transition | Commercial Int
409 | Caulking at kitchen cabinet next to stove at floor needs finished | Commercial Int
411 | Tub/Floor needs caulked, especially at transition | Commercial Int
412 | Caulking at tub | Commercial Int
442 | Poor caulking at cabinet end cap/floor | Commercial Int
443 | Transition at patio door in living room too high off of floor | Commercial Int
446 | Tub/Floor needs caulked, especially at transition and at vanity | Commercial Int
452 | Tub/Floor needs caulked, especially at transition | Commercial Int
453 | Floor too glossy | Commercial Int
450 | Master bath vanity mirror missing | courtesy glass
408 | Bathroom fire sprinkler escutcheon missing | FPS
408 | Living room fire sprinkler escutcheon missing | FPS
408 | Closet sprinkler escutcheon missing | FPS
409 | Closet sprinkler escutcheon missing | FPS
401 | Large sliding doors don't roll well, they're heavy | Frontier
405 | Left bipass door wheel noisy | Frontier
405 | Middle bed roller door rolls rough, can be heard downstairs | Frontier
407 | Master closet door handle installed backwards | Frontier
411 | Closet rod in bedroom closet at ISTA meters cut short left side | Frontier
412 | Closet pocket door dragging on nails in trim | Frontier
443 | Closet pocket door dragging | Frontier
446 | Bathroom door not latching | Frontier
447 | Living room patio door won't latch / deadbolt won't close | Frontier
447 | Bedroom pocket door dragging on nail. | Frontier
448 | Closet rod bedroom not fastened | Frontier
448 | Closet rod in bedroom not fastened | Frontier
448 | Bathroom door not latching | Frontier
450 | Robe holder missing | Frontier
450 | Bifold doors at laundry difficult to open | Frontier
451 | Bathroom mirror top -hardware not level. Not attached to wall (?) | Frontier
450 | Paint patch at living room upper window | g
450 | Paint touch up needed in master bath at showers edge | g
404 | Dryer is very loud | GE
404 | Anti-tip for stove not set correctly | GE
411 | Appliances missing | GE
442 | Washer/Dryer missing | GE
442 | Fridge not plugged in | GE
442 | Microwave above stove missing | GE
443 | Microwave missing | GE
443 | Washer and dryer not connected | GE
444 | Microwave above stove missing | GE
445 | Microwave above stove missing | GE
445 | Anti-tip for stove not set correctly | GE
446 | Anti-tip for stove not set correctly | GE
446 | Microwave above stove missing | GE
447 | Anti-tip for stove not set correctly | GE
447 | Oven vent missing ducting / cover | GE
450 | Oven/stove not installed | GE
451 | Anti-tip for stove not set correctly | GE
453 | Fridge not plugged in | GE
453 | Anti-tip for stove not set correctly | GE
401 | Vanity backsplash needs caulked at light switch | Greens
404 | Paint touch up at pantry in ceiling | Greens
407 | Master bedroom ceiling needs cut in paint | Greens
407 | Bathroom paint needs touched up at shower curtain rod | Greens
407 | Paint touched up at bedroom door | Greens
407 | Paint touched up at VTAC in bedroom | Greens
411 | Paint touch up needed in laundry closet at closet shelf | Greens
442 | Paint touch up needed at towel bar at vanity | Greens
444 | Paint repair at backsplash in bathroom vanity | Greens
445 | Overspray on ceiling | Greens
447 | Overspray on ceiling | Greens
448 | White overspray on bedroom patio wall | Greens
448 | paint touch at window sill near VTAC | Greens
448 | Overspray on ceiling | Greens
451 | Kitchen backsplash caulking needed | Greens
452 | Ceiling has multiple touch up marks "shinners" throughout | Greens
453 | Caulking needed in bathroom backsplash | Greens
405 | Living room window right side broken hardware | NWI
443 | Trickle vent left living room window broken/off | NWI
449 | Bedroom slider patio door difficult to open | NWI
404 | Tub drain not staying open | OWP
404 | No tub water pressure | OWP
407 | Bathroom has no water | OWP
407 | Common bath has no water to tub/shower | OWP
444 | Toilet runs constantly | OWP
447 | No tub water pressure | OWP
450 | Showerhead missing | OWP
453 | No water pressure at shower | OWP
453 | Dishwasher not hooked up | OWP
446 | Bed eFan cover falling/loose | Pac 1
404 | Outlet cover plate missing in bedroom | Robs
406 | Bathroom vanity light out | Robs
407 | Kitchen light fixture ceiling light to be adjusted | Robs
408 | Bath fan disassembled inoperable | Robs
411 | Blank plate needs white screws at bathroom | Robs
442 | Blank plate needs white screws at bathroom | Robs
442 | Bathroom vanity light out | Robs
445 | Light fixture in entry has a broken globe | Robs
445 | Lights are out above kitchen | Robs
446 | Blank plate needs white screws at bathroom | Robs
448 | Bathroom blank covers need white screws | Robs
406 | TSTAT batteries low, no HVAC | US MECH
410 | HVAC not working | US MECH
412 | VTAC cover missing clip for screen - left lower screw | US MECH
446 | VTAC screws stripped out | US MECH
446 | Vent in living room ceiling missing cover | US MECH
451 | TSTAT location - is this correct? | US MECH
453 | VTAC screws on cover / door stripped out - 2 total | US MECH
401 | Vanity above toilet bottom shelf damaged. Back top right damaged/paper | VBW
403 | Upper cabinets at kitchen sink open shelves and bottom sides are scratched and nicked | VBW
404 | Missing pantry shelf on top | VBW
405 | Kitchen drawer hardware / pull at fridge screws incorrectly set - 2nd drawer | VBW
409 | Kitchen drawer pull at or near fridge needs tightened | VBW
410 | Vanity above toilet missing screw left door pull | VBW
410 | Upper cabinets left of kitchen sink whit laminate peeling bottom right | VBW
411 | Micro vent missing cover 3/4" plywood at vent above in cabinet | VBW
442 | 2nd drawer at fridge has incorrect screws | VBW
444 | Dishwasher - cabinet toe kick missing | VBW
444 | Kitchen cabinet at fridge 2nd drawer screws for hardware off | VBW
446 | Kitchen drawer hardware / pull at fridge screws incorrectly set - 2nd drawer | VBW
446 | Near the Sink the lower cabinet has damage to bottom of cabinet | VBW
447 | Vanity above toilet bottom shelf damaged. | VBW
448 | Kitchen cabinet doors missing | VBW
450 | Bathroom vanity missing hardware | VBW
450 | Vanity over toilet back broken | VBW
450 | Master bath cabinet above toilet has damage to the lower shelf | VBW
450 | master bath vanity hardware missing. | VBW
451 | Kitchen drawer back by pantry middle drawer hardware screws incorrect at pull | VBW

## 6th Floor
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
615 | Blinds missing | accountable
616 | Final Clean needed | accountable
616 | Dirty cabinets | accountable
616 | Dirty mirror | accountable
616 | Bathtub dirty in master bath | accountable
617 | Final Clean needed | accountable
617 | Door casing dirty | accountable
618 | Final Clean needed | accountable
619 | Blinds missing | accountable
620 | Blinds missing | accountable
621 | Final Clean needed | accountable
621 | Blinds missing | accountable
621 | Blinds missing | accountable
622 | Blinds missing | accountable
622 | Final Clean needed | accountable
623 | Final Clean needed | accountable
623 | Blinds missing | accountable
624 | Final Clean needed | accountable
625 | Final Clean needed | accountable
625 | Blinds missing | accountable
626 | blinds missing | accountable
626 | Final Clean needed | accountable
627 | Blinds missing | accountable
628 | Blinds missing | accountable
629 | Blinds missing | accountable
629 | Final Clean needed | accountable
629 | Final Clean needed | accountable
630 | Blinds missing | accountable
630 | Final Clean needed | accountable
631 | Final Clean needed | accountable
632 | Blinds missing | accountable
632 | Final Clean needed | accountable
633 | Blinds missing | accountable
633 | Final Clean needed | accountable
634 | Blinds missing | accountable
634 | Final Clean needed | accountable
635 | Final Clean needed | accountable
635 | Blinds missing | accountable
637 | Blinds missing | accountable
638 | Final Clean needed | accountable
638 | Blinds missing | accountable
638 | Mirror needs cleaned | accountable
639 | Blinds missing | accountable
639 | dirty inside cabinets | accountable
621 | Exterior siding balcony | AVA
624 | Siding above patio door pulling | AVA
634 | Plastic on flashing outside master bed window | AXIOM
639 | Metal flashing living room masonry cap flashing bent up | AXIOM
622 | Wall repairs at large sliding glass doors | B230
630 | Holes in wall | B230
638 | Ceiling repair master bed | B230
617 | Island missing top | Color Marble
617 | Backsplash | Color Marble
617 | Countertop caulking | Color Marble
618 | Countertop backsplash caulking | Color Marble
618 | Master bath - countertop and backlash | Color Marble
618 | Master bath - countertop backsplash caulking needed | Color Marble
619 | Caulking needed | Color Marble
621 | Counter top right of stove not set correctly, all kitchen tops not set square | Color Marble
621 | Master bath - countertop caulking | Color Marble
622 | Caulk at kitchen backsplash | Color Marble
623 | Counter top caulking | Color Marble
627 | Countertop caulking | Color Marble
628 | Countertop caulking | Color Marble
630 | Countertop caulking | Color Marble
635 | Counter top crooked above dishwasher | Color Marble
636 | Counter top crooked at lazy Susan | Color Marble
636 | Countertop caulking | Color Marble
637 | Countertop caulking | Color Marble
638 | Backsplash | Color Marble
639 | countertop caulking | Color Marble
615 | Bath floor at vanity missing | commercial int
616 | Gap in floor living side hinge side of laundry door | commercial int
616 | Bathroom floor/tub caulking main bathroom | commercial int
617 | Flooring caulking | commercial int
618 | Master bath - floor and tub caulking | commercial int
618 | Master bath - floor caulking | commercial int
619 | Floor linear seams "Popped Up" | commercial int
619 | Caulking needed at kitchen base / floor | commercial int
621 | Floor / sliding door transition poor | commercial int
621 | Floor caulking (also in master bath) | commercial int
621 | Master bath - floor caulking | commercial int
622 | Caulk at kitchen base / floor | commercial int
622 | Floor caulking | commercial int
623 | Kitchen cabinet/floor caulk | commercial int
624 | Kitchen cabinet/floor caulk | commercial int
624 | LVT linear seams | commercial int
625 | Flooring | commercial int
625 | Floor caulking | commercial int
626 | Floor caulking | commercial int
627 | Floor caulking | commercial int
628 | Floor caulking | commercial int
629 | Floor caulking | commercial int
630 | Floor caulking | commercial int
631 | Floor caulking | commercial int
632 | Floor caulking | commercial int
633 | Floor caulking | commercial int
634 | Seam in bedroom master carpet floor | commercial int
634 | Floor caulking | commercial int
634 | Master bath - floor caulking | commercial int
635 | Floor caulking | commercial int
636 | Floor caulking | commercial int
636 | Floor caulking | commercial int
638 | Transition missing bath/master bedroom | commercial int
638 | Floor caulking | commercial int
638 | Transition strip missing | commercial int
638 | Floor caulking | commercial int
639 | floor caulking | commercial int
615 | Bathroom mirror missing | countesy glass
625 | Mirror | countesy glass
631 | Mirror | countesy glass
615 | Base at Bath door | Frontier
616 | Master closet door not catching | Frontier
616 | Bathroom door not hitting door square | Frontier
618 | Bedroom door not latching | Frontier
621 | Laundry door missing | Frontier
622 | Center glass rolling door/ rolling heavy | Frontier
625 | Molding | Frontier
626 | Bedroom door missing center hinge pin | Frontier
630 | Sliding glass door to patio hard to roll | Frontier
630 | Front bed glass door hitting screw top rail | Frontier
631 | Bed bipass rubbing carpet | Frontier
632 | Hinge pins | Frontier
633 | Bed pocket door dragging - hard to open and close | Frontier
634 | Laundry door cracked/not painted | Frontier
634 | Master bath - door strike box | Frontier
637 | Floor molding | Frontier
637 | Washer bifold has no handle | Frontier
638 | Laundry door not latching | Frontier
638 | Bedroom door not latching | Frontier
615 | Dishwasher / disposal non operable | GE
618 | Washer and dryer not set | GE
620 | Disposal inoperable | GE
620 | Dryer button | GE
622 | Dryer duct not installed | GE
624 | Dent in fridge door | GE
625 | GE button missing from fridge | GE
625 | Wrong size washer/dryer (This is a 2 bedroom apartment) | GE
627 | Dryer vent missing | GE
627 | Fridge off, no power | GE
627 | Anti-tip feature not installed correctly on stove | GE
627 | Appliance light on exhaust fan not working | GE
628 | Power button on dryer broken | GE
630 | Disposal inoperable | GE
630 | Washer water off | GE
631 | Washer/dryer door handle | GE
636 | Washer/dryer are the wrong size | GE
637 | Fridge handle | GE
637 | Wrong washer and dryer | GE
638 | Dryer not working | GE
615 | Paint touch up needed at tub corner | greens
616 | Paint touch at laundry light switch needed | greens
616 | Paint on all door hinges | greens
616 | Bathtub caulking master bath | greens
617 | Paint touch at coat closet ceiling | greens
617 | kitchen backsplash not caulked, pulling up. | greens
617 | Bed base chipped at window | greens
617 | Hallway to bedroom ceiling needs cut in and paint | greens
617 | Bathtub caulking | greens
617 | Paint on casing | greens
618 | Paint on all door hinges | greens
618 | Paint on hinges | greens
618 | Tub caulking | greens
618 | Master bath - paint on cabinet | greens
618 | Master bath- paint on exhaust timer | greens
619 | Overspray on cabinet | greens
619 | Exhaust and fan timer - overspray | greens
621 | Paint touch corner coat closet | greens
621 | Paint run on coat closet jamb next to washer | greens
621 | Casing paint | greens
621 | Tub caulking | greens
621 | Master bath - paint on hinges | greens
622 | Outlet at front door painted | greens
622 | Paint on hinges | greens
623 | Tape on cabinet above dishwasher | greens
623 | Tub caulking | greens
624 | Paint peeling (white) exterior patio | greens
624 | Paint on hinges | greens
624 | Tub caulking | greens
625 | tub caulking | greens
625 | Casework touch up | greens
626 | Paint on light switch at den | greens
626 | Door paint touch up | greens
628 | Paint on light switch | greens
628 | Paint on hinges | greens
629 | Door touch up | greens
629 | Marked up floor molding | greens
630 | Paint peeling white - exterior | greens
631 | Lots paint touch on walls | greens
631 | Paint on hinges | greens
632 | Paint on light switch by fridge | greens
632 | Overspray on cabinet shelving | greens
633 | Paint on hinges | greens
634 | Paint touch hall at front door | greens
635 | Window will touchup needed | greens
635 | Paint touch wall lover at sliding glass doors | greens
635 | Paint drip on door | greens
635 | Paint on hinges | greens
636 | Paint on tub | greens
637 | Paint on door hinge | greens
637 | Paint in tub | greens
638 | Paint on hinges | greens
638 | Cabinet inside has paint on it | greens
638 | Tub caulking | greens
616 | Water meter valves | ISTA
618 | Water meter valves | ISTA
632 | Cracked capstone outside bed window | J&S
635 | Masonry cap cracked outside window in living room | J&S
621 | Masonry outside South Facing living room window mortar missing & several cracked. | J&S / Peter Ross
621 | Window seals on master bedroom | NWI
628 | Bedroom window bottom hinge broken | NWI
616 | Dishwasher not installed | OWP
617 | Tub Diverter | OWP
618 | Tub Diverter | owp
618 | Master bath - tub diverter | OWP
619 | Water meter valves | owp
619 | Tub diverter | OWP
619 | Washer water off | OWP
620 | Water meter valves | OWP
620 | Tub Diverter | OWP
620 | Washer water off | OWP
621 | Water meter valves | owp
621 | Master bath -Tub Diverter | owp
622 | Water meter valves | owp
622 | Washer water off | owp
623 | Water meter valves | OWP
623 | Tub diverter | OWP
623 | Washer water off | OWP
624 | Tub diverter | owp
625 | Water meter valves | owp
625 | Washer water off | owp
626 | Tub diverter | owp
627 | Kitchen faucet loose on top | owp
627 | Water meter valves | OWP
627 | Tub diverter | OWP
628 | Water meter valves | owp
628 | Tub Diverter | owp
629 | Water valves at meters | owp
629 | Tub Diverter | owp
630 | Water valves at meters | owp
630 | Tub Diverter | owp
631 | Water valves at meters | owp
631 | Sink drain plug | owp
631 | Tub diverter | OWP
632 | Tub diverter | owp
633 | Water valves at meters | owp
633 | Tub diverter | owp
634 | Water valves at meters | owp
634 | Drain plug | owp
634 | Master bath - tub diverter | owp
635 | Water valves at meters | owp
635 | Washer water off | OWP
636 | Water valves at meters | owp
636 | Drain plug | owp
636 | Tub Diverter | owp
636 | Tub Diverter | owp
637 | Washer water off | owp
638 | Water valves at meters | owp
638 | Tub diverter | owp
638 | Tub diverter | owp
639 | Tub diverter | owp
639 | flapper valve leaking | owp
616 | Light out master bath | Robs
617 | Both 6F1 dead short | Robs
617 | GFCI replacer | Robs
618 | Kitchen lights are out | Robs
618 | Cabinet uppers hit light fixtures | Robs
618 | GFCI replace | Robs
618 | Master bath - GFCI replace | Robs
620 | Outlet below Electrical panel painted | Robs
621 | Hallway light globe missing | Robs
621 | No power to washer | Robs
628 | Kitchen lights are out | Robs
631 | Upper cabinet above dishwasher hitting light fixture | Robs
632 | Marked round light diffusers | Robs
633 | Upper cabinet door hits light fixture | Robs
634 | Kitchen light out | Robs
634 | Master bath - vent cover | Robs
635 | Light switch | Robs
636 | Kitchen light out | Robs
637 | Kitchen light out | Robs
637 | Vanity lighting | Robs
618 | Vent missing register in living room ceiling | US MECH
621 | Vent register above bedroom door incomplete | US MECH
625 | Vent register missing above bedroom door. | US MECH
634 | Vent above bed door incomplete | US MECH
617 | Shelving | VBW
619 | Chip in cabinet above dishwasher | VBW
619 | Lower cabinet left of stove shelf stained | VBW
625 | Lazy Susan at kitchen wrong door | VBW
625 | Stains backside of pantry door | VBW
626 | Upper cabinet doors hitting above dishwasher | VBW
626 | Edge bending at pantry | VBW
627 | All kitchen edge band incorrect - black | VBW
627 | Left upper cabinet above dishwasher back broken | VBW
628 | Kitchen edge banding incorrect in places on cabinets | VBW
629 | Kitchen edge banding | VBW
629 | pantry hinges not closing | VBW
630 | Kitchen edge banding wrong/incorrect | VBW
631 | Upper pantry door off | VBW
632 | Cabinet edge banding incorrect | VBW
632 | Bottom drawer right of dishwasher not closing all the way | VBW
633 | Cabinet edge band incorrect | VBW
633 | Upper above dishwasher broken back | VBW
634 | Cabinet edge band incorrect | VBW
634 | Drawer closure | VBW
636 | Lazy Susan door hitting sink base | VBW
636 | Edge banding loose left lower above kitchen sink | VBW
638 | Cabinet edge bending | VBW
638 | Cabinet pencil marks | VBW

## 7th floor
Pillar Properties Punch List Lyric @ Capital Hill
8/12 - 9/12
APT # | PUNCH ITEM | TRADE | COMPLETION DATE | NOTES
715 | All blinds are missing | Acountable
716 | Blinds missing | Acountable
717 | Blinds missing | Acountable
719 | Blinds missing | Acountable
720 | Blinds missing | Acountable
721 | Final clean needed | Acountable
723 | Blinds missing | Acountable
725 | Blinds missing | Acountable
726 | Blinds missing | Acountable
728 | Blinds missing | Acountable
729 | Blinds missing | Acountable
732 | Blinds missing | Acountable
733 | Blinds missing | Acountable
735 | Blinds missing | Acountable
739 | Blinds missing | Acountable
716 | Wall repair at Breaker box | B230
727 | Wall repair at ISTA box | B230
730 | Wall repair at ISTA box | B230
732 | Wall repair by the ISTA box | B230
735 | Wall repair at ISTA box | B230
715 | Evoke floor pulling apart at kitchen sink | Commercial Int
722 | Caulking at tub and floor transition needed | Commercial Int
723 | Kitchen floor and cabinets need caulking | Commercial Int
724 | Caulking at vanity and floor transition needed | Commercial Int
725 | Seam at dishwasher in flooring pulling apart | Commercial Int
729 | Caulking at vanity and floor transition needed | Commercial Int
730 | Lower cabinet and floor caulking is damaged on lower side | Commercial Int
732 | Caulking at vanity and floor transition needed | Commercial Int
734 | Caulking needed at master bathroom vanity/floor | Commercial Int
735 | Caulking needed at bathroom vanity/floor | Commercial Int
737 | Caulking needed at bathroom vanity/floor | Commercial Int
737 | High spot in the middle of the floor in the living room | Commercial Int
738 | Master bathroom / bed flooring transition missing | Commercial Int
738 | Scratch in floor on right side of living room | Commercial Int
739 | Caulking needed at floor / vanity in bathroom | Commercial Int
739 | Flooring seam pulling at front door | Commercial Int
715 | Vanity mirror missing | Courtesy Glass
725 | 1st bedroom missing escutcheon at fire sprinkler | FPS
715 | Door not latching | Frontier
715 | Laundry door missing | Frontier
715 | Bedroom door rubbing at header | Frontier
719 | Bathroom door not latching | Frontier
720 | Large glass door for bed is difficult to roll | Frontier
724 | Something is incorrect (wrong hardware) | Frontier
726 | Bathroom door not catching | Frontier
726 | Bedroom door not latching properly. | Frontier
727 | Bathroom door not latching | Frontier
727 | Pocket door dragging | Frontier
729 | Coat closet shelf stained front edge at front door | Frontier
733 | Bedroom door not latching properly. | Frontier
733 | Door stop spring pulled | Frontier
734 | Bedroom door doesn't latch | Frontier
736 | Master bathroom door not latching | Frontier
736 | Bedroom door not latching properly. | Frontier
737 | Bedroom door rubbing / not latching | Frontier
738 | Bedroom door stop missing in master bedroom | Frontier
738 | Bathroom door not latching | Frontier
738 | Bedroom door not latching properly. | Frontier
722 | Washer and dryer missing | GE
723 | Washer trim at wall off | GE
724 | Fridge light out | GE
724 | Stove missing | GE
731 | Microwave inoperable | GE
731 | Disposal inoperable | GE
731 | Washer not hooked up | GE
737 | Fridge missing handle plugs - left side | GE
738 | Fridge is off | GE
739 | Disposal making a lot of noise | GE / OWP
715 | Paint on bathroom timer | Greens
715 | Paint touch up corner of upper right above microwave | Greens
715 | Bed casing need finished and caulked | Greens
717 | Laundry closet rod backing has nail holes | Greens
717 | Bathroom shelf, paint touch up | Greens
718 | Master bedroom wall at closet ceiling / wall needs cut in - wall facing window. | Greens
718 | Caulking needed in bathroom floor and at vanity. | Greens
719 | Caulking needed in bathroom floor and at vanity. | Greens
723 | Caulking around cabinets needed | Greens
724 | Paint exterior at patio falling off building | Greens
725 | Backsplash at kitchen counter needs caulked | Greens
725 | Siding paint touchup outside 1st bedroom window right side | Greens
725 | Bed 2 paint touchup at right side white overspray | Greens
726 | Kitchen backsplash needs recaulked | Greens
726 | Paint touch up at outlet kitchen sink left hand side | Greens
728 | Caulking above laundry door casing | Greens
728 | Paint touch up at kitchen wall near den | Greens
728 | Paint touch up at shower curtain rod | Greens
730 | Paint peeling off exterior patio (white) | Greens
730 | Exterior paint touch up | Greens
733 | Bedroom closet top right corner chipped at casing | Greens
734 | Paint touch up needed at blank plat in bathroom | Greens
734 | Paint touch up at ISTA box needed | Greens
736 | Paint touch up at bathroom fan | Greens
738 | Paint needed at shower curtain rod right side | Greens
739 | Paint touch up needed at ISTA box | Greens
722 | Water meters not installed | ISTA
724 | Patio door threshold filler exterior loose | NWI
730 | Patio door threshold filler exterior loose | NWI
730 | Patio door handle loose | NWI
732 | Window needs adjusted/not latching all the way | NWI
715 | Low shower pressure | OWP
715 | Laundry water cover off the wall | OWP
715 | Hot water ISO valve won't open all the way, hits the metal box | OWP
716 | Hot water valve cannot open all the way, hits metal box | OWP
718 | Hot water valve cannot open all the way, hits metal box | OWP
719 | Hot water valve cannot open all the way, hits metal box | OWP
725 | Bathroom caulk at sink needs addressed | OWP
725 | Bathroom vanity caulking at backsplash | OWP
729 | Low shower pressure | OWP
732 | Low water pressure at shower head | OWP
733 | Toilet constantly runs | OWP
735 | Water not working | OWP
736 | Tub drain stop broken | OWP
737 | Low shower head pressure | OWP
738 | Low water pressure in mater bathroom tub | OWP
738 | Tub Drain plug broken | OWP
718 | Transfer vent living room ceiling missing register | Pac 1
731 | Air transfer vent missing in hall and bedroom | Pac 1
734 | Air transfer vent missing above bedroom door | Pac 1
736 | Air transfer vent missing from living room ceiling | Pac 1
715 | Switch cover missing | Robs
715 | Blank plate in bathroom needs white screws | Robs
715 | Kitchen light out | Robs
716 | Bathroom lights are out | Robs
716 | Blank plate in bathroom needs white screws | Robs
717 | Bathroom vanity light missing cover (?) | Robs
717 | Breaker panel doesn't latch | Robs
718 | Master bathroom light out | Robs
719 | Sticker on bathroom vanity light | Robs
724 | Patio outlet 2 exterior boxes? Too far from wall | Robs
727 | Bath light is out | Robs
727 | Blank plate in bathroom needs white screws and is loose | Robs
731 | Upper cabinet door hitting kitchen light fixture | Robs
731 | Breaker panel door not latching | Robs
731 | Dinning room light fixture crooked | Robs
733 | Bathroom light blub is out | Robs
734 | Light out in bathroom fan | Robs
734 | Pendant lights over at island out | Robs
734 | Blank plate in bathroom needs white screws | Robs
736 | GFI at kitchen sink not resetting | Robs
736 | Cabinet upper doors hitting light fixtures | Robs
737 | Vanity light out | Robs
738 | Bathroom outlet cover missing | Robs
739 | Blank plate in bathroom needs white screws | Robs
725 | Vent missing in hallway above outlet high on wall at ceiling | US MECH
728 | VTAC non operable | US MECH
736 | HVAC inoperable | US MECH
739 | VTAC non operable | US MECH
715 | Cabinet door above microwave is off | VBW
715 | Upper cabinet door right of sink rubs soffit | VBW
722 | Vanity chipped at toilet paper holder | VBW
723 | Upper kitchen cabinet door hitting cabinet door above fridge | VBW
723 | Cabinet door right of sink hits soffit | VBW
724 | Upper kitchen cabinet door hitting cabinet door next to it | VBW
725 | Cabinet over sink the edge banding is peeling | VBW
725 | Missing shelf at top pantry cabinet | VBW
726 | Scratch in cabinet left hand side open shelves at kitchen sink | VBW
727 | Scratch in cabinet near kitchen sink | VBW
727 | Panel above doors on right hand side | VBW
728 | Vanity scratched on right side at toilet paper holder | VBW
730 | Cabinet doors above microwave need adjusted | VBW
731 | Lower left corner at pantry jam is peeling | VBW
734 | lower kitchen cabinet side/scratched, caulk to floor | VBW