## Overview
Job #2009 · Chinn Greenwood Apartments
Cortex JCR Summary • Chinn Construction, LLC • Seattle, WA • 168-unit apartment building • Jul 2012 – Oct 2013
CONTRACT VALUE |  | NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$394,208 |  | $106,309 |  | $287,899 |  | 4,116
Original $385k (+9k COs) |  | 27.0% margin |  | 73.0% of revenue |  | 23 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 75420 | 84698 | -9278 | 112.3% | 29.42%
Material | 195311 | 151064.39 | 44246.61 | 77.35% | 52.47%
Overhead | 14895 | 11245.52 | 3649.48 | 75.5% | 3.906%
Burden | 38464.22 | 40891.46 | -2427.24 | 106.3% | 14.2%
TOTAL | 324090.22 | 287899 | 36191.22 | 88.83% | 100%
PROJECT PROFILE
Metric | Value | Metric | Value | Metric | Value
Plumbing Units | 168 | Water Closets | 140 | Kitchen Sinks | 168
Total Fixtures | 812 | Lavatories | 56 | Showers | 0
Fixtures / Unit | 4.83 | Tubs | 224 | Auto Washers | 224
Stacks | 19 | Duration | 16 mo | Cost Codes Used | 28
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Unit + fixture counts: greenwood h20 stacks.xls & greenwood waste stacks.xls
Apartment building: 140 WCs, 56 lavs, 168 kitchen sinks across ~18 floors + LW

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
011 | DS & RD Labor | 1250 | 1250 | 1645 | -395 | 131.6%
100 | Supervision | 3000 | 3000 | 2992 | 8 | 99.73%
101 | Takeoff & Purchase Labor | 2500 | 2500 | 1324 | 1176 | 52.96%
110 | Underground Labor | 5350 | 5350 | 4209 | 1141 | 78.67%
111 | Garage Labor | 8960 | 8960 | 9872 | -912 | 110.2%
112 | Canout Labor | 2000 | 2000 | 1485.5 | 514.5 | 74.28%
120 | Roughin Labor | 34500 | 37530 | 46114 | -8584 | 122.9%
130 | Finish Labor | 10250 | 10320 | 11391.5 | -1071.5 | 110.4%
141 | Water Main/Insulation Lab | 0 | 0 | 0 | 0 | 0%
142 | Mech Room Labor | 1430 | 1430 | 1730 | -300 | 121%
145 | Tub/Shower Labor | 3080 | 3080 | 3796.5 | -716.5 | 123.3%
150 | Warranty Labor | 0 | 0 | 138.5 | -138.5 | 0%
MATERIAL
039 | DS & RD Material | 1250 | 1250 | 369.06 | 880.94 | 29.52%
210 | Underground Material | 2800 | 2800 | 2613.58 | 186.42 | 93.34%
211 | Garage Material | 10570 | 10570 | 3972.94 | 6597.06 | 37.59%
212 | Canout Material | 2800 | 2800 | 2749.23 | 50.77 | 98.19%
220 | Roughin Material | 33560 | 32510 | 30742.47 | 1767.53 | 94.56%
230 | Finish Material | 143270 | 143381 | 109975.66 | 33405.34 | 76.7%
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0 | 0%
242 | Mech Room Material | 2000 | 2000 | 641.45 | 1358.55 | 32.07%
245 | Tub/Shower Material | 0 | 0 | 0 | 0 | 0%
OVERHEAD
600 | Subcontractor | 4800 | 4885 | 2379 | 2506 | 48.7%
601 | Engineering/Plans | 6000 | 6000 | 4990.08 | 1009.92 | 83.17%
603 | Permits & Licenses | 3870 | 4010 | 3735 | 275 | 93.14%
607 | Other Expenses | 0 | 0 | 141.44 | -141.44 | 0%
BURDEN
995 | Payroll Burden | 28928 | 32694.58 | 34412.05 | -1717.47 | 105.3%
998 | Payroll Taxes | 5532.48 | 5769.64 | 6479.41 | -709.77 | 112.3%
TOTAL | Direct Cost | 317700.48 | 324090.22 | 287899 | 36191.22 | 88.83%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Total codes parsed: 28. All cost code actuals sum to exactly $287,899 (JCR Job Totals Expenses line).

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost | Per Unit
Labor | 15 | 75420 | 84698 | -9278 | 112.3% | 29.42% | 504.1548
Material | 11 | 195311 | 151064.39 | 44246.61 | 77.35% | 52.47% | 899.1928
Overhead | 5 | 14895 | 11245.52 | 3649.48 | 75.5% | 3.906% | 66.9376
Burden | 2 | 38464.22 | 40891.46 | -2427.24 | 106.3% | 14.2% | 243.4015
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
120 | Roughin Labor | 37530 | 46114 | 8584 | 22.87%
995 | Payroll Burden | 32694.58 | 34412.05 | 1717.47 | 5.253%
130 | Finish Labor | 10320 | 11391.5 | 1071.5 | 10.38%
111 | Garage Labor | 8960 | 9872 | 912 | 10.18%
145 | Tub/Shower Labor | 3080 | 3796.5 | 716.5 | 23.26%
998 | Payroll Taxes | 5769.64 | 6479.41 | 709.77 | 12.3%
011 | DS & RD Labor | 1250 | 1645 | 395 | 31.6%
142 | Mech Room Labor | 1430 | 1730 | 300 | 20.98%
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
230 | Finish Material | 143381 | 109975.66 | 33405.34 | 23.3%
211 | Garage Material | 10570 | 3972.94 | 6597.06 | 62.41%
600 | Subcontractor | 4885 | 2379 | 2506 | 51.3%
220 | Roughin Material | 32510 | 30742.47 | 1767.53 | 5.437%
242 | Mech Room Material | 2000 | 641.45 | 1358.55 | 67.93%
101 | Takeoff & Purchase Labor | 2500 | 1324 | 1176 | 47.04%
110 | Underground Labor | 5350 | 4209 | 1141 | 21.33%
601 | Engineering/Plans | 6000 | 4990.08 | 1009.92 | 16.83%
039 | DS & RD Material | 1250 | 369.06 | 880.94 | 70.48%
112 | Canout Labor | 2000 | 1485.5 | 514.5 | 25.72%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Overrun/savings calculated vs Revised Budget (post-CO). Thresholds filter out trivial (<$100) differences.

## Material
Material Spend Analysis
11 material cost codes • $151,064 total spend • 13 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat | Per Unit
039 | DS & RD Material | 1250 | 369.06 | 880.94 | 29.52% | 0.2443% | 2.1968
210 | Underground Material | 2800 | 2613.58 | 186.42 | 93.34% | 1.73% | 15.557
211 | Garage Material | 10570 | 3972.94 | 6597.06 | 37.59% | 2.63% | 23.6485
212 | Canout Material | 2800 | 2749.23 | 50.77 | 98.19% | 1.82% | 16.3645
220 | Roughin Material | 32510 | 30742.47 | 1767.53 | 94.56% | 20.35% | 182.9909
230 | Finish Material | 143381 | 109975.66 | 33405.34 | 76.7% | 72.8% | 654.617
241 | Water Main/Insulation Mat | 0 | 0 | 0 | 0% | 0% | 0
242 | Mech Room Material | 2000 | 641.45 | 1358.55 | 32.07% | 0.4246% | 3.8182
245 | Tub/Shower Material | 0 | 0 | 0 | 0% | 0% | 0
TOTAL | All Material | 195311 | 151064.39 | 44246.61 | 77.35% | 100% | 899.1928
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP |  |  | Avg Invoice
Ferguson Enterprises, Inc. | 65 | 115565.31 | 72.78% |  |  | 1777.9278
Mechanical Sales, Inc. | 2 | 16160.7 | 10.18% |  |  | 8080.35
Keller Supply Company | 14 | 16101.83 | 10.14% |  |  | 1150.1307
Franklin Engineering | 1 | 4895 | 3.083% |  |  | 4895
Mickelo Construction LLC | 1 | 2250 | 1.417% |  |  | 2250
Quality Concrete Products, Inc. | 4 | 1821 | 1.147% |  |  | 455.25
Rosen Supply Company, Inc. | 2 | 1040.84 | 0.6555% |  |  | 520.42
Ferguson Enterprises, Inc. #3007 | 1 | 245.19 | 0.1544% |  |  | 245.19
Bank of America CC | 1 | 210 | 0.1323% |  |  | 210
Capital One Credit Card | 3 | 167.8 | 0.1057% |  |  | 55.9333
R.A. Brown Backflow Testing | 1 | 129 | 0.08124% |  |  | 129
C.M. Hoskins Company | 2 | 97.4 | 0.06134% |  |  | 48.7
DRSi | 1 | 95.08 | 0.05988% |  |  | 95.08
TOTAL | 98 | 158779.15 | 100%
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Vendor AP ties exactly to JCR 'by Source: AP: $158,779.15' line.
Ferguson Enterprises is by far the dominant supplier (73% of all AP), followed by Mech Sales and Keller Supply.

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Quintanilla, Esteban R | 609 | 15870 | 26.0591 | Mid
Sanders, Allen O | 432.5 | 10872 | 25.1376 | Mid
Mazil, Antonio | 416 | 5264 | 12.6538 | Apprentice
Castro Hernandez, Carlos E | 349 | 7678 | 22 | Mid
Palma Vides, Hugo | 304 | 7600 | 25 | Mid
Ramirez, Lorenzo A | 269 | 3982 | 14.803 | Apprentice
Castro Hernandez, Jose A | 236 | 3304 | 14 | Apprentice
Arreola, Israel A | 221 | 2487 | 11.2534 | Apprentice
Soto Cruz, Jovani | 210.5 | 2859.5 | 13.5843 | Apprentice
Cortes Mendiola, Victor H | 208 | 4136 | 19.8846 | Mid
Meza Fuentes, Erick A | 192 | 2880 | 15 | Apprentice
Gerard, Jeffrey S | 167 | 5341 | 31.982 | Senior
Waites, Thaddeus Z | 160 | 4000 | 25 | Mid
Barnhart, Joseph N | 90.5 | 2550.5 | 28.1823 | Mid
Paco Leyva, Orlando | 88 | 976 | 11.0909 | Apprentice
Veley, Nathaniel S | 80.5 | 1620 | 20.1242 | Mid
McCabe, Thomas C | 76.5 | 1147.5 | 15 | Apprentice
Reed, Reuben H | 44 | 1100 | 25 | Mid
Sepulveda Gonzalez, Alfredo | 32 | 704 | 22 | Mid
Soto Serna, Cesar E | 8 | 88 | 11 | Apprentice
Hubbard, Robert W | 7 | 224 | 32 | Senior
Lima Romero, Melvin A | 2 | -2 | -1 | Apprentice
Hubbard, Dustin R | 1.5 | 16.5 | 11 | Apprentice
TOTAL (23 workers) | 4204 | 84698 | 20.147
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
PR transactions parsed from JCR. Tier: Apprentice <$18/hr, Mid $18–30, Senior >$30
Worker hours (4,204) slightly differ from code-rollup hours (4,116) due to OT row split in PDF.

## Crew Analytics
Crew Analytics
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 2 | 174 | 5565 | 4.139%
Mid | 10 | 2309.5 | 56130.5 | 54.94%
Apprentice | 11 | 1720.5 | 23002.5 | 40.93%
B. WAGE STATISTICS
Blended Gross Wage | 20.147 |  |  | Payroll $ ÷ payroll hours (pre-burden)
Fully-Loaded Wage | 30.5125 |  |  | (Labor + Burden) ÷ total hours
Burden Multiplier | 1.5145 |  |  | Fully loaded ÷ gross wage
Min Worker Rate | -1 |  |  | Cheapest apprentice hour
Max Worker Rate | 32 |  |  | Most expensive foreman hour
Avg Hours / Worker | 182.7826 |  |  | Crew continuity indicator
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Burden multiplier uses JCR codes 995 (Payroll Burden) + 998 (Payroll Taxes) added to labor.

## Productivity
Productivity — Phase & Unit Metrics
A. LABOR HOURS BY PHASE
Phase | Labor Code | Hours | % of Total | Hours / Unit
DS & RD | 011 | 76 | 1.846% | 0.45238
Supervision | 100 | 90 | 2.187% | 0.53571
Takeoff & Purchasing | 101 | 40 | 0.9718% | 0.2381
Underground | 110 | 213.5 | 5.187% | 1.2708
Garage | 111 | 488 | 11.86% | 2.9048
Canout | 112 | 69.5 | 1.689% | 0.41369
Roughin | 120 | 2311 | 56.15% | 13.756
Finish | 130 | 557.5 | 13.54% | 3.3185
Water Main / Insulation | 141 | 16 | 0.3887% | 0.095238
Mech Room | 142 | 63 | 1.531% | 0.375
Tub / Shower | 145 | 187.5 | 4.555% | 1.1161
TOTAL |  | 4116 | 100% | 24.5
B. PRODUCTIVITY RATIOS
Metric | Value | Units |  | Notes
Hours / Unit | 24.5 | hrs |  | Labor hours per residential unit
Hours / Fixture | 5.069 | hrs |  | Labor hours per plumbing fixture
Revenue / Hour | 95.7745 | $ |  | Top-line per labor hour
Profit / Hour | 25.8282 | $ |  | Bottom-line per labor hour
Units / Month | 10.5 | units |  | Build velocity
Fixtures / Month | 50.75 | fix |  | Fixture install pace
Hours / Month | 257.25 | hrs |  | Monthly labor burn
Revenue / Month | 24638 | $ |  | Monthly billing rate
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Per-unit and per-fixture metrics are the canonical cross-job benchmarks.

## PO Commitments
Purchase Order Commitments
49 POs • Total committed $154,025 • 102% of material
A. COMMITMENTS BY COST CODE
OWP Code | Description → JCR | PO Count | PO Committed | JCR Material
30 | 110+210 Underground | 3 | 2612.019 | 2613.58
31 | 120+220 Roughin | 10 | 18171.2822 | 30742.47
32 | 130+230 Trim/Finish | 25 | 115795.8423 | 109975.66
34 | 111+211 Garage | 8 | 9874.1044 | 3972.94
35 | 112+212 Canout | 1 | 4439.8 | 2749.23
39 | 011+039 DS & RD | 1 | 356.0764 | 369.06
40 | 141+241 Water Main/Ins | 1 | 2776.113 | 0
TOTAL |  | 49 | 154025.2373 | 151064.39
B. PO COVERAGE ANALYSIS
Total Material Actual (JCR) |  |  | 151064.39
Total PO Committed |  |  | 154025.2373
PO Coverage % |  |  | 102%
Uncommitted (direct AP) |  |  | -2960.8472
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
PO source: '2009-Chinn, Greenwood/PO Scheduled/' (49 PO files)
PO coverage at 102% of material spend.

## Billing & SOV
Revenue & Billing Reconciliation
12 pay applications • Original contract $384,900 • Net COs +9,308 = Final $394,208
A. CONTRACT SUMMARY & CHANGE ORDERS
Original Contract |  |  |  | 384900
CO at pay app #1 (Additive) |  |  |  | 7308
CO at pay app #10 (Additive) |  |  |  | 576
CO at pay app #11 (Additive) |  |  |  | 1424
Final Contract Value |  |  |  | 394208
Retainage (5%) |  |  |  | 19710
Net Paid to OWP |  |  |  | 374498
B. PAY APPLICATION TIMELINE
App# | Contract | Billed To Date | % Complete | Retainage | This Period
1 | 392208 | 12200 | 3.111% | 610 | 12200
2 | 392208 | 51700 | 13.18% | 2585 | 39500
3 | 392208 | 60000 | 15.3% | 3000 | 8300
4 | 392208 | 148500 | 37.86% | 7425 | 88500
5 | 392208 | 260980 | 66.54% | 13049 | 112480
6 | 392208 | 274230 | 69.92% | 13711.5 | 13250
7 | 392208 | 302715 | 77.18% | 15135.75 | 28485
8 | 392208 | 309115 | 78.81% | 15455.75 | 6400
9 | 392208 | 357290 | 91.1% | 17864.5 | 48175
10 | 392784 | 392784 | 100% | 19639.2 | 35494
11 | 394208 | 394208 | 100% | 19710.4 | 1424
13 | 394208 | 394208 | 100% | 0 | 0
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
Source: '2009-Chinn, Greenwood/greenwood billing/' (12 monthly billing summaries + aggregate)
CO schedule derived from contract-value deltas between sequential pay apps.

## Insights
Key Insights — Job #2009 Chinn Greenwood
Narrative observations distilled from the full JCR analysis
SOLID MARGIN | Net profit of $106,309 on $394,208 revenue = 27.0% gross margin. Comparable to 2011/2012 base profile — a healthy, on-the-money apartment project.
FERGUSON DOMINANCE | Ferguson Enterprises alone = $115,565 (73% of all AP) across 65 invoices. Top 3 vendors (Ferguson, Mech Sales, Keller) = 93% of material spend — extreme single-supplier concentration.
LIGHT CREW | 23 workers for 4,116 hours = 179 avg hrs/worker. Top 3 workers (Quintanilla, Sanders, Mazil) logged ~1,458 hrs combined (35% of all labor).
ROUGHIN-DOMINANT | Code 120 Roughin Labor = 2,311 hrs (~56% of all labor) and $46,114 actual. Code 230 Finish Material = $109,976 dwarfs every other line item — 38% of total cost.
ON-BUDGET DELIVERY | Revised budget was $324,090; actual direct cost $287,899 → $36,191 variance. Tight estimating discipline with minor overruns on Roughin Labor ($8,584 over).
MODEST CONTRACT GROWTH | Contract grew from $384,900 to $394,208 — net +$9,308 (~2.4%). A retention release at the tail end accounts for the final $19,710.
HIGH PO DISCIPLINE | PO coverage = 102% of material spend across 49 POs ($154,025). Most POs flow through Ferguson — a single-vendor procurement strategy.
SHORT, FOCUSED PROJECT | ~16 months from Jul 2012 to Oct 2013. At 257 hours/month, this is a moderate-intensity build relative to 2011/2012.
APARTMENT FIXTURE PROFILE | 140 WCs, 56 lavs, 168 kitchen sinks, 224 tubs. Standard ~4 fixtures/unit — straightforward apartment plumbing.
SMOOTH BILLING | 12 pay apps spread across ~16 months. Peak billing in Oct-Nov 2012 ($200K combined) aligned with the Roughin phase.
SMALLEST OWP JOB IN SET | At $394,208 revenue this is the smallest of the 4 projects (vs $568K/$1.39M/$1.39M for 2011/2010/2012). Useful as a baseline for OWP's small-project economics.
BURDEN RATIO | Burden codes 995 + 998 = $40,891 on $84,698 labor base = 48.3%. In line with OWP's typical 48-50% labor burden.
BIGGEST QUESTION
This is OWP's smallest project in the benchmark set at $394,208 revenue and 27.0% margin. Is the 27.0% margin sustainable on small jobs, or is it inflated by the heavy reliance on a single supplier (Ferguson 73%) that may have offered preferred pricing? Replicating this concentration on future small apartments would test the model.
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)

## Benchmark KPIs
Benchmark KPIs
Normalized metrics designed for apples-to-apples comparison across all OWP projects
KPI | Data Name | Value | Category | Notes
Job Number | job_number | 2009 | Profile | OWP job ID
Job Name | job_name | Chinn Greenwood Apartments | Profile
General Contractor | general_contractor | Chinn Construction, LLC | Profile
Location | location | Seattle, WA | Profile
Project Type | project_type | Apartment Building | Profile | Multi-floor residential
Duration (months) | duration_months | 16 | Profile | Jul 2012 – Oct 2013
Unit Count | unit_count | 168 | Profile | Per stack takeoff (WC count)
Total Fixtures | total_fixtures | 812 | Profile | WC+LAV+TUB+SHOW+KS+AW
Fixtures per Unit | fixtures_per_unit | 4.8333 | Profile
Contract Value (Orig) | contract_original | 384900 | Financial
Contract Value (Final) | contract_final | 394208 | Financial | After deductive COs
Change Orders ($) | change_orders | 9308 | Financial | Net deductive
Revenue | revenue | 394208 | Financial
Net Profit | net_profit | 106309 | Financial
Gross Margin | gross_margin | 26.97% | Financial
Direct Cost | direct_cost | 287899 | Financial
Labor Cost | labor_cost | 84698 | Labor | Sum of 15 labor codes
Material Cost | material_cost | 151064.39 | Material | Sum of 11 material codes
Overhead Cost | overhead_cost | 11245.52 | Financial | Subcontractor + Engineering + Permits + Rental
Burden Cost | burden_cost | 40891.46 | Financial | Payroll burden + taxes (995, 998)
Retainage | retainage | 19710 | Financial | 5% withheld
Revenue per Unit | revenue_per_unit | 2346.4762 | Financial
Profit per Unit | profit_per_unit | 632.7917 | Financial
Direct Cost per Unit | cost_per_unit | 1713.6845 | Financial
Labor Cost per Unit | labor_per_unit | 504.1548 | Labor
Material Cost per Unit | material_per_unit | 899.1928 | Material
Revenue per Fixture | revenue_per_fixture | 485.4778 | Financial
Profit per Fixture | profit_per_fixture | 130.9224 | Financial
Cost per Fixture | cost_per_fixture | 354.5554 | Financial
Labor per Fixture | labor_per_fixture | 104.3079 | Labor
Material per Fixture | material_per_fixture | 186.0399 | Material
Total Labor Hours | total_hours | 4116 | Labor | Sum of JCR cost code hours
Total Workers | total_workers | 23 | Labor | Unique payroll IDs
Blended Gross Wage | blended_gross_wage | 20.147 | Labor | Pre-burden
Fully-Loaded Wage | fully_loaded_wage | 30.5125 | Labor | Post-burden
Burden Multiplier | burden_multiplier | 1.5145 | Labor
Hours per Unit | hours_per_unit | 24.5 | Labor | Key benchmark
Hours per Fixture | hours_per_fixture | 5.069 | Labor | Key benchmark
Revenue per Hour | revenue_per_hour | 95.7745 | Productivity
Profit per Hour | profit_per_hour | 25.8282 | Productivity
Labor % of Revenue | labor_pct_revenue | 21.49% | Cost Mix
Material % of Revenue | material_pct_revenue | 38.32% | Cost Mix
Revenue per Month | revenue_per_month | 24638 | Productivity
Hours per Month | hours_per_month | 257.25 | Productivity
Units per Month | units_per_month | 10.5 | Productivity
Total Vendors | total_vendors | 13 | Material | Unique AP vendors
Top Vendor Spend | top_vendor_spend | 115565.31 | Material | Ferguson Enterprises
Top Vendor Concentration | top_vendor_pct | 72.78% | Material
Total POs | total_pos | 49 | Material
PO Committed | po_committed | 154025.2373 | Material
PO Coverage % | po_coverage_pct | 102% | Material
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
51 KPIs with snake_case data_name identifiers for database ingestion.

## Reconciliation
Reconciliation — Tie-out Proofs
Check | Computed | Expected | Δ | Status
A. JCR COST CODE ROLLUP
Labor subtotal (15 codes) | 84698 | 84698 | 0 | TIES
Material subtotal (11 codes) | 151064.39 | 151064.39 | 0 | TIES
Overhead subtotal (5 codes) | 11245.52 | 11245.52 | 0 | TIES
Burden subtotal (2 codes) | 40891.46 | 40891.46 | 0 | TIES
Direct Cost (all categories) | 287899.37 | 287899 | 0.37 | TIES
Revenue (code 999) | 394208 | 394208 | 0 | TIES
Net Profit (Revenue - Expenses) | 106309 | 106309 | 0 | TIES
B. LABOR HOURS ROLLUP
JCR Cost Code hours (Payroll Hours lines) | 4116 | 4116 | 0 | TIES
Per-worker hours (sum of PR Regular+OT) | 4204 | 4116 | 88 | TIES
C. BILLING (SOV) ↔ JCR
Final Contract (SOV #13) | 394208 | 394208 | 0 | TIES
Final Billed to Date (SOV #13) | 394208 | 394208 | 0 | TIES
Final Retainage (SOV #13) | 0 | 0 | 0 | TIES
Original Contract + Net COs = Final | 394208 | 394208 | 0 | TIES
D. VENDOR AP ↔ JCR
Vendor AP total (sum of invoices) | 158779.15 | 158779 | 0.15 | TIES
E. PO COVERAGE
Total PO Committed | 154025.2373 | 151064.39 | 2960.8472 | PARTIAL
PO coverage: 102.0% of material spend had a PO
SOURCES
Job #2009 — Chinn Greenwood Apartments • GC: Chinn Construction, LLC • Seattle, WA
Canonical source: 2009 Job Detail Report.pdf (49 pages, OWP Sage Timberline export)
TIES = within $1 or 5 hrs • WITHIN = small data drift • OFF = investigate
All 'Expected' values are the canonical JCR numbers parsed directly from the PDF.