## Schedule of V. Backup
SCHEDULE OF VALUES
One-Way Plumbing Contract Schedule of Values Work Sheet
To be submitted with applications for payment
PROJECT: Greenwood Apartments |  |  |  |  | PAY APPLICATION #: | 11
LOCATION: Seattle, WA |  |  |  |  | APPLICATION DATE: | 2013-08-13
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: | 2013-08-25
A | B |  | C | D | E | F | G |  | H | I
Area or | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
building or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
floor |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 384900 | 384900 | 0 |  | 384900 |  | 0 | 19245
| plumbing design and shop drawings | SWINERTON | 12900 | 12900 | 0 |  | 12900 | 100% | 0 | 645
| plumbing permit |  | 4300 | 4300 | 0 |  | 4300 | 100% | 0 | 215
underground | garage drains/basins, underground waste piping | SWINERTON | 34500 | 34500 | 0 |  | 34500 | 100% | 0 | 1725
level R1 deck | canout/sleeve at level R1 PT deck | SWINERTON | 8300 | 8300 | 0 |  | 8300 | 100% | 0 | 415
street level | roughin plumbing at live/work, parking garage level |  | 55600 | 55600 | 0 |  | 55600 | 100% | 0 | 2780
street level | stock bathtubs at street level |  | 1010 | 1010 | 0 |  | 1010 | 100% | 0 | 50.5
street level | install bathtubs at street level |  | 180 | 180 | 0 |  | 180 | 100% | 0 | 9
mech room | install duplex water pressure booster package |  | 17200 | 17200 | 0 |  | 17200 | 100% | 0 | 860
storm pump | install pumps in storm basin |  | 6400 | 6400 | 0 |  | 6400 | 100% | 0 | 320
level R1 | roughin plumbing at level R1 |  | 44100 | 44100 | 0 |  | 44100 | 100% | 0 | 2205
level R1 | stock bathtubs at level R1 |  | 9090 | 9090 | 0 |  | 9090 | 100% | 0 | 454.5
level R1 | install bathtubs/valves at level R1 |  | 1620 | 1620 | 0 |  | 1620 | 100% | 0 | 81
level R2 | roughin plumbing at level R2 |  | 44100 | 44100 | 0 |  | 44100 | 100% | 0 | 2205
level R2 | stock bathtubs at level R2 |  | 9090 | 9090 | 0 |  | 9090 | 100% | 0 | 454.5
level R2 | install bathtubs/valves at level R2 |  | 1620 | 1620 | 0 |  | 1620 | 100% | 0 | 81
level R3 | roughin plumbing at level R3 |  | 44100 | 44100 | 0 |  | 44100 | 100% | 0 | 2205
level R3 | stock bathtubs at level R3 |  | 9090 | 9090 | 0 |  | 9090 | 100% | 0 | 454.5
level R3 | install bathtubs/valves at level R3 |  | 1620 | 1620 | 0 |  | 1620 | 100% | 0 | 81
live/work trim | install toilets, lavs and sinks at live/work units |  | 2860 | 2860 | 0 |  | 2860 | 100% | 0 | 143
level R1 | install toilets, lavs and sinks at level R1 |  | 25740 | 25740 | 0 |  | 25740 | 100% | 0 | 1287
level R2 | install toilets, lavs and sinks at level R2 |  | 25740 | 25740 | 0 |  | 25740 | 100% | 0 | 1287
level R3 | install toilets, lavs and sinks at level R3 |  | 25740 | 25740 | 0 |  | 25740 | 100% | 0 | 1287
SUBTOTAL |  |  | 384900 | 384900 | 0 | 0 | 384900 |  | 0 | 19245
CO # | CHANGE ORDERS
CO#1 | change copper to cpvc & pex |  | -1950 | -1950 | 0 |  | -1950 | 100% | 0 | -97.5
CO#1 | add disposals |  | 4760 | 4760 | 0 |  | 4760 | 100% | 0 | 238
CO#1 | change kitchen sinks from under mount to drop in. |  | -2856 | -2856 | 0 |  | -2856 | 100% | 0 | -142.8
CO#2 | add 5 downspout pickups for parapet change |  | 5189 | 5189 | 0 |  | 5189 | 100% | 0 | 259.45
CO#3 | add trash chute washdown |  | 1211 | 1211 | 0 |  | 1211 | 100% | 0 | 60.55
CO#4 | ri for rooftop bar sink |  | 1056 | 1056 | 0 |  | 1056 | 100% | 0 | 52.8
CO#4 | relocate kitchen sink RI 3 units |  | 474 | 474 | 0 |  | 474 | 100% | 0 | 23.7
CO#5 | ada clearance changes |  | 1353 |  | 1353 |  | 1353 | 100% | 0 | 67.65
9237 | CONTRACT TOTAL |  | 394137 | 392784 | 1353 | 0 | 394137 |  | 0 | 19706.85
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN