## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | Greenwood & 107th Apt (12-0304) |  |  | DATE: | 2013-08-13
SUBCONTRACTOR: | ONE WAY PLUMBING, LLC
SERVICE PROVIDED:
BILLING PERIOD: | 8-1-13 - 8-31-13 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 384900 | a
| Previous Billing CHANGE ORDERS: | 7884 | b
| This Billing CHANGE ORDERS: | 1353 | c
| NEW CONTRACT TOTAL: | 394137 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 394137 | e
| AMOUNT REMAINING ON CONTRACT: | 0 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 384900 | g = e
| Previous retention held - total: | 19245 | h
| TOTAL PAID TO DATE 1: | 373144.8 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 1353 | j
| Current retainage held: | 67.65 | k
| CURRENT DUE 2: | 1285.35 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT