## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | Greenwood & 107th Apt (12-0304) |  |  | DATE: | 2013-03-19
SUBCONTRACTOR: | ONE WAY PLUMBING, LLC
SERVICE PROVIDED:
BILLING PERIOD: | 3-1-13 - 3-31-13 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 384900 | a
| Previous Billing CHANGE ORDERS: | 6199 | b
| This Billing CHANGE ORDERS: | 0 | c
| NEW CONTRACT TOTAL: | 391099 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 309115 | e
| AMOUNT REMAINING ON CONTRACT: | 81984 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 302715 | g = e
| Previous retention held - total: | 15135.75 | h
| TOTAL PAID TO DATE 1: | 260518.5 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 6400 | j
| Current retainage held: | 320 | k
| CURRENT DUE 2: | 6080 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT