## Executive Summary
CORTEX PROJECT INTELLIGENCE REPORT
Project: 2009 - Chinn Greenwood Ave Apartments
Contractor: OWP, LLC (One-Way Plumbing)
GC: Chinn Construction, LLC
Report Date: April 5, 2026
SECTION | METRIC | VALUE | NOTES
Project Overview | Job Number | 2009 | Chinn Greenwood Ave Apts
| Location | Seattle, WA (Greenwood & 107th) | Multi-family residential apartments
| Trade | Plumbing | Specialty subcontractor
| General Contractor | Chinn Construction, LLC | Identified from AR invoices in JDR
| Project Duration | Jul 2012 - Aug 2013 (~13 months) | Permit to final billing
| Total Documents | 317 files | 124 PDF, 164 XLS/XLSX, 26 DOC/DOCX, 2 ZIP, 1 DB
| Duplicate Files | 79 exact duplicate groups (158 files) | 25% of all files are duplicates
Financial Summary | Total Revenue (Billed) | $394,208.00 | 12 invoices to Chinn Construction
| Total Expenses | $287,899.37 | GL $3,531 + AP $158,779 + PR $125,589
| Net Profit | $106,308.63 | 27.0% profit margin
| Retainage Outstanding | $19,710.40 | 5% of revenue - still held
| Budget vs Actual | $9,308 better than budget | Revenue +2.4%, material savings offset labor overruns
Expense Breakdown | Direct Labor | $84,698.00 | 29.4% of expenses ¦ 4,116 hours ¦ $20.58/hr avg
| Payroll Burden | $34,412.05 | 11.9% of expenses
| Payroll Taxes | $6,479.41 | 2.2% of expenses
| Materials | $151,064.39 | 52.5% of expenses ¦ 23% under budget
| Subcontractor | $2,379.00 | 0.8% ¦ Backflow testing, concrete
| Engineering/Plans | $4,990.08 | 1.7% ¦ DRSi, Franklin Engineering
| Permits & Licenses | $3,735.00 | 1.3%
| Other Expenses | $141.44 | <0.1%
Key Findings | Profit Margin | 27.0% - Strong | Well above 15-20% industry avg for plumbing subs
| Labor:Material Ratio | 44:52 | Normal range (industry: 40-60% labor, 30-50% material)
| Biggest Budget Overrun | Roughin Labor +$11,614 (+33.7%) | 2,311 hours vs budgeted — scope/complexity underestimated
| Biggest Savings | Finish Material -$33,294 (-23.2%) | Strong procurement/buyout on fixtures
| Workforce | 22 workers, peak crew ~12 | Superintendent: Jeffrey Gerard (full project)
Cortex Coverage | Schemas Present | 5 of 13 | Submittal, Pay Apps, Job Cost, Design Changes, PO
| Schemas Missing | 8 of 13 | Contract Clause, Change Order, RFI, Daily Report, etc.
| Use Cases Unlockable | ~8 of 30 | Limited by missing schemas
| Estimated Coverage | 18.6% | 64 of 344 Cortex fields coverable

## Profitability Summary
PROFITABILITY SUMMARY — JOB 2009 CHINN GREENWOOD
FINANCIAL OVERVIEW
Metric | Amount | Notes
Total Revenue (Billed to GC) | 394208 | 12 invoices to Chinn Construction, LLC
Total Expenses | 287899.37 | GL $3,530.76 + AP $158,779.15 + PR $125,589.46
Net Profit | 106308.63 | Formula
Profit Margin % | 26.97% | Formula
Retainage Outstanding | 19710.4 | 5% of revenue — still held by GC
Original Revenue Budget | 384900 | From JDR Org Budget
Revenue vs Budget Variance | 9308 | Formula
COST BREAKDOWN BY CATEGORY
Category | Cost Code Range | Org Budget | Actual Amount | Budget Variance | % of Expenses | Assessment
Direct Labor | 011-150 | 72320 | 84698 | 12378 | 29.42% | 17.1% over budget — Roughin drove overrun
Payroll Burden | 995 | 28928 | 34412.05 | 5484.05 | 11.95% | Scales with labor hours
Payroll Taxes | 998 | 5532.48 | 6479.41 | 946.93 | 2.251% | Scales with labor hours
Materials | 039, 210-245 | 196250 | 151064.39 | -45185.61 | 52.47% | 23% UNDER budget — strong buyout savings
Subcontractor | 600 | 4800 | 2379 | -2421 | 0.8263% | Backflow testing, concrete work
Engineering/Plans | 601 | 6000 | 4990.08 | -1009.92 | 1.733% | DRSi, Franklin Engineering
Permits & Licenses | 603 | 3870 | 3735 | -135 | 1.297% | Seattle plumbing + backflow permits
Other Expenses | 607 | 0 | 141.44 | 141.44 | 0.04913% | Miscellaneous
TOTAL EXPENSES |  | 317700.48 | 287899.37 | -29801.11
COST CODE DETAIL — ALL 28 CODES
Code | Description | Type | Org Budget | Rev Budget | +/- Budget | Actual Amount | Bgt Var %
011 | DS & RD Labor | Labor | 1250 | 1250 | 395 | 1645 | 31.6%
039 | DS & RD Material | Material | 1250 | 1250 | -880.94 | 369.06 | -70.48%
100 | Supervision | Labor | 3000 | 3000 | -8 | 2992 | -0.2667%
101 | Takeoff & Purchase Labor | Labor | 2500 | 2500 | -1176 | 1324 | -47.04%
110 | Underground Labor | Labor | 5350 | 5350 | -1141 | 4209 | -21.33%
111 | Garage Labor | Labor | 8960 | 8960 | 912 | 9872 | 10.18%
112 | Canout Labor | Labor | 2000 | 2000 | -514.5 | 1485.5 | -25.72%
120 | Roughin Labor | Labor | 34500 | 37530 | 8584 | 46114 | 33.66%
130 | Finish Labor | Labor | 10250 | 10320 | 1071.5 | 11391.5 | 11.14%
141 | Water Main/Insulation Lab | Labor | 0 | 0 | 0 | 0 | N/A
142 | Mech Room Labor | Labor | 1430 | 1430 | 300 | 1730 | 20.98%
145 | Tub/Shower Labor | Labor | 3080 | 3080 | 716.5 | 3796.5 | 23.26%
150 | Warranty Labor | Labor | 0 | 0 | 138.5 | 138.5 | N/A
210 | Underground Material | Material | 2800 | 2800 | -186.42 | 2613.58 | -6.658%
211 | Garage Material | Material | 10570 | 10570 | -6597.06 | 3972.94 | -62.41%
212 | Canout Material | Material | 2800 | 2800 | -50.77 | 2749.23 | -1.813%
220 | Roughin Material | Material | 33560 | 32510 | -1767.53 | 30742.47 | -8.396%
230 | Finish Material | Material | 143270 | 143381 | -33405.34 | 109975.66 | -23.24%
241 | Water Main/Insul Mat | Material | 0 | 0 | 0 | 0 | N/A
242 | Mech Room Material | Material | 2000 | 2000 | -1358.55 | 641.45 | -67.93%
245 | Tub/Shower Material | Material | 0 | 0 | 0 | 0 | N/A
600 | Subcontractor | Other | 4800 | 4800 | -2421 | 2379 | -50.44%
601 | Engineering/Plans | Other | 6000 | 6000 | -1009.92 | 4990.08 | -16.83%
603 | Permits & Licenses | Other | 3870 | 4010 | -275 | 3735 | -3.488%
607 | Other Expenses | Other | 0 | 0 | 141.44 | 141.44 | N/A
995 | Payroll Burden | Overhead | 28928 | 32694.58 | 1717.47 | 34412.05 | 18.96%
998 | Payroll Taxes | Overhead | 5532.48 | 5769.64 | 709.77 | 6479.41 | 17.12%
999 | Sales (Revenue) | Revenue | -384900 | -394208 | 0 | -394208 | -2.418%
REVENUE DETAIL — BILLINGS TO CHINN CONSTRUCTION, LLC
Date | Invoice # | Amount | Retainage (5%) | Notes
07/19/12 | 036335 | $3,300 + $4,300 + $4,600 | $165 + $215 + $230 | Underground phase
08/16/12 | 036340 | $9,600 + $29,900 | $480 + $1,495 | Underground + Roughin start
09/20/12 | 036344 | $8,300 | $415 | Roughin
10/18/12 | 036351 | $44,500 + $35,000 + $9,000 | $2,225 + $1,750 + $450 | Peak roughin billing
11/15/12 | 036356 | $1,010 + $9,100 + $9,090 + $35,100 + $9,090 + $40,000 + $9,090 | $50.50 + various | Major roughin billing
12/20/12 | 036364 | $11,100 + $4,100 + $1,950 credit | $555 + $205 + $97.50 credit | Roughin close-out
02/19/13 | 036373 | $180 + $17,200 + multi items | $9 + $860 + various | Trim start + retainage adj
03/19/13 | 036379 | $6,400 | $320 | Trim
04/18/13 | 036389 | $20,000 + $25,740 + others | $1,000 + $1,287 + various | Trim major billing
05/16/13 | 036400 | $2,860 + $25,740 + $5,740 + others | $143 + $1,287 + various | Trim + finish billing
08/20/13 | 036419 | $71 credit | $3.55 credit | Adjustment
08/27/13 | 036418 | $1,353 credit | $67.65 credit | Final adjustment
TOTAL BILLED |  | $394,208.00 | $19,710.40

## Labor & Productivity
LABOR & PRODUCTIVITY ANALYSIS
LABOR HOURS & COST BY PHASE
Code | Phase | Org Budget | Actual Amount | Hours | $/Hour | Budget Var $ | Budget Var %
011 | DS & RD | 1250 | 1645 | 76 | 21.6447 | 395 | 31.6%
100 | Supervision | 3000 | 2992 | 90 | 33.2444 | -8 | -0.2667%
101 | Takeoff & Purchase | 2500 | 1324 | 40 | 33.1 | -1176 | -47.04%
110 | Underground | 5350 | 4209 | 213.5 | 19.7143 | -1141 | -21.33%
111 | Garage | 8960 | 9872 | 488 | 20.2295 | 912 | 10.18%
112 | Canout | 2000 | 1485.5 | 69.5 | 21.3741 | -514.5 | -25.72%
120 | Roughin | 34500 | 46114 | 2311 | 19.9541 | 11614 | 33.66%
130 | Finish/Trim | 10250 | 11391.5 | 557.5 | 20.4332 | 1141.5 | 11.14%
141 | Water Main/Insulation | 0 | 0 | 16 | 0 | 0 | N/A
142 | Mech Room | 1430 | 1730 | 63 | 27.4603 | 300 | 20.98%
145 | Tub/Shower | 3080 | 3796.5 | 187.5 | 20.248 | 716.5 | 23.26%
150 | Warranty | 0 | 138.5 | 4 | 34.625 | 138.5 | N/A
TOTAL |  | 72320 | 84698 | 4116 | 20.5777 | 12378 | 17.12%
KEY LABOR METRICS
Total Direct Labor Cost | 84698
Total Labor Hours | 4116
Effective Labor Rate (avg) | 20.5777
Labor as % of Total Expenses | 29.42%
Labor + Burden + Tax as % of Expenses | 43.62%
Roughin % of Total Labor | 54.45%
Roughin % of Total Hours | 56.15%
Peak Crew Size (Oct 2012 roughin) | 12
Unique Workers on Project | 22
WORKER ROSTER
Name | Employee Code | Role | Primary Phase(s)
Gerard, Jeffrey S | GE69 | Superintendent/PM | All phases (Jul 2012 - Jun 2013)
Quintanilla, Esteban R | QU35 | Lead Plumber | Roughin, Garage, Mech Room (highest hours)
Castro Hernandez, Carlos E | CA75 | Journeyman | Roughin, Finish
Castro Hernandez, Jose A | CA77 | Journeyman | Roughin, Finish
Palma Vides, Hugo | PA46 | Journeyman | Roughin (40hr weeks)
Sanders, Allen O | SA54 | Journeyman | Roughin, Finish, Trim
Ramirez, Lorenzo A | RA50 | Journeyman | Roughin
Mazil, Antonio | MA98 | Journeyman | Roughin
Cortes Mendiola, Victor H | CO71 | Journeyman | Roughin
Arreola, Israel A | AR70 | Journeyman | Roughin
Veley, Nathaniel S | VE45 | Journeyman | Underground
Hubbard, Robert W | HU06 | Apprentice | Underground
Meza Fuentes, Erick A | ME98 | Journeyman | Roughin, Finish
McCabe, Thomas C | MC09 | Journeyman | DS&RD, Finish
Waites, Thaddeus Z | WA35 | Journeyman | Roughin
Barnhart, Joseph N | BA70 | Journeyman | Finish, Trim
Soto Cruz, Jovani | SO78 | Journeyman | Finish, Trim
Paco Leyva, Orlando | PA11 | Journeyman | Roughin
Reed, Reuben H | RE18 | Journeyman | Underground (short stint)
Sepulveda Gonzalez, Alfredo | SE64 | Journeyman | Finish
Lima Romero, Melvin A | LI49 | Apprentice | Finish (limited hours)
Soto Serna, Cesar E | SO79 | Journeyman | Finish (limited)

## Master Document List
File Name | Relative Path | Directory | Extension | Size (KB) | Document Category | Cortex Schema
greenwood waste stacks.xls | greenwood waste stacks.xls | . | .xls | 50.5 | Other | Unclassified
greenwood h20 stacks.xls | greenwood h20 stacks.xls | . | .xls | 52.0 | Other | Unclassified
Chinn Greenwood P-tag list and front page detail.xlsx | Chinn Greenwood P-tag list and front page detail.xlsx | . | .xlsx | 31.2 | Other | Unclassified
Chinn Greenwood P-tag list and front page detail.xls | Chinn Greenwood P-tag list and front page detail.xls | . | .xls | 60.0 | Other | Unclassified
GREENWOOD WATTS.xls | PO Scheduled/GREENWOOD WATTS.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD SIOUX CHIEF QUOTE.xls | PO Scheduled/GREENWOOD SIOUX CHIEF QUOTE.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOODDRAINS L-1.xls | PO Scheduled/GREENWOODDRAINS L-1.xls | PO Scheduled | .xls | 38.0 | Purchase Order | Job Cost Report
GREENWOOD 5-7-13 45169.xls | PO Scheduled/GREENWOOD 5-7-13 45169.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD PEX MAINS.xls | PO Scheduled/GREENWOOD PEX MAINS.xls | PO Scheduled | .xls | 39.5 | Purchase Order | Job Cost Report
Greenwood lsp direct FEI 15553 ROB.xlsx | PO Scheduled/Greenwood lsp direct FEI 15553 ROB.xlsx | PO Scheduled | .xlsx | 18.2 | Purchase Order | Job Cost Report
GREENWOOD STALLS.xls | PO Scheduled/GREENWOOD STALLS.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD ZOELLER.xls | PO Scheduled/GREENWOOD ZOELLER.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
Greenwood GARAGE BASINS.xls | PO Scheduled/Greenwood GARAGE BASINS.xls | PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
Greenwood water service copper.xls | PO Scheduled/Greenwood water service copper.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-1 15626.xlsx | PO Scheduled/GREENWOOD TRIM L-1 15626.xlsx | PO Scheduled | .xlsx | 19.2 | Purchase Order | Job Cost Report
GREENWOOD RELIEF PAN DRAINS.xls | PO Scheduled/GREENWOOD RELIEF PAN DRAINS.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 45084 11-29-12.xls | PO Scheduled/GREENWOOD MISC 45084 11-29-12.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
Greenwood PROSET.xls | PO Scheduled/Greenwood PROSET.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 11-7-12.xls | PO Scheduled/GREENWOOD MISC 11-7-12.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD ADA KITCHEN SINKS 15674.xlsx | PO Scheduled/GREENWOOD ADA KITCHEN SINKS 15674.xlsx | PO Scheduled | .xlsx | 20.4 | Purchase Order | Job Cost Report
Greenwood UNIT PEX FEI.xls | PO Scheduled/Greenwood UNIT PEX FEI.xls | PO Scheduled | .xls | 36.5 | Purchase Order | Job Cost Report
GREENWOOD RI MATERIAL PVC.xls | PO Scheduled/GREENWOOD RI MATERIAL PVC.xls | PO Scheduled | .xls | 38.0 | Purchase Order | Job Cost Report
Greenwood lsp direct FEI 15553.xlsx | PO Scheduled/Greenwood lsp direct FEI 15553.xlsx | PO Scheduled | .xlsx | 18.1 | Purchase Order | Job Cost Report
GREENWOOD ADA COVERS 45180 6-12-13.xls | PO Scheduled/GREENWOOD ADA COVERS 45180 6-12-13.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC TRIM 15676.xls | PO Scheduled/GREENWOOD MISC TRIM 15676.xls | PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-3 lva faucets 15675.xlsx | PO Scheduled/GREENWOOD TRIM L-3 lva faucets 15675.xlsx | PO Scheduled | .xlsx | 17.9 | Purchase Order | Job Cost Report
GREENWOOD FAUCET BRETT.xls | PO Scheduled/GREENWOOD FAUCET BRETT.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
Greenwood MSI BOOSTER PUMP.xls | PO Scheduled/Greenwood MSI BOOSTER PUMP.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD MISC MATERIAL 10-31-12.xls | PO Scheduled/GREENWOOD MISC MATERIAL 10-31-12.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-2 15625.xlsx | PO Scheduled/GREENWOOD TRIM L-2 15625.xlsx | PO Scheduled | .xlsx | 19.2 | Purchase Order | Job Cost Report
Greenwood trench drain KELLER.xls | PO Scheduled/Greenwood trench drain KELLER.xls | PO Scheduled | .xls | 36.5 | Purchase Order | Job Cost Report
GREENWOOD 3-21-13 45139.xls | PO Scheduled/GREENWOOD 3-21-13 45139.xls | PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD SPECIALTY PRODUCTS ROB.xls | PO Scheduled/GREENWOOD SPECIALTY PRODUCTS ROB.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD 12-14-12 45092.xls | PO Scheduled/GREENWOOD 12-14-12 45092.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD GARAGE MATERIAL PVC.xls | PO Scheduled/GREENWOOD GARAGE MATERIAL PVC.xls | PO Scheduled | .xls | 38.5 | Purchase Order | Job Cost Report
GREENWOOD 5-1-13 45167.xls | PO Scheduled/GREENWOOD 5-1-13 45167.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-3 15624.xlsx | PO Scheduled/GREENWOOD TRIM L-3 15624.xlsx | PO Scheduled | .xlsx | 19.1 | Purchase Order | Job Cost Report
GREENWOOD PVC 10-8-12.xls | PO Scheduled/GREENWOOD PVC 10-8-12.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD 5-1-13 45166.xls | PO Scheduled/GREENWOOD 5-1-13 45166.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD SPECIALTY PRODUCTS.xls | PO Scheduled/GREENWOOD SPECIALTY PRODUCTS.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD STORM MATERIAL PVC.xls | PO Scheduled/GREENWOOD STORM MATERIAL PVC.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD ROOFDECK FAUCET 15715.xls | PO Scheduled/GREENWOOD ROOFDECK FAUCET 15715.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 10-25-12.xls | PO Scheduled/GREENWOOD MISC 10-25-12.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD 2-15-13 45118.xls | PO Scheduled/GREENWOOD 2-15-13 45118.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | PO Scheduled/GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD TRIM LW 15627.xlsx | PO Scheduled/GREENWOOD TRIM LW 15627.xlsx | PO Scheduled | .xlsx | 19.2 | Purchase Order | Job Cost Report
GREENWOOD CI MATERIAL 10-12-12.xls | PO Scheduled/GREENWOOD CI MATERIAL 10-12-12.xls | PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD STRUT 10-17-12.xls | PO Scheduled/GREENWOOD STRUT 10-17-12.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD MISC TRIM 15688.xls | PO Scheduled/GREENWOOD MISC TRIM 15688.xls | PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD RI VALVES.xls | PO Scheduled/GREENWOOD RI VALVES.xls | PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD GW.xls | PO Scheduled/GREENWOOD GW.xls | PO Scheduled | .xls | 38.5 | Purchase Order | Job Cost Report
GREENWOOD CI MATERIAL.xls | PO Scheduled/GREENWOOD CI MATERIAL.xls | PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD PVCGW8-27-12.xls | PO Scheduled/GREENWOOD PVCGW8-27-12.xls | PO Scheduled | .xls | 33.5 | Purchase Order | Job Cost Report
Natural and Built Environments Sedona schedule of values.xls | greenwood billing/Natural and Built Environments Sedona schedule of values.xls | greenwood billing | .xls | 63.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | greenwood billing/Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-3.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-3.doc | greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 8 - 3-20-13.xlsx | greenwood billing/Greenwood schedule of values- 8 - 3-20-13.xlsx | greenwood billing | .xlsx | 31.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-7.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-7.docx | greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | greenwood billing | .xlsx | 15.1 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 4 - 10-18-12.xls | greenwood billing/Greenwood schedule of values- 4 - 10-18-12.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 5 - 11-15-12.xls | greenwood billing/Greenwood schedule of values- 5 - 11-15-12.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 3 - 9-20-12.xls | greenwood billing/Greenwood schedule of values- 3 - 9-20-12.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 7 - 2-20-13.xlsx | greenwood billing/Greenwood schedule of values- 7 - 2-20-13.xlsx | greenwood billing | .xlsx | 31.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-2.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-2.doc | greenwood billing | .doc | 36.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | greenwood billing/Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | greenwood billing | .xlsx | 32.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | greenwood billing/Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 11 - 8-20-13.xlsx | greenwood billing/Greenwood schedule of values- 11 - 8-20-13.xlsx | greenwood billing | .xlsx | 32.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 10 - 5-20-13.xlsx | greenwood billing/Greenwood schedule of values- 10 - 5-20-13.xlsx | greenwood billing | .xlsx | 32.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
GREENWOOD AGGREGATE BILLING.xlsx | greenwood billing/GREENWOOD AGGREGATE BILLING.xlsx | greenwood billing | .xlsx | 14.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | greenwood billing/Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 2 - 8-20-12.xls | greenwood billing/Greenwood schedule of values- 2 - 8-20-12.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-10.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-10.docx | greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-5.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-5.doc | greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-6.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-6.docx | greenwood billing | .docx | 21.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | greenwood billing/Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | greenwood billing | .xls | 30.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments.doc | greenwood billing | .doc | 35.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | greenwood billing/Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Copy of Chinn Construction Greenwood schedule of values.xls | greenwood billing/Copy of Chinn Construction Greenwood schedule of values.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | greenwood billing/Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | greenwood billing | .xlsx | 31.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-11.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11.docx | greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-1.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-1.doc | greenwood billing | .doc | 35.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-8.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-8.docx | greenwood billing | .docx | 21.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-4.doc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-4.doc | greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | greenwood billing/Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | greenwood billing | .xlsx | 31.9 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | greenwood billing/Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | greenwood billing/Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 1 - 7-19-12.xls | greenwood billing/Greenwood schedule of values- 1 - 7-19-12.xls | greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-9.docx | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-9.docx | greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
JOB ORDER SUMMARY GREENWOOD.xlsx | 2009-Chinn, Greenwood/JOB ORDER SUMMARY GREENWOOD.xlsx | 2009-Chinn, Greenwood | .xlsx | 13.1 | Other | Unclassified
Greenwood OWP AS BUILT DRAWINGS.pdf | 2009-Chinn, Greenwood/Greenwood OWP AS BUILT DRAWINGS.pdf | 2009-Chinn, Greenwood | .pdf | 18994.8 | Plans/Drawings | Design Changes & Pre-CO
greenwood waste stacks.xls | 2009-Chinn, Greenwood/greenwood waste stacks.xls | 2009-Chinn, Greenwood | .xls | 50.5 | Other | Unclassified
greenwood plumbing permit.pdf | 2009-Chinn, Greenwood/greenwood plumbing permit.pdf | 2009-Chinn, Greenwood | .pdf | 246.5 | Permit | Project Admin Docs
greenwood h20 stacks.xls | 2009-Chinn, Greenwood/greenwood h20 stacks.xls | 2009-Chinn, Greenwood | .xls | 52.0 | Other | Unclassified
Chinn Greenwood P-tag list and front page detail.xlsx | 2009-Chinn, Greenwood/Chinn Greenwood P-tag list and front page detail.xlsx | 2009-Chinn, Greenwood | .xlsx | 31.2 | Other | Unclassified
Chinn Greenwood P-tag list and front page detail.xls | 2009-Chinn, Greenwood/Chinn Greenwood P-tag list and front page detail.xls | 2009-Chinn, Greenwood | .xls | 60.0 | Other | Unclassified
greenwood rpba permit.pdf | 2009-Chinn, Greenwood/greenwood rpba permit.pdf | 2009-Chinn, Greenwood | .pdf | 237.0 | Permit | Project Admin Docs
GREENWOOD WATTS.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD WATTS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD SIOUX CHIEF QUOTE.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD SIOUX CHIEF QUOTE.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOODDRAINS L-1.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOODDRAINS L-1.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 38.0 | Purchase Order | Job Cost Report
GREENWOOD 5-7-13 45169.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-7-13 45169.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD PEX MAINS.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PEX MAINS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 39.5 | Purchase Order | Job Cost Report
Greenwood lsp direct FEI 15553 ROB.xlsx | 2009-Chinn, Greenwood/PO Scheduled/Greenwood lsp direct FEI 15553 ROB.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 18.2 | Purchase Order | Job Cost Report
GREENWOOD STALLS.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD STALLS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD ZOELLER.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ZOELLER.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
Greenwood GARAGE BASINS.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood GARAGE BASINS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
Greenwood water service copper.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood water service copper.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-1 15626.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-1 15626.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 19.2 | Purchase Order | Job Cost Report
GREENWOOD RELIEF PAN DRAINS.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD RELIEF PAN DRAINS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 45084 11-29-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 45084 11-29-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
Greenwood PROSET.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood PROSET.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 11-7-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 11-7-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD ADA KITCHEN SINKS 15674.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ADA KITCHEN SINKS 15674.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 20.4 | Purchase Order | Job Cost Report
Greenwood UNIT PEX FEI.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood UNIT PEX FEI.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.5 | Purchase Order | Job Cost Report
GREENWOOD RI MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD RI MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 38.0 | Purchase Order | Job Cost Report
Greenwood lsp direct FEI 15553.xlsx | 2009-Chinn, Greenwood/PO Scheduled/Greenwood lsp direct FEI 15553.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 18.1 | Purchase Order | Job Cost Report
GREENWOOD ADA COVERS 45180 6-12-13.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ADA COVERS 45180 6-12-13.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC TRIM 15676.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC TRIM 15676.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-3 lva faucets 15675.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-3 lva faucets 15675.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 17.9 | Purchase Order | Job Cost Report
GREENWOOD FAUCET BRETT.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD FAUCET BRETT.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
Greenwood MSI BOOSTER PUMP.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood MSI BOOSTER PUMP.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD MISC MATERIAL 10-31-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC MATERIAL 10-31-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-2 15625.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-2 15625.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 19.2 | Purchase Order | Job Cost Report
Greenwood trench drain KELLER.xls | 2009-Chinn, Greenwood/PO Scheduled/Greenwood trench drain KELLER.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.5 | Purchase Order | Job Cost Report
GREENWOOD 3-21-13 45139.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 3-21-13 45139.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD SPECIALTY PRODUCTS ROB.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD SPECIALTY PRODUCTS ROB.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD 12-14-12 45092.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 12-14-12 45092.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD GARAGE MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD GARAGE MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 38.5 | Purchase Order | Job Cost Report
GREENWOOD 5-1-13 45167.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-1-13 45167.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD TRIM L-3 15624.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-3 15624.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 19.1 | Purchase Order | Job Cost Report
GREENWOOD PVC 10-8-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PVC 10-8-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD 5-1-13 45166.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-1-13 45166.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD SPECIALTY PRODUCTS.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD SPECIALTY PRODUCTS.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD STORM MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD STORM MATERIAL PVC.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD ROOFDECK FAUCET 15715.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ROOFDECK FAUCET 15715.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD MISC 10-25-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 10-25-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD 2-15-13 45118.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 2-15-13 45118.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD TRIM LW 15627.xlsx | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM LW 15627.xlsx | 2009-Chinn, Greenwood/PO Scheduled | .xlsx | 18.9 | Purchase Order | Job Cost Report
GREENWOOD CI MATERIAL 10-12-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD CI MATERIAL 10-12-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.5 | Purchase Order | Job Cost Report
GREENWOOD STRUT 10-17-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD STRUT 10-17-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD MISC TRIM 15688.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC TRIM 15688.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 35.0 | Purchase Order | Job Cost Report
GREENWOOD RI VALVES.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD RI VALVES.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 34.5 | Purchase Order | Job Cost Report
GREENWOOD GW.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD GW.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 38.5 | Purchase Order | Job Cost Report
GREENWOOD CI MATERIAL.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD CI MATERIAL.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 36.0 | Purchase Order | Job Cost Report
GREENWOOD PVCGW8-27-12.xls | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PVCGW8-27-12.xls | 2009-Chinn, Greenwood/PO Scheduled | .xls | 33.5 | Purchase Order | Job Cost Report
Greenwood OWP AS BUILT DRAWINGS.pdf | 2009-Chinn, Greenwood/GREENWOOD ASBUILTS/Greenwood OWP AS BUILT DRAWINGS.pdf | 2009-Chinn, Greenwood/GREENWOOD ASBUILTS | .pdf | 18994.8 | Plans/Drawings | Design Changes & Pre-CO
Tab 7 HB1, HB2 hosebibs.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 7 HB1, HB2 hosebibs.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 2625.8 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
tab 6 P13 amenity water heater.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/tab 6 P13 amenity water heater.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 306.2 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 3 shower valve parts.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 3 shower valve parts.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 276.6 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 5 P10 resident unit water heater.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 5 P10 resident unit water heater.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 53.7 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 3 P4, P5 shower valve.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 3 P4, P5 shower valve.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 512.3 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 9 storm pumps.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 9 storm pumps.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 763.9 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 2 P3, P12 lavatory faucet.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 2 P3, P12 lavatory faucet.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 396.0 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 1 P2, P11 toilets.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 1 P2, P11 toilets.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 869.7 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 4 P6 kitchen garbage disposal.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 4 P6 kitchen garbage disposal.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 1618.6 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
tab 10 BFP-1 backflow preventor.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/tab 10 BFP-1 backflow preventor.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 1358.5 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 8 BP booster pump package.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 8 BP booster pump package.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 372.9 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 3 P4, P5 shower valves.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 3 P4, P5 shower valves.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 1521.8 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
warranties.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/warranties.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 7323.1 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 1 P1 toilets.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 1 P1 toilets.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 547.6 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
x cleaning instructions.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/x cleaning instructions.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 1469.2 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Tab 4 P6 kitchen sink faucet.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 4 P6 kitchen sink faucet.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 690.8 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
z Periodic inspection list.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/z Periodic inspection list.pdf | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files | .pdf | 160.4 | Closeout/O&M | Project Admin Docs (Punch List/Closeout)
Natural and Built Environments Sedona schedule of values.xls | 2009-Chinn, Greenwood/greenwood billing/Natural and Built Environments Sedona schedule of values.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 63.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-3.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-3.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 8 - 3-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 8 - 3-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 31.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-7.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-7.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.1 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 4 - 10-18-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 4 - 10-18-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 5 - 11-15-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 5 - 11-15-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 3 - 9-20-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 3 - 9-20-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 7 - 2-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 7 - 2-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 31.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-2.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-2.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 36.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 32.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 11 - 8-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 11 - 8-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 32.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 10 - 5-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 10 - 5-20-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 32.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
GREENWOOD AGGREGATE BILLING.xlsx | 2009-Chinn, Greenwood/greenwood billing/GREENWOOD AGGREGATE BILLING.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 14.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 2 - 8-20-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 2 - 8-20-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-10.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-10.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-5.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-5.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-6.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-6.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | 2009-Chinn, Greenwood/greenwood billing/Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 30.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 35.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Copy of Chinn Construction Greenwood schedule of values.xls | 2009-Chinn, Greenwood/greenwood billing/Copy of Chinn Construction Greenwood schedule of values.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 31.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-11.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-1.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-1.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 35.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-8.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-8.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.7 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-4.doc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-4.doc | 2009-Chinn, Greenwood/greenwood billing | .doc | 37.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 31.9 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | 2009-Chinn, Greenwood/greenwood billing | .xlsx | 15.2 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 31.5 | Billing/Invoice | Project Admin Docs (Pay Apps)
Greenwood schedule of values- 1 - 7-19-12.xls | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 1 - 7-19-12.xls | 2009-Chinn, Greenwood/greenwood billing | .xls | 61.0 | Billing/Invoice | Project Admin Docs (Pay Apps)
Progress Payment Lien Release - Greenwood Apartments-9.docx | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-9.docx | 2009-Chinn, Greenwood/greenwood billing | .docx | 21.8 | Billing/Invoice | Project Admin Docs (Pay Apps)
WB-2 icemaker box with shock arrester.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/WB-2 icemaker box with shock arrester.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 503.7 | Submittal | Submittal
Kohler K3609 elongated toilet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K3609 elongated toilet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 68.1 | Submittal | Submittal
Zoeller storm pumps.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Zoeller storm pumps.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 3807.8 | Submittal | Submittal
Kohler K4774 elongated seat.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K4774 elongated seat.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 71.1 | Submittal | Submittal
Eemax SP4208 tankless heater.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Eemax SP4208 tankless heater.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 178.8 | Submittal | Submittal
Kohler K304-UX roughin valve.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K304-UX roughin valve.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 350.1 | Submittal | Submittal
P1 resident toilet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/P1 resident toilet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 60.7 | Submittal | Submittal
LSP overflow trim kit.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/LSP overflow trim kit.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 70.1 | Submittal | Submittal
Woodford 65 frostproof hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Woodford 65 frostproof hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 351.1 | Submittal | Submittal
Kohler K11742-E, 2.0 gpm shower head.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K11742-E, 2.0 gpm shower head.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 70.8 | Submittal | Submittal
backwater valve access.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/backwater valve access.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 147.6 | Submittal | Submittal
OW-1 Sand oil seperator.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/OW-1 Sand oil seperator.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 111.3 | Submittal | Submittal
LSP brass angle stops.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/LSP brass angle stops.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 146.3 | Submittal | Submittal
PVC backwater valve.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/PVC backwater valve.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 128.6 | Submittal | Submittal
Watts 957 reduced pressure backflow assembly.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Watts 957 reduced pressure backflow assembly.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 619.8 | Submittal | Submittal
Kohler K596 chrome kitchen faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K596 chrome kitchen faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 82.2 | Submittal | Submittal
FD-2 cast iron hub drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/FD-2 cast iron hub drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 254.6 | Submittal | Submittal
Woodford B24 Keyless hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Woodford B24 Keyless hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 187.3 | Submittal | Submittal
Kohler K2699-4 china lavatory.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K2699-4 china lavatory.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 59.8 | Submittal | Submittal
Kohler K15597-F office restroom lav faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K15597-F office restroom lav faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 63.6 | Submittal | Submittal
Woodford B65 Keyless hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Woodford B65 Keyless hosebib.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 346.7 | Submittal | Submittal
Dearborn plastic P-trap.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Dearborn plastic P-trap.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 62.1 | Submittal | Submittal
Kohler K4775 round front seat.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K4775 round front seat.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 71.1 | Submittal | Submittal
Moen 52710EP hand held shower.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Moen 52710EP hand held shower.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 337.2 | Submittal | Submittal
Kohler KT15601-4SE tub shower trim.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler KT15601-4SE tub shower trim.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 61.7 | Submittal | Submittal
Oatey aluminium water heater pan.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Oatey aluminium water heater pan.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 445.4 | Submittal | Submittal
AO Smith residential electric water heaters.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/AO Smith residential electric water heaters.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 480.2 | Submittal | Submittal
Kohler K15182-F chrome lav faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K15182-F chrome lav faucet.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 54.3 | Submittal | Submittal
TD-1 trench drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/TD-1 trench drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 1152.9 | Submittal | Submittal
LSP overflow kit.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/LSP overflow kit.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 67.4 | Submittal | Submittal
Elkay ELUHAD2115-5 ADA kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Elkay ELUHAD2115-5 ADA kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 175.0 | Submittal | Submittal
GD-1, SD-1 concrete garage floor drain with iron grate.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/GD-1, SD-1 concrete garage floor drain with iron grate.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 111.7 | Submittal | Submittal
Kohler K3348-4 single bowl self-rim kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K3348-4 single bowl self-rim kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 37.3 | Submittal | Submittal
P7 wash machine outlet box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/P7 wash machine outlet box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 730.3 | Submittal | Submittal
FD-1 cast iron floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/FD-1 cast iron floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 262.4 | Submittal | Submittal
PVC waste pipe spec.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/PVC waste pipe spec.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 18.7 | Submittal | Submittal
Elkay EGUH2115 kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Elkay EGUH2115 kitchen sink.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 541.5 | Submittal | Submittal
Kohler K2005 wall hung lav.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K2005 wall hung lav.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 58.2 | Submittal | Submittal
Proflo PFXT expansion tank.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Proflo PFXT expansion tank.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood | .pdf | 504.5 | Submittal | Submittal
P6 kitchen sink.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P6 kitchen sink.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1101.8 | Submittal | Submittal
CPVC pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/CPVC pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1496.3 | Submittal | Submittal
P13 leasing office water heater.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P13 leasing office water heater.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 740.5 | Submittal | Submittal
P7 dishwasher connection.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P7 dishwasher connection.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 615.7 | Submittal | Submittal
TD1 trench drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/TD1 trench drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1041.7 | Submittal | Submittal
BP booster pump package.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/BP booster pump package.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 372.9 | Submittal | Submittal
P1 toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P1 toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1403.4 | Submittal | Submittal
HD1 hub drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/HD1 hub drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 196.9 | Submittal | Submittal
HB2 hosebib.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/HB2 hosebib.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 391.6 | Submittal | Submittal
waste, vent and storm drain pipe.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/waste, vent and storm drain pipe.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 991.5 | Submittal | Submittal
BV backwater valve and access.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/BV backwater valve and access.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 351.8 | Submittal | Submittal
P5 ADA bathtub.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P5 ADA bathtub.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 2189.5 | Submittal | Submittal
OW1 oil water separator.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/OW1 oil water separator.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 335.4 | Submittal | Submittal
BFP1 reduced pressure backflow assembly.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/BFP1 reduced pressure backflow assembly.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1143.1 | Submittal | Submittal
Proset sleeve components.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/Proset sleeve components.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 980.8 | Submittal | Submittal
P12 leasing office lavatory.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P12 leasing office lavatory.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1713.7 | Submittal | Submittal
FD1 garage floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/FD1 garage floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 333.2 | Submittal | Submittal
P4 bathtub.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P4 bathtub.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 2383.2 | Submittal | Submittal
P3 lavatory.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P3 lavatory.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1342.9 | Submittal | Submittal
FD2 floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/FD2 floor drain.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 202.9 | Submittal | Submittal
P9 wash machine box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P9 wash machine box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 311.0 | Submittal | Submittal
P2 ADA toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P2 ADA toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1476.2 | Submittal | Submittal
P8 icemaker box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P8 icemaker box.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 266.7 | Submittal | Submittal
HB1 hosebib.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/HB1 hosebib.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 365.8 | Submittal | Submittal
P11 leasing office toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P11 leasing office toilet.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1494.2 | Submittal | Submittal
SP1 storm sump pump.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/SP1 storm sump pump.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 2446.6 | Submittal | Submittal
PEX pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/PEX pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 3061.4 | Submittal | Submittal
P10 water heater.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/P10 water heater.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 1105.4 | Submittal | Submittal
Alternate kitchen sink for ADA units.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/Alternate kitchen sink for ADA units.pdf | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 41.1 | Submittal | Submittal
pipe hangers and supports.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/pipe hangers and supports.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 2566.1 | Submittal | Submittal
Chinn Greenwood complete plumbing submittal.zip | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/Chinn Greenwood complete plumbing submittal.zip | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .zip | 31483.6 | Submittal | Submittal
FCO floor cleanout.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/FCO floor cleanout.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 134.5 | Submittal | Submittal
copper pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/copper pipe and fitting.PDF | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02 | .pdf | 2138.2 | Submittal | Submittal
Pages from Greenwood Apartments Construction set 2.pdf | 2009 Greenwood/Pages from Greenwood Apartments Construction set 2.pdf | 2009 Greenwood | .pdf | 173.0 | Plans/Drawings | Design Changes & Pre-CO
Greenwood Apartments Construction set.pdf | 2009 Greenwood/Greenwood Apartments Construction set.pdf | 2009 Greenwood | .pdf | 2461.7 | Plans/Drawings | Design Changes & Pre-CO
Thumbs.db | 2009 Greenwood/Thumbs.db | 2009 Greenwood | .db | 25.5 | Other | Unclassified
BPC Booster System Rev1-Model.pdf | 2009 Greenwood/BPC Booster System Rev1-Model.pdf | 2009 Greenwood | .pdf | 34.0 | Other | Unclassified
Greenwood Water Room.pdf | 2009 Greenwood/Greenwood Water Room.pdf | 2009 Greenwood | .pdf | 91.1 | Other | Unclassified
Pages from Greenwood Apartments Construction set 1.pdf | 2009 Greenwood/Pages from Greenwood Apartments Construction set 1.pdf | 2009 Greenwood | .pdf | 248.4 | Plans/Drawings | Design Changes & Pre-CO
Pages from Greenwood ASI-03 10-8-12.pdf | 2009 Greenwood/Pages from Greenwood ASI-03 10-8-12.pdf | 2009 Greenwood | .pdf | 448.7 | ASI/RFI | RFI / Design Changes & Pre-CO
greenwood booster pump.pdf | 2009 Greenwood/chinn greenwood/greenwood booster pump.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2752.9 | Other | Unclassified
C-204.pdf | 2009 Greenwood/chinn greenwood/C-204.pdf | 2009 Greenwood/chinn greenwood | .pdf | 564.1 | Other | Unclassified
Greenwood ASI-03 11 x 17.pdf | 2009 Greenwood/chinn greenwood/Greenwood ASI-03 11 x 17.pdf | 2009 Greenwood/chinn greenwood | .pdf | 4703.0 | ASI/RFI | RFI / Design Changes & Pre-CO
GRE Greenwood_ Arch and Struct.zip | 2009 Greenwood/chinn greenwood/GRE Greenwood_ Arch and Struct.zip | 2009 Greenwood/chinn greenwood | .zip | 5247.0 | Other | Unclassified
greenwood full size.pdf | 2009 Greenwood/chinn greenwood/greenwood full size.pdf | 2009 Greenwood/chinn greenwood | .pdf | 50377.0 | Other | Unclassified
greenwood irrigation.pdf | 2009 Greenwood/chinn greenwood/greenwood irrigation.pdf | 2009 Greenwood/chinn greenwood | .pdf | 11142.9 | Other | Unclassified
greenwood PLUMBING 7-23-12.pdf | 2009 Greenwood/chinn greenwood/greenwood PLUMBING 7-23-12.pdf | 2009 Greenwood/chinn greenwood | .pdf | 3690.1 | Other | Unclassified
GRENWOOD PLUMBING RUSHING.pdf | 2009 Greenwood/chinn greenwood/GRENWOOD PLUMBING RUSHING.pdf | 2009 Greenwood/chinn greenwood | .pdf | 25565.6 | Other | Unclassified
GreenwoodApts_Prelim_8-1-12.pdf | 2009 Greenwood/chinn greenwood/GreenwoodApts_Prelim_8-1-12.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2046.1 | Other | Unclassified
greenwood fire shop drawings.pdf | 2009 Greenwood/chinn greenwood/greenwood fire shop drawings.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2380.2 | Other | Unclassified
greenwood a101 full size.pdf | 2009 Greenwood/chinn greenwood/greenwood a101 full size.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2196.2 | Other | Unclassified
Greenwood ASI-03.pdf | 2009 Greenwood/chinn greenwood/Greenwood ASI-03.pdf | 2009 Greenwood/chinn greenwood | .pdf | 5428.5 | ASI/RFI | RFI / Design Changes & Pre-CO
Greenwood Apartments Construction set.pdf | 2009 Greenwood/chinn greenwood/Greenwood Apartments Construction set.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2461.7 | Plans/Drawings | Design Changes & Pre-CO
MCA RATING GREENWOOD.pdf | 2009 Greenwood/chinn greenwood/MCA RATING GREENWOOD.pdf | 2009 Greenwood/chinn greenwood | .pdf | 273.5 | Other | Unclassified
C-203.pdf | 2009 Greenwood/chinn greenwood/C-203.pdf | 2009 Greenwood/chinn greenwood | .pdf | 870.4 | Other | Unclassified
Copy of Chinn Greenwood Revised copy of P-tag list and front page detail.xls | 2009 Greenwood/chinn greenwood/Copy of Chinn Greenwood Revised copy of P-tag list and front page detail.xls | 2009 Greenwood/chinn greenwood | .xls | 61.0 | Other | Unclassified
greenwood a101 garage piping.pdf | 2009 Greenwood/chinn greenwood/greenwood a101 garage piping.pdf | 2009 Greenwood/chinn greenwood | .pdf | 1284.2 | Other | Unclassified
Greenwood Apartments added drains.pdf | 2009 Greenwood/chinn greenwood/Greenwood Apartments added drains.pdf | 2009 Greenwood/chinn greenwood | .pdf | 850.2 | Other | Unclassified
MSI Job Setup Sheet Greenwood.pdf | 2009 Greenwood/chinn greenwood/MSI Job Setup Sheet Greenwood.pdf | 2009 Greenwood/chinn greenwood | .pdf | 46.8 | Other | Unclassified
greenwood a102 PLUMBING.pdf | 2009 Greenwood/chinn greenwood/greenwood a102 PLUMBING.pdf | 2009 Greenwood/chinn greenwood | .pdf | 1221.0 | Other | Unclassified
greenwood 2603cth.pdf | 2009 Greenwood/chinn greenwood/greenwood 2603cth.pdf | 2009 Greenwood/chinn greenwood | .pdf | 642.8 | Other | Unclassified
Pages from Greenwood Apartments Construction set.pdf | 2009 Greenwood/chinn greenwood/Pages from Greenwood Apartments Construction set.pdf | 2009 Greenwood/chinn greenwood | .pdf | 248.4 | Plans/Drawings | Design Changes & Pre-CO
greenwood a101ground work.pdf | 2009 Greenwood/chinn greenwood/greenwood a101ground work.pdf | 2009 Greenwood/chinn greenwood | .pdf | 1185.9 | Other | Unclassified
Greenwood ASI-03 10-8-12.pdf | 2009 Greenwood/chinn greenwood/Greenwood ASI-03 10-8-12.pdf | 2009 Greenwood/chinn greenwood | .pdf | 4630.1 | ASI/RFI | RFI / Design Changes & Pre-CO
greenwood asi 1.pdf | 2009 Greenwood/chinn greenwood/greenwood asi 1.pdf | 2009 Greenwood/chinn greenwood | .pdf | 1395.7 | ASI/RFI | RFI / Design Changes & Pre-CO
greenwood s2.0 full size.pdf | 2009 Greenwood/chinn greenwood/greenwood s2.0 full size.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2697.5 | Other | Unclassified
greenwood a102 full size.pdf | 2009 Greenwood/chinn greenwood/greenwood a102 full size.pdf | 2009 Greenwood/chinn greenwood | .pdf | 2182.8 | Other | Unclassified
greenwood storm pumps.pdf | 2009 Greenwood/chinn greenwood/greenwood storm pumps.pdf | 2009 Greenwood/chinn greenwood | .pdf | 7238.2 | Other | Unclassified

## Duplicates
Hash | File Path | Group Size
fee0a28cb7ce | greenwood h20 stacks.xls | 2
fee0a28cb7ce | 2009-Chinn, Greenwood/greenwood h20 stacks.xls | 2
4732e2d9e07a | Chinn Greenwood P-tag list and front page detail.xlsx | 2
4732e2d9e07a | 2009-Chinn, Greenwood/Chinn Greenwood P-tag list and front page detail.xlsx | 2
976f27f28193 | Chinn Greenwood P-tag list and front page detail.xls | 2
976f27f28193 | 2009-Chinn, Greenwood/Chinn Greenwood P-tag list and front page detail.xls | 2
01d598ce5498 | PO Scheduled/GREENWOODDRAINS L-1.xls | 2
01d598ce5498 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOODDRAINS L-1.xls | 2
c9ecd1d6680b | PO Scheduled/GREENWOOD 5-7-13 45169.xls | 2
c9ecd1d6680b | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-7-13 45169.xls | 2
697582730905 | PO Scheduled/GREENWOOD PEX MAINS.xls | 2
697582730905 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PEX MAINS.xls | 2
09daaab5826f | PO Scheduled/Greenwood lsp direct FEI 15553 ROB.xlsx | 2
09daaab5826f | 2009-Chinn, Greenwood/PO Scheduled/Greenwood lsp direct FEI 15553 ROB.xlsx | 2
17a04f4e47ba | PO Scheduled/Greenwood water service copper.xls | 2
17a04f4e47ba | 2009-Chinn, Greenwood/PO Scheduled/Greenwood water service copper.xls | 2
566d9b321c02 | PO Scheduled/GREENWOOD TRIM L-1 15626.xlsx | 2
566d9b321c02 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-1 15626.xlsx | 2
073a5bb9297a | PO Scheduled/GREENWOOD MISC 45084 11-29-12.xls | 2
073a5bb9297a | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 45084 11-29-12.xls | 2
dc70216fdee2 | PO Scheduled/Greenwood PROSET.xls | 2
dc70216fdee2 | 2009-Chinn, Greenwood/PO Scheduled/Greenwood PROSET.xls | 2
ca6f44073eed | PO Scheduled/GREENWOOD MISC 11-7-12.xls | 2
ca6f44073eed | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 11-7-12.xls | 2
90f2e45dcade | PO Scheduled/GREENWOOD ADA KITCHEN SINKS 15674.xlsx | 2
90f2e45dcade | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ADA KITCHEN SINKS 15674.xlsx | 2
54598e4c51a4 | PO Scheduled/Greenwood UNIT PEX FEI.xls | 2
54598e4c51a4 | 2009-Chinn, Greenwood/PO Scheduled/Greenwood UNIT PEX FEI.xls | 2
34932c3c2b3b | PO Scheduled/GREENWOOD RI MATERIAL PVC.xls | 2
34932c3c2b3b | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD RI MATERIAL PVC.xls | 2
0eddd334635a | PO Scheduled/Greenwood lsp direct FEI 15553.xlsx | 2
0eddd334635a | 2009-Chinn, Greenwood/PO Scheduled/Greenwood lsp direct FEI 15553.xlsx | 2
891f849dd590 | PO Scheduled/GREENWOOD ADA COVERS 45180 6-12-13.xls | 2
891f849dd590 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ADA COVERS 45180 6-12-13.xls | 2
92f40e9f7a15 | PO Scheduled/GREENWOOD MISC TRIM 15676.xls | 2
92f40e9f7a15 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC TRIM 15676.xls | 2
4b4e680a57c5 | PO Scheduled/GREENWOOD TRIM L-3 lva faucets 15675.xlsx | 2
4b4e680a57c5 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-3 lva faucets 15675.xlsx | 2
307ec3093038 | PO Scheduled/GREENWOOD FAUCET BRETT.xls | 2
307ec3093038 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD FAUCET BRETT.xls | 2
aeecafa90fc3 | PO Scheduled/GREENWOOD MISC MATERIAL 10-31-12.xls | 2
aeecafa90fc3 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC MATERIAL 10-31-12.xls | 2
9ca8fc6d03a1 | PO Scheduled/GREENWOOD TRIM L-2 15625.xlsx | 2
9ca8fc6d03a1 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-2 15625.xlsx | 2
3cddf3e93c39 | PO Scheduled/GREENWOOD SPECIALTY PRODUCTS ROB.xls | 2
3cddf3e93c39 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD SPECIALTY PRODUCTS ROB.xls | 2
f7a6446d4927 | PO Scheduled/GREENWOOD 12-14-12 45092.xls | 2
f7a6446d4927 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 12-14-12 45092.xls | 2
035ec5adcc38 | PO Scheduled/GREENWOOD GARAGE MATERIAL PVC.xls | 2
035ec5adcc38 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD GARAGE MATERIAL PVC.xls | 2
9ea760b59af8 | PO Scheduled/GREENWOOD 5-1-13 45167.xls | 2
9ea760b59af8 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-1-13 45167.xls | 2
2e9192302605 | PO Scheduled/GREENWOOD TRIM L-3 15624.xlsx | 2
2e9192302605 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD TRIM L-3 15624.xlsx | 2
143b1619d496 | PO Scheduled/GREENWOOD PVC 10-8-12.xls | 2
143b1619d496 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PVC 10-8-12.xls | 2
0303ed468933 | PO Scheduled/GREENWOOD 5-1-13 45166.xls | 2
0303ed468933 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD 5-1-13 45166.xls | 2
d493b31d2312 | PO Scheduled/GREENWOOD SPECIALTY PRODUCTS.xls | 2
d493b31d2312 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD SPECIALTY PRODUCTS.xls | 2
6a20b0fa18a8 | PO Scheduled/GREENWOOD STORM MATERIAL PVC.xls | 2
6a20b0fa18a8 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD STORM MATERIAL PVC.xls | 2
377971ce6148 | PO Scheduled/GREENWOOD ROOFDECK FAUCET 15715.xls | 2
377971ce6148 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD ROOFDECK FAUCET 15715.xls | 2
2993775dc0df | PO Scheduled/GREENWOOD MISC 10-25-12.xls | 2
2993775dc0df | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD MISC 10-25-12.xls | 2
a7fef111d290 | PO Scheduled/GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | 2
a7fef111d290 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD GARAGE MATERIAL PVC 10-15-12.xls | 2
43d0f43870c8 | PO Scheduled/GREENWOOD RI VALVES.xls | 2
43d0f43870c8 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD RI VALVES.xls | 2
7629c3b96e60 | PO Scheduled/GREENWOOD PVCGW8-27-12.xls | 2
7629c3b96e60 | 2009-Chinn, Greenwood/PO Scheduled/GREENWOOD PVCGW8-27-12.xls | 2
704b9ed4bea8 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | 2
704b9ed4bea8 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 5 -11-15-12.xls | 2
6ca4a68d78dc | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-3.doc | 2
6ca4a68d78dc | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-3.doc | 2
2d6d1389d38a | greenwood billing/Greenwood schedule of values- 8 - 3-20-13.xlsx | 2
2d6d1389d38a | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 8 - 3-20-13.xlsx | 2
d7e57e50bf73 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-7.docx | 2
d7e57e50bf73 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-7.docx | 2
9075e20d923f | greenwood billing/Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | 2
9075e20d923f | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 10 -5-16-13.xlsx | 2
a4021592b779 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | 2
a4021592b779 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13.xlsx | 2
f5178b96be16 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | 2
f5178b96be16 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 7 -2-19-13.xlsx | 2
12ee7d92e05d | greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | 2
12ee7d92e05d | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 11 -8-13-13 with Mike D revision Aug 19 2013.xlsx | 2
76cf2659534e | greenwood billing/Greenwood schedule of values- 4 - 10-18-12.xls | 2
76cf2659534e | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 4 - 10-18-12.xls | 2
ad8f0f15546c | greenwood billing/Greenwood schedule of values- 5 - 11-15-12.xls | 2
ad8f0f15546c | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 5 - 11-15-12.xls | 2
4460dfb4b303 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | 2
4460dfb4b303 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 6 -12-20-12.xlsx | 2
5c916f15fc25 | greenwood billing/Greenwood schedule of values- 3 - 9-20-12.xls | 2
5c916f15fc25 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 3 - 9-20-12.xls | 2
bb537b631d86 | greenwood billing/Greenwood schedule of values- 7 - 2-20-13.xlsx | 2
bb537b631d86 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 7 - 2-20-13.xlsx | 2
9476b1040553 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-2.doc | 2
9476b1040553 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-2.doc | 2
16ae8f79f326 | greenwood billing/Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | 2
16ae8f79f326 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 11 - 8-20-13 revised.xlsx | 2
102e4b387632 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | 2
102e4b387632 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 1 - 7-19-12.xls | 2
a86ca1355018 | greenwood billing/Greenwood schedule of values- 11 - 8-20-13.xlsx | 2
a86ca1355018 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 11 - 8-20-13.xlsx | 2
47741c0664f4 | greenwood billing/Greenwood schedule of values- 10 - 5-20-13.xlsx | 2
47741c0664f4 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 10 - 5-20-13.xlsx | 2
2ac52903e096 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | 2
2ac52903e096 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11 revised.docx | 2
374601a2e706 | greenwood billing/GREENWOOD AGGREGATE BILLING.xlsx | 2
374601a2e706 | 2009-Chinn, Greenwood/greenwood billing/GREENWOOD AGGREGATE BILLING.xlsx | 2
bcdf564eb2c5 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | 2
bcdf564eb2c5 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 9 -4-18-13.xlsx | 2
c03df33f7370 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | 2
c03df33f7370 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 4 -10-18-12.xls | 2
9d55be481ab8 | greenwood billing/Greenwood schedule of values- 2 - 8-20-12.xls | 2
9d55be481ab8 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 2 - 8-20-12.xls | 2
9a16bed9e015 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-10.docx | 2
9a16bed9e015 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-10.docx | 2
9a1639c8eade | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-5.doc | 2
9a1639c8eade | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-5.doc | 2
7a06d77df465 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-6.docx | 2
7a06d77df465 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-6.docx | 2
614ebcbdbfa0 | greenwood billing/Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | 2
614ebcbdbfa0 | 2009-Chinn, Greenwood/greenwood billing/Copy of Greenwood Apt - Subcontractor Monthly Billing Summary Form.xls | 2
415691251e34 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments.doc | 2
415691251e34 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments.doc | 2
a17b62c4224d | greenwood billing/Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | 2
a17b62c4224d | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 3 - 9-20-12.xls | 2
553c9a4182c7 | greenwood billing/Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | 2
553c9a4182c7 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 6 - 12-20-12 co 1.xlsx | 2
8d48557c8061 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11.docx | 2
8d48557c8061 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-11.docx | 2
48e7788412a1 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-1.doc | 2
48e7788412a1 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-1.doc | 2
3d91cd3054b1 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-8.docx | 2
3d91cd3054b1 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-8.docx | 2
37eee048f007 | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-4.doc | 2
37eee048f007 | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-4.doc | 2
53034afc5045 | greenwood billing/Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | 2
53034afc5045 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 9 - 4-20-13 co4.xlsx | 2
d2e22d5aba35 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | 2
d2e22d5aba35 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 8 -3-19-13.xlsx | 2
e5e4c2182b21 | greenwood billing/Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | 2
e5e4c2182b21 | 2009-Chinn, Greenwood/greenwood billing/Greenwood Apt - Monthly Billing Summary - 2 - 8-20-12.xls | 2
646320752341 | greenwood billing/Greenwood schedule of values- 1 - 7-19-12.xls | 2
646320752341 | 2009-Chinn, Greenwood/greenwood billing/Greenwood schedule of values- 1 - 7-19-12.xls | 2
2b26539167fb | greenwood billing/Progress Payment Lien Release - Greenwood Apartments-9.docx | 2
2b26539167fb | 2009-Chinn, Greenwood/greenwood billing/Progress Payment Lien Release - Greenwood Apartments-9.docx | 2
b17ff8382d1f | 2009-Chinn, Greenwood/Greenwood OWP AS BUILT DRAWINGS.pdf | 2
b17ff8382d1f | 2009-Chinn, Greenwood/GREENWOOD ASBUILTS/Greenwood OWP AS BUILT DRAWINGS.pdf | 2
723f02785b46 | 2009-Chinn, Greenwood/Closeout Documents/Chinn O and M files/Tab 8 BP booster pump package.pdf | 2
723f02785b46 | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood complete submittal package/2012-08-02/BP booster pump package.pdf | 2
14e317151bba | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K4774 elongated seat.pdf | 2
14e317151bba | 2009-Chinn, Greenwood/Submittals/Chinn Greenwood/Kohler K4775 round front seat.pdf | 2
09f9f3914f8c | 2009 Greenwood/Greenwood Apartments Construction set.pdf | 2
09f9f3914f8c | 2009 Greenwood/chinn greenwood/Greenwood Apartments Construction set.pdf | 2
SUMMARY
79 exact duplicate groups ¦ 158 total duplicate files (25% of 317)
Root cause: parallel directory structures (files at both nested and root levels)
Recommendation: consolidate to single canonical directory, eliminate duplicates

## Relational Map
DOCUMENT RELATIONSHIP MAP
Source Document | Related Document | Relationship | Link Field | Project Example | Cortex Schema
Purchase Orders (.xls) | Invoices (billing folders) | PO funds invoice payment | PO Number, Vendor | PO 45092 → /31-Roughin invoices | Job Cost ↔ Project Admin
Purchase Orders (.xls) | Submittals (.pdf) | PO procures submitted material | Product Code | GREENWOOD RI MATERIAL PVC → PVC spec.pdf | Job Cost ↔ Submittal
Submittals (.pdf) | Plans (.pdf) | Submittal fulfills plan spec | Fixture Tag (P1-P13) | P7 wash machine → Plans plumbing sheet | Submittal ↔ Design Changes
Schedule of Values (.xls) | Invoices (billing) | SOV tracks billing progress | Phase/Line Item | SOV Roughin line → /31-Roughin invoices | Project Admin (internal)
Monthly Billing (.xls) | Schedule of Values (.xls) | MBS summarizes SOV progress | Period, Amount | Jul 2012 billing → SOV 7/19/12 | Project Admin (internal)
As-Built Drawings (.pdf) | Plans (.pdf) | As-builts update original plans | Sheet Number | OWP AS BUILT → Construction set P-sheets | Design Changes
ASI Documents (.pdf) | Plans (.pdf) | ASI modifies original design | ASI Number | Greenwood ASI-03 → Construction set | Design Changes & Pre-CO
Warranty Docs (.pdf) | Submittals (.pdf) | Warranty covers submitted equipment | Equipment Model | warranties.pdf → AO Smith submittal | Project Admin ↔ Submittal
P-Tag List (.xls) | Submittals (.pdf) | P-tags index all submitted fixtures | Fixture Tag | P-tag → P1 toilet, P7 wash machine | Submittal (master index)
Job Detail Report (.pdf) | All financial documents | Master financial ledger | Cost Code, Date | JDR code 220 → Roughin Material invoices | Job Cost Report (master)
Lien Releases (.docx) | Monthly Billing (.xls) | Release accompanies billing | Period, Amount | Lien release → Monthly billing | Project Admin
Vendor Invoices (in JDR) | Purchase Orders (.xls) | Invoice fulfills PO | Vendor, PO# | Ferguson Inv 2462727 → PO 45092 | Job Cost ↔ Submittal

## Missing Documents
KEY MISSING DOCUMENTS
Document Type | Cortex Schema | Impact | Use Cases Blocked | Priority
Signed Contract / Subcontract | Contract Clause | Cannot assess risk, LD clauses, scope | UC4, UC6, UC9 | CRITICAL
Change Orders (executed COs) | Change Order | No CO recovery or approval rate analysis | UC1, UC3, UC4, UC8 | CRITICAL
RFI Log / RFI Documents | RFI | No design issue tracking or root cause | UC21, UC23, UC24 | CRITICAL
Daily Field Reports | Daily Report | No contemporaneous delay documentation | UC17, UC24 | HIGH
Production/Crew Activity Logs | Production Activity | No labor productivity benchmarking | UC16-UC20 | HIGH
Estimate/Bid Workup | Estimate | No bid accuracy or sweet spot analysis | UC11-UC15 | HIGH
Meeting Minutes | Project Admin | No action item or decision tracking | UC10, UC22 | MEDIUM
Formal Correspondence | Project Admin | No contractual notice tracking | UC4, UC26 | MEDIUM
Punch List | Project Admin | No closeout quality metrics | UC22, UC30 | MEDIUM
Sub Bid Tabulations | Sub Bid Analysis | No buyout intelligence | UC12, UC30 | MEDIUM
Safety/Inspection Reports | Safety & Inspection | No safety pattern analysis | UC9 | LOW
GC-Approved Pay App Copies | Project Admin | Cannot verify payment receipt timing | UC2, UC7 | HIGH

## Key Insights
KEY INSIGHTS
# | Insight | Evidence | Recommendation
1 | STRONG PROFITABILITY (27% margin): This project generated $106K net profit on $394K revenue — well above the 15-20% industry average for plumbing subcontractors. | Revenue $394,208 vs Expenses $287,899. Profit $106,309. Budget was ~$97K profit, so actual beat budget by $9.3K. | Benchmark this margin for future similar projects. Use as Cortex reference for UC27 (True Profitability).
2 | MATERIAL BUYOUT SAVED THE PROJECT: Material came in $45K (23%) under budget, which more than offset a $12K (17%) labor overrun. Procurement discipline drove profitability. | Material budget $196,250 → Actual $151,064 (saved $45,186). Labor budget $72,320 → Actual $84,698 (over by $12,378). Net savings = $32,808. | Track material buyout savings per Cortex Sub Bid schema. This is a repeatable competitive advantage if systematic.
3 | ROUGHIN PHASE WAS THE BOTTLENECK: Roughin consumed 56% of all labor hours (2,311 of 4,116) and was 34% over budget — the single largest cost overrun on the project. | Code 120 Roughin: Budget $34,500, Actual $46,114. 2,311 hours at $19.96/hr. Peak crew of 12 during Oct 2012 (40hr/week for 10+ workers). | Roughin estimating needs recalibration for multi-family. Consider breaking roughin into sub-phases for better tracking.
4 | FINISH MATERIAL IS 72% OF ALL MATERIAL COST: Code 230 (Finish Material) at $110K represents the bulk of procurement, dominated by Ferguson Enterprises invoices. | Code 230: $109,976 of $151,064 total material (72.8%). Key invoices: $15,861 (Ferguson), $16,250 (Mechanical Sales booster pump), $9,864 (Ferguson). | Negotiate volume pricing with Ferguson. The booster pump ($16,250 from Mechanical Sales) was a single major line item worth pre-negotiating.
5 | GC IDENTIFIED AS CHINN CONSTRUCTION: The AR entries reveal Chinn Construction, LLC as the GC, with 12 invoices and 5% retainage retention — $19,710 still outstanding. | Code 999 (Sales): All AR entries to 'Chinn Construction, LLC $Greenwood'. Retainage column totals $19,710.40. Invoice range 036335-036418. | Pursue retainage release if not already collected. Build Chinn Construction into Cortex GC intelligence (UC6-UC10) for future projects.
6 | ZERO CHANGE ORDER DOCUMENTATION despite T&M work existing: Invoice folder 38-T&M exists and Code 150 shows warranty labor, yet no COs are filed. | T&M folder exists in file structure. Warranty labor = $138.50 (4 hours). No CO, PCO, or COR documents anywhere in 317 files. | If COs existed but weren't filed, this is a documentation gap. If extra work was done without COs, this is potential unbilled revenue (UC1).
7 | EFFECTIVE LABOR RATE OF $20.58/HR: Across 4,116 hours and 22 workers, the blended rate is $20.58/hr. With burden ($34K) and tax ($6.5K), fully-loaded rate is ~$30.55/hr. | Direct labor $84,698 / 4,116 hours = $20.58. Add burden $34,412 + tax $6,479 = total loaded cost $125,589 / 4,116 = $30.51/hr. | Benchmark against current rates. If billing rates to GC were higher, the labor markup is a key profit driver.
8 | DOCUMENT ORGANIZATION IS POOR: 25% of files are exact duplicates across parallel directories, and files lack consistent naming or version control. | 79 duplicate groups, 158 files. PO Scheduled/ and greenwood billing/ exist at two directory levels. Multiple versions of SOV and billing summaries. | Implement Cortex document intake workflow. Deduplicate immediately. Establish canonical folder structure.
9 | COMPREHENSIVE SUBMITTAL PACKAGE: 72 submittal documents covering every plumbing fixture (P1-P13), all pipe specs, and specialty items is the strongest documentation category. | Complete P-tag list, individual and compiled submittal packages, ADA-specific submittals, all major manufacturers (Kohler, Watts, AO Smith, Armstrong). | Use as Cortex Submittal schema baseline. Highest coverage category at 56% of schema fields.
10 | PROJECT TIMELINE EFFICIENT: 13 months from permit to final billing with clear phase sequencing and no evidence of major delays. | Permit Jul 2012 → Underground Jul-Aug → Roughin Aug-Dec → Trim Jan-Jun 2013 → Warranty Oct 2013. Sequential with appropriate overlaps. | Use as benchmark timeline. The fact that roughin went 34% over budget in cost but stayed on schedule suggests it was a scope issue, not inefficiency.

## Not Asking
QUESTIONS WE ARE NOT ASKING (BUT SHOULD BE)
# | Question | Why It Matters | Cortex Use Case
1 | Were there change orders on this project, and if so, were they all billed? | Zero CO documentation for 13 months is abnormal. T&M folder exists, implying extra work. Potential unbilled revenue. | UC1: Unbilled CO Recovery
2 | What was the original bid/estimate and how did it compare to final cost? | No estimate workup in files. JDR shows budgets but not the bid submitted to Chinn Construction. | UC11-15: Estimating Intelligence
3 | Has the $19,710 retainage been released? | 5% retainage on $394K revenue. If held 10+ years, this is cash sitting on the table. | UC2: Retention Float Acceleration
4 | What was the crew productivity rate per unit (per apartment)? | We have total hours (4,116) but not unit count. Cannot benchmark $/unit or hours/unit for future estimates. | UC16: Foreman Productivity Gap
5 | Were payments from Chinn Construction received on time? | Only sub-side billing exists. No payment receipt tracking. | UC7: GC Payment Velocity
6 | Were there any back-charges from the GC? | No back-charge docs, no punch list, no deficiency notices. | UC4: Back-Charge Defense
7 | Why was Roughin 34% over budget? Scope change or estimating error? | $11,614 overrun is the largest variance. Root cause matters for future estimating accuracy. | UC13: Labor Hour Variance
8 | How does this project compare to other OWP multi-family projects? | Single project file — no portfolio benchmarking possible. | UC29: Project Type Profitability
9 | What submittals were rejected or required resubmission? | 72 spec sheets but zero transmittal letters or approval stamps. | UC23: Coordination Rework
10 | What was the safety record? | Zero safety documentation in 317 files. | Safety Schema
11 | What lessons were documented for future estimating? | No post-mortem or closeout feedback loop. | Estimate (Post-Completion)
12 | How many projects does OWP do per year with Chinn Construction? | Determines GC relationship value and risk concentration. | UC9: GC Risk Concentration

## Schema Coverage
CORTEX SCHEMA COVERAGE ANALYSIS
Project 2009 — Chinn Greenwood Ave Apartments
Schema | Total Fields | Fields Coverable | Coverage % | Files Present | Key Gaps | UCs Impacted
1. Change Order | 18 | 0 | 0% | None | No CO documents | UC1,3,4,8 BLOCKED
2. RFI | 23 | 0 | 0% | None | No RFI log | UC21,23,24 BLOCKED
3. Contract Clause | 14 | 0 | 0% | None | No signed contract | UC4,6,9 BLOCKED
4. Design Changes | 41 | 5 | 12% | ASI-03, As-builts | Only 1 ASI, no CCD/PR | UC21 PARTIAL
5. Estimate | 33 | 0 | 0% | None | No bid workup | UC11-15 BLOCKED
6. Sub Bid Analysis | 29 | 3 | 10% | Vendor quotes (limited) | No bid tabs | UC12,30 BLOCKED
7. Submittal | 18 | 10 | 56% | 72 spec sheets, P-tags | No transmittals/approvals | UC23 PARTIAL
8. Daily Report | 12 | 0 | 0% | None | No daily reports | UC17,24 BLOCKED
9. Production Activity | 37 | 0 | 0% | None | No crew logs | UC16-20 BLOCKED
10. Job Cost Report | 37 | 20 | 54% | JDR (49pg), 98 POs, invoices | No budget-vs-actual detail | UC11,27 PARTIAL
11. Safety & Inspection | 23 | 0 | 0% | None | No safety docs | UC9 PARTIAL
12. Project Admin | 32 | 18 | 56% | 82 billing, SOV, permits, liens | No minutes/correspondence/punch | UC2,7,26 PARTIAL
13. Cross-Doc Relations | 27 | 8 | 30% | PO→Invoice, Sub→P-tag linkable | Most links broken by missing schemas | Compound UCs DEGRADED
SUMMARY
Total Cortex Fields: 344 | Fields Coverable: 64 | Overall Coverage: 18.6%
Schemas >0%: 6 of 13 | Schemas at 0%: 7 of 13
UCs Fully Blocked: 18 of 30 | UCs Partial: 8 of 30 | UCs Fully Available: 0 of 30