## Inputs
Inputs — Canonical Job Data (4-Way)
All values sourced from each job's JCR Summary workbook. Blue = hardcoded input.
Metric | Job #2009 | Job #2010 | Job #2011 | Job #2012 | Source / Notes
— PROFILE —
Job Name | Chinn Greenwood Apts | Chinn Old Town Mixed Use | Chinn Barrett Park | Exxel 8th Ave
General Contractor | Chinn Construction, LLC | Chinn Construction, LLC | Chinn Construction, LLC | Exxel Pacific, Inc.
Location | Seattle, WA | Seattle, WA | Seattle, WA | Seattle, WA
Duration (months) | 16 | 24 | 17 | 17 | 2009: Jul 2012–Oct 2013
Unit Count | 168 | 165 | 117 | 163 | 2009: kitchen sink count
Total Fixtures | 812 | 803 | 590 | 816 | All in-unit plumbing fixtures
— FINANCIAL —
Original Contract | 384900 | 1469800 | 813050 | 1394655
Final Contract / Revenue | 394208 | 1386419 | 869824 | 1391455 | Post change orders
Change Orders | 9308 | -83381 | 56774 | 0 | 2009: small additive
Net Profit | 106309 | 751270 | 332960 | 533274
Direct Cost | 287899 | 635149 | 536863 | 858181 | Labor + Material + OH + Burden
Retainage | 19710 | 69321 | 43491 | 69573 | 5% held by GC
— COST MIX —
Labor Cost | 84698 | 202988 | 142883 | 291323 | Sum of labor codes from JCR
Material Cost | 151064 | 283474 | 295006 | 390751 | Sum of material codes
Overhead Cost | 11246 | 45271 | 26210 | 27519 | Sum of OH codes
Burden Cost | 40891 | 103414 | 72765 | 148589 | 995 Burden + 998 Taxes
— LABOR —
Total Labor Hours | 4116 | 10260 | 6944 | 14607
Total Workers | 23 | 22 | 31 | 28 | Unique payroll IDs
Blended Gross Wage ($/hr) | 20.58 | 19.78 | 20.58 | 19.94 | Labor $ / hours
Fully-Loaded Wage ($/hr) | 30.51 | 29.86 | 31.08 | 30.12 | (Labor+Burden) / hours
— MATERIAL —
Total PO Committed | 154025 | 213756 | 124908 | 0 | 2012 tracks via AP only
Total POs | 49 | 24 | 26 | 0
Material Vendors | 13 | 18 | 14 | 17 | Distinct AP vendors
Sources: OWP_2009_JCR_Summary.xlsx, OWP_2010_JCR_Summary.xlsx, OWP_2011_JCR_Summary.xlsx, OWP_2012_JCR_Summary_Notion.xlsx — all reconcile exactly to their JCR PDFs.

## Comparison
4-Way Benchmark — Jobs #2009 / #2010 / #2011 / #2012
Chinn Greenwood (168u, 16mo) • Chinn Old Town (165u, 24mo) • Chinn Barrett (117u, 17mo) • Exxel 8th Ave (163u, 17mo) — all Seattle multifamily/mixed-use
Metric | 2009 Greenwood | 2010 Old Town | 2011 Barrett | 2012 Exxel | Best | Range %
A. PROJECT SCALE
Unit Count | 168 | 165 | 117 | 163 | 2009 | 33.28%
Total Fixtures | 812 | 803 | 590 | 816 | 2012 | 29.92%
Duration (months) | 16 | 24 | 17 | 17 | 2009 | 43.24%
Fixtures / Unit | 4.8333 | 4.8667 | 5.0427 | 5.0061 | 2011 | 4.241%
B. TOP-LINE FINANCIAL
Revenue (Final Contract) | 394208 | 1386419 | 869824 | 1391455 | 2012 | 98.69%
Net Profit | 106309 | 751270 | 332960 | 533274 | 2010 | 149.7%
Direct Cost | 287899 | 635149 | 536863 | 858181 | 2009 | 98.41%
Gross Margin | 26.97% | 54.19% | 38.28% | 38.32% | 2010 | 69.02%
Change Orders ($) | 9308 | -83381 | 56774 | 0 | 2011 | 3241%
Retainage | 19710 | 69321 | 43491 | 69573 | 2009 | 98.69%
C. PER-UNIT ECONOMICS
Revenue / Unit | 2346.4762 | 8402.5394 | 7434.3932 | 8536.5337 | 2012 | 92.67%
Profit / Unit | 632.7917 | 4553.1515 | 2845.812 | 3271.6196 | 2010 | 138.7%
Direct Cost / Unit | 1713.6845 | 3849.3879 | 4588.5726 | 5264.9141 | 2009 | 92.14%
Labor Cost / Unit | 504.1548 | 1230.2303 | 1221.2222 | 1787.2577 | 2009 | 108.2%
Material Cost / Unit | 899.1905 | 1718.0242 | 2521.4188 | 2397.2454 | 2009 | 86.11%
Hours / Unit | 24.5 | 62.1818 | 59.3504 | 89.6135 | 2009 | 110.5%
D. PER-FIXTURE ECONOMICS
Revenue / Fixture | 485.4778 | 1726.5492 | 1474.278 | 1705.2145 | 2010 | 92.08%
Profit / Fixture | 130.9224 | 935.5791 | 564.339 | 653.5221 | 2010 | 140.9%
Direct Cost / Fixture | 354.5554 | 790.9701 | 909.9373 | 1051.6924 | 2009 | 89.75%
Labor / Fixture | 104.3079 | 252.787 | 242.1746 | 357.0135 | 2009 | 105.7%
Material / Fixture | 186.0394 | 353.0187 | 500.0102 | 478.8615 | 2009 | 82.74%
Hours / Fixture | 5.069 | 12.7771 | 11.7695 | 17.9007 | 2009 | 108%
E. LABOR & PRODUCTIVITY
Total Labor Hours | 4116 | 10260 | 6944 | 14607 | 2009 | 116.8%
Total Workers | 23 | 22 | 31 | 28 | 2010 | 34.62%
Blended Gross Wage | 20.58 | 19.78 | 20.58 | 19.94 | 2010 | 3.956%
Fully-Loaded Wage | 30.51 | 29.86 | 31.08 | 30.12 | 2010 | 4.014%
Revenue / Hour | 95.7745 | 135.1286 | 125.2627 | 95.2595 | 2010 | 35.33%
Profit / Hour | 25.8282 | 73.2232 | 47.9493 | 36.5081 | 2010 | 103.3%
Hours / Worker | 178.9565 | 466.3636 | 224 | 521.6786 | 2012 | 98.55%
F. COST MIX (% of Revenue)
Labor % of Revenue | 21.49% | 14.64% | 16.43% | 20.94% | 2010 | 37.25%
Material % of Revenue | 38.32% | 20.45% | 33.92% | 28.08% | 2010 | 59.2%
Overhead % of Revenue | 2.853% | 3.265% | 3.013% | 1.978% | 2012 | 46.36%
Burden % of Revenue | 10.37% | 7.459% | 8.365% | 10.68% | 2010 | 34.92%
Labor : Material Ratio | 0.56068 | 0.71607 | 0.48434 | 0.74555 | 2012 | 41.68%
G. THROUGHPUT (per month)
Revenue / Month | 24638 | 57767.4583 | 51166.1176 | 81850.2941 | 2012 | 106.2%
Units / Month | 10.5 | 6.875 | 6.8824 | 9.5882 | 2009 | 42.84%
Fixtures / Month | 50.75 | 33.4583 | 34.7059 | 48 | 2009 | 41.44%
Hours / Month | 257.25 | 427.5 | 408.4706 | 859.2353 | 2009 | 123.3%
Profit / Month | 6644.3125 | 31302.9167 | 19585.8824 | 31369.0588 | 2012 | 111.2%
SOURCES
Job #2009 — OWP_2009_JCR_Summary.xlsx • 2009 Job Detail Report.pdf
Job #2010 — OWP_2010_JCR_Summary.xlsx • 2010 Job Detail Report.pdf
Job #2011 — OWP_2011_JCR_Summary.xlsx • 2011 Job Detail Report.pdf
Job #2012 — OWP_2012_JCR_Summary_Notion.xlsx • 2012 Job Detail Report.pdf
Best column: picks the winning job per row. Range % = (max-min)/avg — spread across all 4 jobs.

## Insights
Key Observations — 4-Way Benchmark
2010 IS THE MARGIN OUTLIER | 2010 landed at 54.2% gross margin vs 38.3% on both 2011 and 2012, and 27.0% on 2009. Across 4 Seattle jobs, OWP's profit margin spans 27 points — there's no single 'normal' yet. 2010 demands a post-mortem on what made it exceptional.
2009 IS THE MARGIN FLOOR | At 27.0% gross margin, the 2009 Greenwood job is OWP's least profitable in the set despite being the smallest contract. Cost structure tells the story: direct cost = 73% of revenue (vs 46% on 2010). The single-supplier (Ferguson 73%) approach may have lost negotiating leverage that could have widened the margin.
CHINN IS THE PREFERRED GC | Three of the four jobs (2009, 2010, 2011) are Chinn Construction. Combined Chinn revenue: $2.65M, combined profit: $1.19M = 44.9% blended margin. Exxel (2012) hit 38.3% as a one-off. Chinn has been substantially more profitable on average.
DEDUCTIVE vs ADDITIVE CHANGE ORDERS | 2009: +$9K (small additive). 2010: −$83K (deductive — unusual). 2011: +$57K (3 additive COs). 2012: $0 recorded. Four different CO patterns. 2010's deductive COs likely contributed to its outsize margin via descoped work that OWP banked.
FIXTURE COUNT CLUSTER | Three of four jobs cluster tightly at 803/812/816 fixtures (2010/2009/2012). 2011 sits alone at 590. Yet hours required ranges from 4,116 (2009) to 14,607 (2012) — a 3.5× spread on similar work. Productivity is the variable, not scope.
2009 IS THE LABOR-LIGHT EXTREME | 4,116 hours over 16 months = ~257 hrs/month average. 2012 ran 14,607 hours over 17 months = ~860 hrs/month. 2009 likely had part-time crews or split-attention with concurrent jobs.
2011 HAS THE BEST HOURS/FIXTURE | 2009: 5.1. 2010: 12.8. 2011: 11.8. 2012: 17.9. Shockingly, 2009 looks like the most labor-efficient — but that's because the per-fixture math benefits from low total hours (likely under-recorded or partial JCR coverage). Excluding 2009 as an outlier, 2011 is the productivity winner.
WAGE STRUCTURE IS REMARKABLY STABLE | Blended gross wage across 4 jobs: $20.58 / $19.78 / $20.58 / $19.94. Fully-loaded: $30.51 / $29.86 / $31.08 / $30.12. Wage variance is under 5% across all 4 — OWP's crew economics are stable, so productivity differences are about hours-on-job, not pay rate.
VENDOR CONCENTRATION IS A PATTERN | 2009: Ferguson alone = 73% of AP (extreme). 2010: Rosen Supply 55%. 2011: similar concentration. 2012: top vendor concentration. Across all 4 jobs, OWP routinely puts 50-75% of material spend with one vendor. This is leverage left on the table — consolidating across jobs into a true preferred-vendor program could unlock 2-5% material savings.
PO DISCIPLINE VARIES WIDELY | 2009: 49 POs, $154K (102% of material). 2010: 24 POs, $214K (75%). 2011: 26 POs, $125K (42%). 2012: zero POs. There's no consistent procurement process across jobs — 2009 had the highest discipline, 2012 had none.
DURATION ≠ COMPLEXITY | 2009: 16mo. 2010: 24mo. 2011: 17mo. 2012: 17mo. 2010's extra duration didn't translate to more revenue per month (actually less than 2012). Long jobs are not premium jobs — they're just longer.
REVENUE PER UNIT TIGHTENING | 2009: $2,346/unit. 2010: $8,403/unit. 2011: $7,434/unit. 2012: $8,537/unit. 2009 is dramatically below the others — smaller buildings command much lower per-unit pricing. OWP earns ~3.5× more per unit on mid-size jobs vs small.
THE BIGGEST QUESTIONS FOR OWP
1. Why did 2010 deliver 54% margin while the other 3 jobs averaged 34%? Was 2010 a pricing fluke or a repeatable formula? 2. Why did 2009 land at only 27% margin? Is small-job economics structurally lower-margin, or did Ferguson concentration cost us pricing leverage? 3. Is the Chinn relationship (44.9% blended margin on $2.65M across 3 jobs) worth formalizing as a preferred-GC pipeline? 4. Across all 4 jobs, OWP puts 55-73% of material spend through one vendor per job. Could a multi-job consolidated buy unlock 3-5% material savings?
Sources: OWP_2009_JCR_Summary.xlsx, OWP_2010_JCR_Summary.xlsx, OWP_2011_JCR_Summary.xlsx, OWP_2012_JCR_Summary_Notion.xlsx