## Schedule of V. Backup
Schedule of values
PROJECT: | Old Town Mixed Use |  |  |  | PAY APPLICATION #: |  | 16
LOCATION: | Redmond, WA |  |  |  | APPLICATION DATE: |  | 2014-04-17
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2014-04-30
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1469800 | 1276289 | 128977 |  | 1405266 |  | 64534 | 70263.3
| plumbing design, engineering and permit set of drawings |  | 33000 | 33000 | 0 |  | 33000 | 100% | 0 | 1650
| plumbing permit and plumbing plan review fee | EXXEL | 39000 | 39000 | 0 |  | 39000 | 100% | 0 | 1950
P01/P02 SOG | underground piping/basins at level P01 and P02 SOG | EXXEL | 22400 | 22400 | 0 |  | 22400 | 100% | 0 | 1120
L01 PT deck | canout, sleeve, install drains PT deck at level L01 | EXXEL | 3100 | 3100 | 0 |  | 3100 | 100% | 0 | 155
L02 PT deck | canout, sleeve, install drains PT deck at level L02 | EXXEL | 6300 | 6300 | 0 |  | 6300 | 100% | 0 | 315
R1 PT deck | canout, sleeve, install drains PT deck at level R1 | EXXEL | 20400 | 20400 | 0 |  | 20400 | 100% | 0 | 1020
level P01/P02 | Roughin plumbing at parking level P01/P02 | EXXEL | 28700 | 28700 | 0 |  | 28700 | 100% | 0 | 1435
level L01 | Roughin plumbing at retail and parking level L01 | EXXEL | 36800 | 36800 | 0 |  | 36800 | 100% | 0 | 1840
level L02 | Roughin plumbing at parking level lm2 east | EXXEL | 138500 | 138500 | 0 |  | 138500 | 100% | 0 | 6925
H2O mech room | stock domestic water valve room |  | 16400 | 16400 | 0 |  | 16400 | 100% | 0 | 820
H2O mech room | install domestic water valve room | EXXEL | 4800 | 4800 | 0 |  | 4800 | 100% | 0 | 240
level R1 west | roughin plumbing in units at level R1 west |  | 101600 | 101600 | 0 |  | 101600 | 100% | 0 | 5080
level R1 east | roughin plumbing in units at level R1 east |  | 67800 | 67800 | 0 |  | 67800 | 100% | 0 | 3390
level R1 west | stock Sterling bathtubs at level R1 west |  | 4600 | 4600 | 0 |  | 4600 | 100% | 0 | 230
level R1 east | stock Sterling bathtubs at level R1 east |  | 2800 | 2800 | 0 |  | 2800 | 100% | 0 | 140
level R1 west | install bathtubs at level R1 west |  | 1500 | 1500 | 0 |  | 1500 | 100% | 0 | 75
level R1 east | install bathtubs at level R1 east |  | 900 | 900 | 0 |  | 900 | 100% | 0 | 45
level R2 west | roughin plumbing in units at level R2 west |  | 101700 | 101700 | 0 |  | 101700 | 100% | 0 | 5085
level R2 east | roughin plumbing in units at level R2 east |  | 67800 | 67800 | 0 |  | 67800 | 100% | 0 | 3390
level R2 west | stock Sterling bathtubs at level R2 west |  | 5000 | 5000 | 0 |  | 5000 | 100% | 0 | 250
level R2 east | stock Sterling bathtubs at level R2 east | roughin plumbing in units at level 1 west | 2800 | 2800 | 0 |  | 2800 | 100% | 0 | 140
level R2 west | install bathtubs at level R2 west |  | 1600 | 1600 | 0 |  | 1600 | 100% | 0 | 80
level R2 east | install bathtubs at level R2 east |  | 900 | 900 | 0 |  | 900 | 100% | 0 | 45
level R3 west | roughin plumbing in units at level R3 west |  | 101700 | 101700 | 0 |  | 101700 | 100% | 0 | 5085
level R3 east | roughin plumbing in units at level R3 east |  | 67800 | 67800 | 0 |  | 67800 | 100% | 0 | 3390
level R3 west | stock Sterling bathtubs at level R3 west |  | 5000 | 5000 | 0 |  | 5000 | 100% | 0 | 250
level R3 east | stock Sterling bathtubs at level R3 east |  | 2800 | 2800 | 0 |  | 2800 | 100% | 0 | 140
level R3 west | install bathtubs at level R3 west |  | 1600 | 1600 | 0 |  | 1600 | 100% | 0 | 80
level R3 east | install bathtubs at level R3 east |  | 900 | 900 | 0 |  | 900 | 100% | 0 | 45
level R4 west | roughin plumbing in units at level R4 west |  | 101700 | 101700 | 0 |  | 101700 | 100% | 0 | 5085
level R4 east | roughin plumbing in units at level R4 east |  | 67800 | 67800 | 0 |  | 67800 | 100% | 0 | 3390
level R4 west | stock Sterling bathtubs at level R4 west |  | 5000 | 5000 | 0 |  | 5000 | 100% | 0 | 250
level R4 east | stock Sterling bathtubs at level R4 east |  | 2800 | 2800 | 0 |  | 2800 | 100% | 0 | 140
level R4 west | install bathtubs at level R4 west |  | 1600 | 1600 | 0 |  | 1600 | 100% | 0 | 80
level R4 east | install bathtubs at level R4 east |  | 900 | 900 | 0 |  | 900 | 100% | 0 | 45
level R5 west | roughin plumbing in units at level R5 west |  | 101700 | 101700 | 0 |  | 101700 | 100% | 0 | 5085
level R5 east | roughin plumbing in units at level R5 east |  | 67800 | 67800 | 0 |  | 67800 | 100% | 0 | 3390
level R5 west | stock Sterling bathtubs at level R5 west |  | 5000 | 5000 | 0 |  | 5000 | 100% | 0 | 250
level R5 east | stock Sterling bathtubs at level R5 |  | 2800 | 2800 | 0 |  | 2800 | 100% | 0 | 140
level R5 west | install bathtubs at level R5 west |  | 1600 | 1600 | 0 |  | 1600 | 100% | 0 | 80
level R5 east | install bathtubs at level R5 east |  | 900 | 900 | 0 |  | 900 | 100% | 0 | 45
level R2 west | install toilets, lavs, sinks and water heaters at level R1 west |  | 26600 | 14533 | 12067 |  | 26600 | 100% | 0 | 1330
level R2 east | install toilets, lavs, sinks and water heaters at level R1 east |  | 17800 | 9915 | 7885 |  | 17800 | 100% | 0 | 890
level R3 west | install toilets, lavs, sinks and water heaters at level R2 west |  | 26600 | 2458 | 24142 |  | 26600 | 100% | 0 | 1330
level R3east | install toilets, lavs, sinks and water heaters at level R2 east |  | 17800 | 1583 | 16217 |  | 17800 | 100% | 0 | 890
level R4 west | install toilets, lavs, sinks and water heaters at level R3 west |  | 26600 | 0 | 26600 |  | 26600 | 100% | 0 | 1330
level R4 east | install toilets, lavs, sinks and water heaters at level R3 east |  | 17800 | 0 | 17800 |  | 17800 | 100% | 0 | 890
level R5 west | install toilets, lavs, sinks and water heaters at level R4 west |  | 26600 | 0 | 14671 |  | 14671 | 55.15% | 11929 | 733.55
level R5 east | install toilets, lavs, sinks and water heaters at level R4 east |  | 17800 | 0 | 9595 |  | 9595 | 53.9% | 8205 | 479.75
level R6 west | install toilets, lavs, sinks and water heaters at level R5 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R6east | install toilets, lavs, sinks and water heaters at level R5 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
SUBTOTAL |  |  | 1469800 | 1276289 | 128977 | 0 | 1405266 | 48.0906 | 64534 | 70263.3
CHANGE ORDERS
#1 | change DWV cast iron piping in garage and vents in residential units to pvc |  | -55000 | -55000 | 0 |  | -55000 | 100% | 0 | -2750
#1 | change waste stacks from cast iron to plastic in residential units |  | -25000 | -25000 | 0 |  | -25000 | 100% | 0 | -1250
#2 | reconcile plumbing fixture allowance (change tubs) |  | -8837 | -8837 | 0 |  | -8837 | 100% | 0 | -441.85
#3 | credit installation of bathroom vanity sinks |  | -4234 | -4234 | 0 |  | -4234 | 100% | 0 | -211.7
#4 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
-93071 | CONTRACT TOTAL |  | 1376729 | 1183218 | 128977 | 0 | 1312195 | #DIV/0! | 64534 | 65609.75
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN