## Schedule of V. Backup
Schedule of values
PROJECT: | Old Town Mixed Use |  |  |  | PAY APPLICATION #: |  | 5
LOCATION: | Redmond, WA |  |  |  | APPLICATION DATE: |  | 2013-03-19
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2013-03-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1469800 | 97500 | 0 |  | 97500 |  | 1372300 | 4875
| plumbing design, engineering and permit set of drawings |  | 33000 | 33000 | 0 |  | 33000 | 100% | 0 | 1650
| plumbing permit and plumbing plan review fee | EXXEL | 39000 | 39000 | 0 |  | 39000 | 100% | 0 | 1950
P01/P02 SOG | underground piping/basins at level P01 and P02 SOG | EXXEL | 22400 | 22400 | 0 |  | 22400 | 100% | 0 | 1120
L01 PT deck | canout, sleeve, install drains PT deck at level L01 | EXXEL | 3100 | 3100 | 0 |  | 3100 | 100% | 0 | 155
L02 PT deck | canout, sleeve, install drains PT deck at level L02 | EXXEL | 6300 | 0 | 0 |  | 0 | 0% | 6300 | 0
R1 PT deck | canout, sleeve, install drains PT deck at level R1 | EXXEL | 20400 | 0 | 0 |  | 0 | 0% | 20400 | 0
level P01/P02 | Roughin plumbing at parking level P01/P02 | EXXEL | 28700 | 0 | 0 |  | 0 | 0% | 28700 | 0
level L01 | Roughin plumbing at retail and parking level L01 | EXXEL | 36800 | 0 | 0 |  | 0 | 0% | 36800 | 0
level L02 | Roughin plumbing at parking level P2 east | EXXEL | 138500 | 0 | 0 |  | 0 | 0% | 138500 | 0
H2O mech room | stock domestic water valve room |  | 16400 | 0 | 0 |  | 0 | 0% | 16400 | 0
H2O mech room | install domestic water valve room | EXXEL | 4800 | 0 | 0 |  | 0 | 0% | 4800 | 0
level R1 west | roughin plumbing in units at level R1 west |  | 101600 | 0 | 0 |  | 0 | 0% | 101600 | 0
level R1 east | roughin plumbing in units at level R1 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R1 west | stock Sterling bathtubs at level R1 west |  | 4600 | 0 | 0 |  | 0 | 0% | 4600 | 0
level R1 east | stock Sterling bathtubs at level R1 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R1 west | install bathtubs at level R1 west |  | 1500 | 0 | 0 |  | 0 | 0% | 1500 | 0
level R1 east | install bathtubs at level R1 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R2 west | roughin plumbing in units at level R2 west |  | 101700 | 0 | 0 |  | 0 | 0% | 101700 | 0
level R2 east | roughin plumbing in units at level R2 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R2 west | stock Sterling bathtubs at level R2 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R2 east | stock Sterling bathtubs at level R2 east | roughin plumbing in units at level 1 west | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R2 west | install bathtubs at level R2 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R2 east | install bathtubs at level R2 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R3 west | roughin plumbing in units at level R3 west |  | 101700 | 0 | 0 |  | 0 | 0% | 101700 | 0
level R3 east | roughin plumbing in units at level R3 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R3 west | stock Sterling bathtubs at level R3 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R3 east | stock Sterling bathtubs at level R3 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R3 west | install bathtubs at level R3 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R3 east | install bathtubs at level R3 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R4 west | roughin plumbing in units at level R4 west |  | 101700 | 0 | 0 |  | 0 | 0% | 101700 | 0
level R4 east | roughin plumbing in units at level R4 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R4 west | stock Sterling bathtubs at level R4 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R4 east | stock Sterling bathtubs at level R4 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R4 west | install bathtubs at level R4 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R4 east | install bathtubs at level R4 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R5 west | roughin plumbing in units at level R5 west |  | 101700 | 0 | 0 |  | 0 | 0% | 101700 | 0
level R5 west | roughin plumbing in units at level R5 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R5 west | stock Sterling bathtubs at level R5 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R5 east | stock Sterling bathtubs at level R5 |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R5 west | install bathtubs at level R5 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R5 east | install bathtubs at level R5 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R1 west | install toilets, lavs, sinks and water heaters at level R1 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R1 east | install toilets, lavs, sinks and water heaters at level R1 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R2 west | install toilets, lavs, sinks and water heaters at level R2 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R2 east | install toilets, lavs, sinks and water heaters at level R2 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R3 west | install toilets, lavs, sinks and water heaters at level R3 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R3 east | install toilets, lavs, sinks and water heaters at level R3 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R4 west | install toilets, lavs, sinks and water heaters at level R4 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R4 east | install toilets, lavs, sinks and water heaters at level R4 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R5 west | install toilets, lavs, sinks and water heaters at level R5 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R5 east | install toilets, lavs, sinks and water heaters at level R5 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
SUBTOTAL |  |  | 1469800 | 97500 | 0 | 0 | 97500 | 4 | 1372300 | 4875
CHANGE ORDERS
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CONTRACT TOTAL |  |  | 1469800 | 97500 | 0 | 0 | 97500 | #DIV/0! | 1372300 | 4875
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN