## Schedule of V. Backup
Schedule of values
PROJECT: | Old Town Mixed Use |  |  |  | PAY APPLICATION #: |  | 9
LOCATION: | Redmond, WA |  |  |  | APPLICATION DATE: |  | 2013-08-20
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2013-08-31
A | B |  | C | D | E | F | G |  | H | I
Area, level | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
and/or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
phase |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1469800 | 355200 | 251700 |  | 606900 |  | 862900 | 30345
| plumbing design, engineering and permit set of drawings |  | 33000 | 33000 | 0 |  | 33000 | 100% | 0 | 1650
| plumbing permit and plumbing plan review fee | EXXEL | 39000 | 39000 | 0 |  | 39000 | 100% | 0 | 1950
P01/P02 SOG | underground piping/basins at level P01 and P02 SOG | EXXEL | 22400 | 22400 | 0 |  | 22400 | 100% | 0 | 1120
L01 PT deck | canout, sleeve, install drains PT deck at level L01 | EXXEL | 3100 | 3100 | 0 |  | 3100 | 100% | 0 | 155
L02 PT deck | canout, sleeve, install drains PT deck at level L02 | EXXEL | 6300 | 6300 | 0 |  | 6300 | 100% | 0 | 315
R1 PT deck | canout, sleeve, install drains PT deck at level R1 | EXXEL | 20400 | 20400 | 0 |  | 20400 | 100% | 0 | 1020
level P01/P02 | Roughin plumbing at parking level P01/P02 | EXXEL | 28700 | 25500 | 3200 |  | 28700 | 100% | 0 | 1435
level L01 | Roughin plumbing at retail and parking level L01 | EXXEL | 36800 | 25000 | 5000 |  | 30000 | 81.52% | 6800 | 1500
level L02 | Roughin plumbing at parking level lm2 east | EXXEL | 138500 | 120000 | 7000 |  | 127000 | 91.7% | 11500 | 6350
H2O mech room | stock domestic water valve room |  | 16400 | 0 | 0 |  | 0 | 0% | 16400 | 0
H2O mech room | install domestic water valve room | EXXEL | 4800 | 0 | 0 |  | 0 | 0% | 4800 | 0
level R1 west | roughin plumbing in units at level R1 west |  | 101600 | 46000 | 29000 |  | 75000 | 73.82% | 26600 | 3750
level R1 east | roughin plumbing in units at level R1 east |  | 67800 | 9500 | 25500 |  | 35000 | 51.62% | 32800 | 1750
level R1 west | stock Sterling bathtubs at level R1 west |  | 4600 | 0 | 0 |  | 0 | 0% | 4600 | 0
level R1 east | stock Sterling bathtubs at level R1 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R1 west | install bathtubs at level R1 west |  | 1500 | 0 | 0 |  | 0 | 0% | 1500 | 0
level R1 east | install bathtubs at level R1 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R2 west | roughin plumbing in units at level R2 west |  | 101700 | 5000 | 70000 |  | 75000 | 73.75% | 26700 | 3750
level R2 east | roughin plumbing in units at level R2 east |  | 67800 | 0 | 12000 |  | 12000 | 17.7% | 55800 | 600
level R2 west | stock Sterling bathtubs at level R2 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R2 east | stock Sterling bathtubs at level R2 east | roughin plumbing in units at level 1 west | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R2 west | install bathtubs at level R2 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R2 east | install bathtubs at level R2 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R3 west | roughin plumbing in units at level R3 west |  | 101700 | 0 | 75000 |  | 75000 | 73.75% | 26700 | 3750
level R3 east | roughin plumbing in units at level R3 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R3 west | stock Sterling bathtubs at level R3 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R3 east | stock Sterling bathtubs at level R3 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R3 west | install bathtubs at level R3 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R3 east | install bathtubs at level R3 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R4 west | roughin plumbing in units at level R4 west |  | 101700 | 0 | 25000 |  | 25000 | 24.58% | 76700 | 1250
level R4 east | roughin plumbing in units at level R4 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R4 west | stock Sterling bathtubs at level R4 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R4 east | stock Sterling bathtubs at level R4 east |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R4 west | install bathtubs at level R4 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R4 east | install bathtubs at level R4 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R5 west | roughin plumbing in units at level R5 west |  | 101700 | 0 | 0 |  | 0 | 0% | 101700 | 0
level R5 west | roughin plumbing in units at level R5 east |  | 67800 | 0 | 0 |  | 0 | 0% | 67800 | 0
level R5 west | stock Sterling bathtubs at level R5 west |  | 5000 | 0 | 0 |  | 0 | 0% | 5000 | 0
level R5 east | stock Sterling bathtubs at level R5 |  | 2800 | 0 | 0 |  | 0 | 0% | 2800 | 0
level R5 west | install bathtubs at level R5 west |  | 1600 | 0 | 0 |  | 0 | 0% | 1600 | 0
level R5 east | install bathtubs at level R5 east |  | 900 | 0 | 0 |  | 0 | 0% | 900 | 0
level R1 west | install toilets, lavs, sinks and water heaters at level R1 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R1 east | install toilets, lavs, sinks and water heaters at level R1 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R2 west | install toilets, lavs, sinks and water heaters at level R2 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R2 east | install toilets, lavs, sinks and water heaters at level R2 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R3 west | install toilets, lavs, sinks and water heaters at level R3 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R3 east | install toilets, lavs, sinks and water heaters at level R3 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R4 west | install toilets, lavs, sinks and water heaters at level R4 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R4 east | install toilets, lavs, sinks and water heaters at level R4 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
level R5 west | install toilets, lavs, sinks and water heaters at level R5 west |  | 26600 | 0 | 0 |  | 0 | 0% | 26600 | 0
level R5 east | install toilets, lavs, sinks and water heaters at level R5 east |  | 17800 | 0 | 0 |  | 0 | 0% | 17800 | 0
SUBTOTAL |  |  | 1469800 | 355200 | 251700 | 0 | 606900 | 11.8843 | 862900 | 30345
CHANGE ORDERS
#1 | change DWV cast iron piping in garage and vents in residential units to pvc |  | -55000 | 0 | -40000 |  | -40000 | 72.73% | -15000 | -2000
#1 | change waste stacks from cast iron to plastic in residential units |  | -25000 | 0 | -8000 |  | -8000 | 32% | -17000 | -400
#2 | reconcile plumbing fixture allowance (change tubs) |  | -8837 | 0 | 0 |  | 0 | 0% | -8837 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
-88837 | CONTRACT TOTAL |  | 1380963 | 355200 | 203700 | 0 | 558900 | #DIV/0! | 822063 | 27945
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN