## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | OLD TOWN MIXED USE-12-0602 |  |  | DATE: | 2014-01-16
SUBCONTRACTOR: | ONE WAY PLUMBING, LLC
SERVICE PROVIDED:
BILLING PERIOD: | 1-1-2014 - 1-31-2014 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 1469800 | a
| Previous Billing CHANGE ORDERS: | -93071 | b
| This Billing CHANGE ORDERS: |  | c
| NEW CONTRACT TOTAL: | 1376729 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 1158963 | e
| AMOUNT REMAINING ON CONTRACT: | 217766 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 1097463 | g = e
| Previous retention held - total: | 54873.15 | h
| TOTAL PAID TO DATE 1: | 984957.15 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 61500 | j
| Current retainage held: | 3075 | k
| CURRENT DUE 2: | 58425 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT