## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | OLD TOWN MIXED USE-12-0602 |  |  | DATE: | 2013-05-16
SUBCONTRACTOR: | ONE WAY PLUMBING, LLC
SERVICE PROVIDED:
BILLING PERIOD: | 5-1-13 - 5-31-13 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 1469800 | a
| Previous Billing CHANGE ORDERS: | $ | b
| This Billing CHANGE ORDERS: | $ | c
| NEW CONTRACT TOTAL: | 1469800 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 124200 | e
| AMOUNT REMAINING ON CONTRACT: | 1345600 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 103800 | g = e
| Previous retention held - total: | 5190 | h
| TOTAL PAID TO DATE 1: | 92625 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 20400 | j
| Current retainage held: | 1020 | k
| CURRENT DUE 2: | 19380 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT