## Sheet1
SUBCONTRACTORS MONTHLY BILLING SUMMARY
PROJECT NAME: | Barrett Park Apartments (12-0806) |  |  | DATE: | 2014-03-10
SUBCONTRACTOR: | ONE WAY PLUMBING, LLC
SERVICE PROVIDED:
BILLING PERIOD: | 2-15-14 - 3-15-14 |  |  | INVOICE #:
| ORIGINAL CONTRACT AMOUNT: | 813050 | a
| Previous Billing CHANGE ORDERS: | 56773.5 | b
| This Billing CHANGE ORDERS: | 0 | c
| NEW CONTRACT TOTAL: | 869823.5 | d = a+b+c
| TOTAL AMOUNT BILLED TO DATE: | 869823.5 | e
| AMOUNT REMAINING ON CONTRACT: | 0 | f = d - e
PREVIOUSLY BILLED:
| TOTAL AMOUNT BILLED TO DATE: | 769506 | g = e
| Previous retention held - total: | 38475.3 | h
| TOTAL PAID TO DATE 1: | 632233.55 | i = g - h
CURRENT BILLING AMOUNT:
| Current billing: | 100317.5 | j
| Current retainage held: | 5015.875 | k
| CURRENT DUE 2: | 95301.625 | l = j - k
**Please Note:
All invoices must be submitted for payment to the CHINN Construction main office by the 20th of each month.
No invoices can or will be paid without all primary and/or secondary lien releases.
Please complete the attached PROGRESS PAYMENT LIEN RELEASE form
1 UNCONDITIONAL AMOUNT
2 CONDITIONAL AMOUNT