## Schedule of V. Backup
SCHEDULE OF VALUES
One-Way Plumbing Contract Schedule of Values Work Sheet
To be submitted with applications for payment
PROJECT: Barrett Park Apartments |  |  |  |  | PAY APPLICATION #: |  | 13
LOCATION: Seattle, WA |  |  |  |  | APPLICATION DATE: |  | 2014-03-10
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2014-03-15
A | B |  | C | D | E | F | G |  | H | I
Area or | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
building or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
floor |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 813050 | 727550 | 85500 |  | 813050 |  | 0 | 40652.5
| plumbing design, engineered plan set | SWINERTON | 33800 | 33800 | 0 |  | 33800 | 100% | 0 | 1690
| plumbing permit |  | 8400 | 8400 | 0 |  | 8400 | 100% | 0 | 420
underground | garage drains/basins, underground waste and drain piping | SWINERTON | 46400 | 46400 | 0 |  | 46400 | 100% | 0 | 2320
level 1 | canout/sleeve and deck drains at PT deck level 1 | SWINERTON | 18700 | 18700 | 0 |  | 18700 | 100% | 0 | 935
parking level | roughin waste, vent, storm water piping in garage |  | 87200 | 87200 | 0 |  | 87200 | 100% | 0 | 4360
level 1 | roughin plumbing at level 1 |  | 98450 | 98450 | 0 |  | 98450 | 100% | 0 | 4922.5
level 1 | stock bathtubs at level 1 |  | 12600 | 12600 | 0 |  | 12600 | 100% | 0 | 630
level 1 | install bathtubs/valves at level 1 |  | 2400 | 2400 | 0 |  | 2400 | 100% | 0 | 120
level 2 | roughin plumbing at level 2 |  | 93800 | 93800 | 0 |  | 93800 | 100% | 0 | 4690
level 2 | stock bathtubs at level 2 |  | 13900 | 13900 | 0 |  | 13900 | 100% | 0 | 695
level 2 | install bathtubs/valves at level 2 |  | 2700 | 2700 | 0 |  | 2700 | 100% | 0 | 135
level 3 | roughin plumbing at level 3 |  | 93800 | 93800 | 0 |  | 93800 | 100% | 0 | 4690
level 3 | stock bathtubs at level 3 |  | 13900 | 13900 | 0 |  | 13900 | 100% | 0 | 695
level 3 | install bathtubs/valves at level 3 |  | 2700 | 2700 | 0 |  | 2700 | 100% | 0 | 135
level 4 | roughin plumbing at level 4 |  | 93800 | 93800 | 0 |  | 93800 | 100% | 0 | 4690
level 4 | stock bathtubs at level 4 |  | 13900 | 13900 | 0 |  | 13900 | 100% | 0 | 695
level 4 | install bathtubs/valves at level 4 |  | 2700 | 2700 | 0 |  | 2700 | 100% | 0 | 135
level 1 | install toilets, lavs, sinks, water heaters at level 1 |  | 41300 | 0 | 41300 |  | 41300 | 100% | 0 | 2065
level 2 | install toilets, lavs, sinks, water heaters at level 2 |  | 44200 | 0 | 44200 |  | 44200 | 100% | 0 | 2210
level 3 | install toilets, lavs, sinks, water heaters at level 3 |  | 44200 | 44200 | 0 |  | 44200 | 100% | 0 | 2210
level 4 | install toilets, lavs, sinks, water heaters at level 4 |  | 44200 | 44200 | 0 |  | 44200 | 100% | 0 | 2210
SUBTOTAL |  |  | 813050 | 727550 | 85500 | 0 | 813050 |  | 0 | 40652.5
CO # | CHANGE ORDERS
CO#1 | furnish and install footing,sub slab drains |  | 25400 | 25400 | 0 |  | 25400 | 100% | 0 | 1270
CO#2 | add trash chute wash down |  | 959 | 959 | 0 |  | 959 | 100% | 0 | 47.95
CO#3 | change plumbing fixtures |  | 30414.5 | 15597 | 14817.5 |  | 30414.5 | 100% | 0 | 1520.725
CO#4 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#5 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#6 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#7 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#8 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#9 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#10 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
56773.5 | CONTRACT TOTAL |  | 869823.5 | 769506 | 100317.5 | 0 | 869823.5 |  | 0 | 43491.175
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN