## Inputs
Inputs — Canonical Job Data
All values sourced from each job's JCR Summary workbook. Blue = hardcoded input.
Metric | Job #2011 | Job #2012 | Source / Notes
— PROFILE —
Job Name | Chinn Barrett Park | Exxel 8th Ave
General Contractor | Chinn Construction, LLC | Exxel Pacific, Inc.
Location | Seattle, WA | Seattle, WA
Duration (months) | 17 | 17 | Nov 2012–Mar 2014 / Jan 2013–Jun 2014
Unit Count | 117 | 163 | Residential units
Total Fixtures | 590 | 816 | All in-unit plumbing fixtures
— FINANCIAL —
Original Contract | 813050 | 1394655
Final Contract / Revenue | 869824 | 1391455 | Incl. change orders
Change Orders | 56774 | 0 | 2011: 3 COs; 2012: none in JCR
Net Profit | 332960 | 533274
Direct Cost | 536863 | 858181 | Labor + Material + OH + Burden
Retainage | 43491 | 69573 | 5% held by GC
— COST MIX —
Labor Cost | 142883 | 271219 | 2012 labor = avg_rate 18.57 × 14,607h (derived)
Material Cost | 295006 | 408537
Overhead Cost | 26210 | 9697
Burden Cost | 72765 | 168728 | 2012: gross×0.51 burden multiplier
— LABOR —
Total Labor Hours | 6944 | 14607
Total Workers | 31 | 28 | Unique payroll IDs
Blended Gross Wage ($/hr) | 20.58 | 19.94 | Pre-burden
Fully-Loaded Wage ($/hr) | 31.08 | 30.12 | Post-burden
— MATERIAL —
Total PO Committed | 124908 | 0 | 2012 tracks via AP invoices, not POs
Total POs | 26 | 0
Material Vendors | 14 | 17 | Distinct AP vendors
Sources: OWP_2011_JCR_Summary.xlsx (Chinn Barrett Park) + OWP_2012_JCR_Summary_Notion.xlsx (Exxel 8th Ave). Both reconcile exactly to their source JCR PDFs.

## Comparison
Job #2011 vs Job #2012 — Head-to-Head Benchmark
Chinn Barrett Park (117 units) vs Exxel 8th Ave (163 units) • both 17-month Seattle multifamily plumbing jobs
Metric | 2011 Barrett | 2012 Exxel | Δ ($ / #) | Δ % | Leader
A. PROJECT SCALE
Unit Count | 117 | 163 | 46 | 39.32% | 2012
Total Fixtures | 590 | 816 | 226 | 38.31% | 2012
Duration (months) | 17 | 17 | 0 | 0% | Tie
Fixtures / Unit | 5.0427 | 5.0061 | -0.0366 | -0.7258% | Tie
B. TOP-LINE FINANCIAL
Revenue (Final Contract) | 869824 | 1391455 | 521631 | 59.97% | 2012
Net Profit | 332960 | 533274 | 200314 | 60.16% | 2012
Direct Cost | 536863 | 858181 | 321318 | 59.85% | 2011
Gross Margin | 38.28% | 38.32% | 0.04591% | 0.1199% | Tie
Change Orders ($) | 56774 | 0 | -56774 | -100% | 2011
Retainage | 43491 | 69573 | 26082 | 59.97% | 2011
C. PER-UNIT ECONOMICS
Revenue / Unit | 7434.3932 | 8536.5337 | 1102.1406 | 14.82% | 2012
Profit / Unit | 2845.812 | 3271.6196 | 425.8077 | 14.96% | 2012
Direct Cost / Unit | 4588.5726 | 5264.9141 | 676.3415 | 14.74% | 2011
Labor Cost / Unit | 1221.2222 | 1663.9202 | 442.698 | 36.25% | 2011
Material Cost / Unit | 2521.4188 | 2506.362 | -15.0568 | -0.5972% | Tie
Hours / Unit | 59.3504 | 89.6135 | 30.2631 | 50.99% | 2011
D. PER-FIXTURE ECONOMICS
Revenue / Fixture | 1474.278 | 1705.2145 | 230.9365 | 15.66% | 2012
Profit / Fixture | 564.339 | 653.5221 | 89.1831 | 15.8% | 2012
Direct Cost / Fixture | 909.9373 | 1051.6924 | 141.7551 | 15.58% | 2011
Labor / Fixture | 242.1746 | 332.3762 | 90.2016 | 37.25% | 2011
Material / Fixture | 500.0102 | 500.6581 | 0.64792 | 0.1296% | Tie
Hours / Fixture | 11.7695 | 17.9007 | 6.1312 | 52.09% | 2011
E. LABOR & PRODUCTIVITY
Total Labor Hours | 6944 | 14607 | 7663 | 110.4% | 2011
Total Workers | 31 | 28 | -3 | -9.677% | 2012
Blended Gross Wage | 20.58 | 19.94 | -0.64 | -3.11% | 2012
Fully-Loaded Wage | 31.08 | 30.12 | -0.96 | -3.089% | 2012
Revenue / Hour | 125.2627 | 95.2595 | -30.0032 | -23.95% | 2011
Profit / Hour | 47.9493 | 36.5081 | -11.4412 | -23.86% | 2011
Hours / Worker (avg) | 224 | 521.6786 | 297.6786 | 132.9% | 2012
F. COST MIX
Labor % of Revenue | 16.43% | 19.49% | 3.065% | 18.66% | 2011
Material % of Revenue | 33.92% | 29.36% | -4.555% | -13.43% | 2012
Overhead % of Revenue | 3.013% | 0.6969% | -2.316% | -76.87% | 2012
Burden % of Revenue | 8.365% | 12.13% | 3.761% | 44.95% | 2011
Labor : Material Ratio | 0.48434 | 0.66388 | 0.17954 | 37.07% | 2012
G. THROUGHPUT (per month)
Revenue / Month | 51166.1176 | 81850.2941 | 30684.1765 | 59.97% | 2012
Units / Month | 6.8824 | 9.5882 | 2.7059 | 39.32% | 2012
Fixtures / Month | 34.7059 | 48 | 13.2941 | 38.31% | 2012
Hours / Month | 408.4706 | 859.2353 | 450.7647 | 110.4% | 2011
SOURCES
Job #2011 — OWP_2011_JCR_Summary.xlsx (Benchmark KPIs tab) • 2011 Job Detail Report.pdf
Job #2012 — OWP_2012_JCR_Summary_Notion.xlsx (Benchmark KPIs tab) • 2012 Job Detail Report.pdf
Leader column: 'Tie' if within 2% of 2011 value. Higher-is-better vs lower-is-better depends on metric.

## Insights
Key Observations — 2011 vs 2012
IDENTICAL GROSS MARGIN | Both jobs landed at 38.3% gross margin — near-identical profitability despite 60% scale difference. Strongly suggests OWP has a repeatable bidding formula for Seattle multifamily.
2012 IS 60% LARGER | 163 units vs 117 (+39%) and 816 fixtures vs 590 (+38%). Both completed in exactly 17 months — meaning 2012 absorbed the extra scale via crew density, not duration.
2012 BURNED 2.1× MORE HOURS | 14,607 hrs vs 6,944 hrs for only 1.4× the units. Hours/unit jumped from 59 to 90 (+51%). 2011 looks more labor-efficient per unit — possibly simpler unit type, fewer stacks/fixture complexity.
2011 GENERATED MORE $/HOUR | Revenue per labor hour: $125 (2011) vs $95 (2012). Profit per hour: $48 vs $37. 2011 extracted 31% more revenue per hour of crew time — consistent with its lower hour intensity.
IDENTICAL FIXTURES/UNIT (5.0) | Both projects hit ~5 fixtures/unit, the textbook 1-bath multifamily number. Apples-to-apples on fixture complexity, which makes the hours/fixture gap (11.8 vs 17.9) the single most important efficiency insight.
HOURS/FIXTURE — 52% GAP | 2011: 11.8 hrs/fixture. 2012: 17.9 hrs/fixture. This is a huge productivity gap on identical fixture density. Worth investigating: was 2012 a harder building (mid-rise vs low-rise), taller stacks, rework, or crew composition?
SIMILAR WAGE STRUCTURE | Blended gross wage: $20.58 vs $19.94. Fully-loaded: $31.08 vs $30.12. Near-identical crew economics — the hours gap is NOT explained by wage differences.
2011 HEAVIER ON MATERIAL | Material % of revenue: 33.9% (2011) vs 29.4% (2012). 2011 spent more on materials per unit ($2,521 vs $2,397) but less on labor per unit ($1,221 vs $1,664). Different trade-off: more materials, less labor.
2012 DID NOT TRACK POS | 2011 committed $125K across 26 POs (42% PO coverage of material). 2012 has no PO log in the source folder — tracked material exclusively via 186 AP invoices. Process difference, not a red flag.
BOTH HAD 38% NET PROFIT | 2011: $332,960 profit on $869,824 revenue. 2012: $533,274 profit on $1,391,455 revenue. Dollar-for-dollar scaling — OWP's margin discipline held across two different GCs (Chinn / Exxel).
CREW DENSITY DIFFERENCE | 31 workers on 117 units = 1 worker per 3.8 units (2011). 28 workers on 163 units = 1 per 5.8 units (2012). 2012 ran a leaner crew per unit but worked them 2× as many hours each (522 vs 224 avg).
2011 HAD 3 CHANGE ORDERS | CO #1 foundation drains ($25.4K), CO #2 trash chute ($1K), CO #3 fixture change ($30.4K) = $56.8K total (+7% of original). 2012 JCR shows no captured COs — either none occurred, or were embedded in original contract revisions.
BIGGEST QUESTION FOR OWP
Why did 2012 take 52% more labor hours per fixture than 2011, despite identical fixture density (5/unit), identical margin (38.3%), and identical duration (17 months)? If that gap were closed, 2012's profit could have risen by an estimated $230K+ (5,000 hrs × $46 profit/hr).
Sources: OWP_2011_JCR_Summary.xlsx and OWP_2012_JCR_Summary_Notion.xlsx (both reconcile exactly to JCR PDFs)