SUBCONTRACTOR/SUPPLIER APPLICATION FOR PAYMENT

General Contractor:  EXXEL PACIFIC, INC.

Subcontractor/Supplier: One Way Plumbing, LLC

Address:	127 10th Street South, suite 200   Kirkland, WA 98033

City / State / Zip

Phone No. 	425-968-8314 ext. 115	Fax No.	425-968-8794

Project:	8TH Avenue Apts	Job No.    201301

Pay Application Number 4			Application Date 6-20-13

Period Date5-1-13		Through 5-31-13

1.	Original Contract Amount	$ 1,394,655.00

2.	Approved Change Order Number (s)

_______1___ through __1__________	$11,100.00

3.	Adjusted Contract Amount	$1,405,755.00

4.	Total Completed & Stored To-Date	$121,100.00

5.	Less Previous Billed	$105,200.00

(sum of line 6 of all previous months)

6.	Total (line 4 minus line 5)	$15,900.00

7.	Less   5 % Retainage /           % Discount	$795.00

8.	Amount Due this Request	$15,105.00

Exxel Pacific, Inc. Use Only

Subcontract #:    			Phase Code:  				$

Pay Application #:    		   				$

Approval:    		   				$

Comments:	  		  				$

Total:		$

CERTIFICATE OF THE SUBCONTRACTOR:  I hereby certify that the work performed and the materials supplied to-date, as shown on the above represent the actual value of accomplishment under the terms of the Contract (and all authorized changes thereto) between the undersigned and Exxel Pacific, Inc. relating to the above referenced project.

I also certify that payment, less applicable retention, have been made through the period covered by previous payments received from the contractor, to (1) all my subcontractors (sub-subcontractors) and (2) for all materials and labor used in or in connection with the performance of this Contract.  I further certify I have complied with Federal, State and local tax laws, including Social Security laws, and Unemployment Compensation laws and Workmen’s Compensation laws insofar as applicable to the performance of this Contract.

__One Way Plumbing, LLC______________	 Brett Mortimore___/Title President______

(Subcontractor/Supplier Company Name) 	(Printed Name of Authorized Corporate Officer/Partner/Owner)

DATED this 20_day of _June_, 2013_.	_________________________________________

(Signature)

Revised 5-14-12