## Schedule of V. Backup
SCHEDULE OF VALUES
One-Way Plumbing Contract Schedule of Values Work Sheet
To be submitted with applications for payment
PROJECT: 8th Ave Apartments |  |  |  |  | PAY APPLICATION #: |  | 11
LOCATION: Seattle, WA |  |  |  |  | APPLICATION DATE: |  | 2014-01-20
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2014-01-31
A | B |  | C | D | E | F | G |  | H | I
Area or | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
building or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
floor |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1394655 | 1177950 | 119750 |  | 1297700 |  | 96955 | 64885
| plumbing design and engineering | SWINERTON | 48000 | 48000 | 0 |  | 48000 | 100% | 0 | 2400
| Plumbing and gas pipe permits |  | 11000 | 11000 | 0 |  | 11000 | 100% | 0 | 550
underground | garage drains/basin, underground waste,storm,foundation | SWINERTON | 34000 | 34000 | 0 |  | 34000 | 100% | 0 | 1700
level 1 PT deck | canout/sleeve and install deck drains at level 1 | SWINERTON | 12200 | 12200 | 0 |  | 12200 | 100% | 0 | 610
level 2 PT deck | canout/sleeve at level 2 | SWINERTON | 15900 | 15900 | 0 |  | 15900 | 100% | 0 | 795
level 3 PT deck | canout/sleeve at level 3 | SWINERTON | 15900 | 15900 | 0 |  | 15900 | 100% | 0 | 795
level P1 | roughin plumbing at level P1 | SWINERTON | 91600 | 91600 | 0 |  | 91600 | 100% | 0 | 4580
level P1 | install water heaters, pumps, tank at heater room |  | 62500 | 43800 | 8200 |  | 52000 | 83.2% | 10500 | 2600
level P1 | install duplex water pressure booster package |  | 28000 | 19600 | 8400 |  | 28000 | 100% | 0 | 1400
level P1 | install garage and foundation drain pump systems |  | 8500 | 7200 | 1300 |  | 8500 | 100% | 0 | 425
| roughin and install gas piping |  | 10500 | 5250 | 5250 |  | 10500 | 100% | 0 | 525
level 1 | roughin plumbing at level 1 |  | 139600 | 126000 | 13600 |  | 139600 | 100% | 0 | 6980
level 1 | stock bathtubs at level 1 |  | 2900 | 2900 | 0 |  | 2900 | 100% | 0 | 145
level 1 | install bathtubs/valves at level 1 |  | 800 | 0 | 800 |  | 800 | 100% | 0 | 40
level 2 | roughin plumbing at level 2 |  | 122600 | 92000 | 30600 |  | 122600 | 100% | 0 | 6130
level 2 | stock bathtubs at level 2 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 2 | install bathtubs/valves at level 2 |  | 3500 | 0 | 3500 |  | 3500 | 100% | 0 | 175
level 3 | roughin plumbing at level 3 |  | 122600 | 122600 | 0 |  | 122600 | 100% | 0 | 6130
level 3 | firestop plumbing in wood frame |  | 2900 | 0 | 2900 |  | 2900 | 100% | 0 | 145
level 3 | stock bathtubs at level 3 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 3 | install bathtubs/valves at level 3 |  | 3500 | 3500 | 0 |  | 3500 | 100% | 0 | 175
level 4 | roughin plumbing at level 4 |  | 122600 | 122600 | 0 |  | 122600 | 100% | 0 | 6130
level 4 | firestop plumbing in wood frame |  | 2900 | 0 | 2900 |  | 2900 | 100% | 0 | 145
level 4 | stock bathtubs at level 4 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 4 | install bathtubs/valves at level 4 |  | 3500 | 3500 | 0 |  | 3500 | 100% | 0 | 175
level 5 | roughin plumbing at level 5 |  | 122600 | 122600 | 0 |  | 122600 | 100% | 0 | 6130
level 5 | firestop plumbing in wood frame |  | 2900 | 0 | 2900 |  | 2900 | 100% | 0 | 145
level 5 | stock bathtubs at level 5 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 5 | install bathtubs/valves at level 5 |  | 3500 | 3500 | 0 |  | 3500 | 100% | 0 | 175
level 6 | roughin plumbing at level 6 |  | 122600 | 122600 | 0 |  | 122600 | 100% | 0 | 6130
level 6 | firestop plumbing in wood frame |  | 2900 | 0 | 2900 |  | 2900 | 100% | 0 | 145
level 6 | stock bathtubs at level 6 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 6 | install bathtubs/valves at level 6 |  | 3500 | 3500 | 0 |  | 3500 | 100% | 0 | 175
level 7 | roughin plumbing at level 7 |  | 70900 | 70900 | 0 |  | 70900 | 100% | 0 | 3545
level 7 | firestop plumbing in wood frame |  | 2700 | 0 | 2700 |  | 2700 | 100% | 0 | 135
level 7 | stock bathtubs at level 7 |  | 12300 | 12300 | 0 |  | 12300 | 100% | 0 | 615
level 7 | install bathtubs/valves at level 7 |  | 3500 | 3500 | 0 |  | 3500 | 100% | 0 | 175
level 1 | install toilets, lavs and sinks at level 1 |  | 4455 | 0 | 0 |  | 0 | 0% | 4455 | 0
level 2 | install toilets, lavs and sinks at level 2 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 3 | install toilets, lavs and sinks at level 3 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 4 | install toilets, lavs and sinks at level 4 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 5 | install toilets, lavs and sinks at level 5 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 6 | install toilets, lavs and sinks at level 6 |  | 19300 | 0 | 14500 |  | 14500 | 75.13% | 4800 | 725
level 7 | install toilets, lavs and sinks at level 7 |  | 19300 | 0 | 19300 |  | 19300 | 100% | 0 | 965
SUBTOTAL |  |  | 1394655 | 1177950 | 119750 | 0 | 1297700 |  | 96955 | 64885
CO # | CHANGE ORDERS
CO#1 | upgrade to elongated bowl |  | 2754 | 0 | 450 |  | 450 | 16.34% | 2304 | 22.5
CO#1 | change lav faucets to grohe 34270 |  | -102 | 0 | -102 |  | -102 | 100% | 0 | -5.1
CO#1 | change fiberglass tub/shower to aquatic smooth wall stall |  | 3705 | 3705 | 0 |  | 3705 | 100% | 0 | 185.25
CO#1 | upgrade kitchen sinks to 8'' deep bowls in type b units |  | 4743 | 0 | 785 |  | 785 | 16.55% | 3958 | 39.25
CO#2 | delete firestopping scope |  | -14300 | 0 | -14300 |  | -14300 | 100% | 0 | -715
CO#3 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#4 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#5 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#6 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
-3200 | CONTRACT TOTAL |  | 1391455 | 1181655 | 106583 | 0 | 1288238 |  | 103217 | 64411.9
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN