## Schedule of V. Backup
SCHEDULE OF VALUES
One-Way Plumbing Contract Schedule of Values Work Sheet
To be submitted with applications for payment
PROJECT: 8th Ave Apartments |  |  |  |  | PAY APPLICATION #: |  | 2
LOCATION: Seattle, WA |  |  |  |  | APPLICATION DATE: |  | 2013-04-18
DESCRIPTION: APPLICATION FOR PAYMENT |  |  |  |  | PERIOD TO: |  | 2013-04-30
A | B |  | C | D | E | F | G |  | H | I
Area or | DESCRIPTION | Name of Subcontractor/ | SCHEDULED | WORK COMPLETED |  |  | COMPLETED | PERCENT | BALANCE | RETAINAGE
building or |  | Supplier | Value | FROM | THIS |  | AND STORED | COMPLETE | TO FINISH | 5%
floor |  |  |  | PREVIOUS | PERIOD |  | TO DATE
Plumbing | description of work |  | 1394655 | 48000 | 41000 |  | 89000 |  | 1305655 | 4450
| plumbing design and engineering | SWINERTON | 48000 | 48000 | 0 |  | 48000 | 100% | 0 | 2400
| Plumbing and gas pipe permits |  | 11000 | 0 | 11000 |  | 11000 | 100% | 0 | 550
underground | garage drains/basin, underground waste,storm,foundation | SWINERTON | 34000 | 0 | 30000 |  | 30000 | 88.24% | 4000 | 1500
level 1 PT deck | canout/sleeve and install deck drains at level 1 | SWINERTON | 12200 | 0 | 0 |  | 0 | 0% | 12200 | 0
level 2 PT deck | canout/sleeve at level 2 | SWINERTON | 15900 | 0 | 0 |  | 0 | 0% | 15900 | 0
level 3 PT deck | canout/sleeve at level 3 | SWINERTON | 15900 | 0 | 0 |  | 0 | 0% | 15900 | 0
level P1 | roughin plumbing at level P1 | SWINERTON | 91600 | 0 | 0 |  | 0 | 0% | 91600 | 0
level P1 | install water heaters, pumps, tank at heater room |  | 62500 | 0 | 0 |  | 0 | 0% | 62500 | 0
level P1 | install duplex water pressure booster package |  | 28000 | 0 | 0 |  | 0 | 0% | 28000 | 0
level P1 | install garage and foundation drain pump systems |  | 8500 | 0 | 0 |  | 0 | 0% | 8500 | 0
| roughin and install gas piping |  | 10500 | 0 | 0 |  | 0 | 0% | 10500 | 0
level 1 | roughin plumbing at level 1 |  | 139600 | 0 | 0 |  | 0 | 0% | 139600 | 0
level 1 | stock bathtubs at level 1 |  | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
level 1 | install bathtubs/valves at level 1 |  | 800 | 0 | 0 |  | 0 | 0% | 800 | 0
level 2 | roughin plumbing at level 2 |  | 122600 | 0 | 0 |  | 0 | 0% | 122600 | 0
level 2 | stock bathtubs at level 2 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 2 | install bathtubs/valves at level 2 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 3 | roughin plumbing at level 3 |  | 122600 | 0 | 0 |  | 0 | 0% | 122600 | 0
level 3 | firestop plumbing in wood frame |  | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
level 3 | stock bathtubs at level 3 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 3 | install bathtubs/valves at level 3 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 4 | roughin plumbing at level 4 |  | 122600 | 0 | 0 |  | 0 | 0% | 122600 | 0
level 4 | firestop plumbing in wood frame |  | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
level 4 | stock bathtubs at level 4 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 4 | install bathtubs/valves at level 4 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 5 | roughin plumbing at level 5 |  | 122600 | 0 | 0 |  | 0 | 0% | 122600 | 0
level 5 | firestop plumbing in wood frame |  | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
level 5 | stock bathtubs at level 5 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 5 | install bathtubs/valves at level 5 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 6 | roughin plumbing at level 6 |  | 122600 | 0 | 0 |  | 0 | 0% | 122600 | 0
level 6 | firestop plumbing in wood frame |  | 2900 | 0 | 0 |  | 0 | 0% | 2900 | 0
level 6 | stock bathtubs at level 6 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 6 | install bathtubs/valves at level 6 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 7 | roughin plumbing at level 7 |  | 70900 | 0 | 0 |  | 0 | 0% | 70900 | 0
level 7 | firestop plumbing in wood frame |  | 2700 | 0 | 0 |  | 0 | 0% | 2700 | 0
level 7 | stock bathtubs at level 7 |  | 12300 | 0 | 0 |  | 0 | 0% | 12300 | 0
level 7 | install bathtubs/valves at level 7 |  | 3500 | 0 | 0 |  | 0 | 0% | 3500 | 0
level 1 | install toilets, lavs and sinks at level 1 |  | 4455 | 0 | 0 |  | 0 | 0% | 4455 | 0
level 2 | install toilets, lavs and sinks at level 2 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 3 | install toilets, lavs and sinks at level 3 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 4 | install toilets, lavs and sinks at level 4 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 5 | install toilets, lavs and sinks at level 5 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 6 | install toilets, lavs and sinks at level 6 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
level 7 | install toilets, lavs and sinks at level 7 |  | 19300 | 0 | 0 |  | 0 | 0% | 19300 | 0
SUBTOTAL |  |  | 1394655 | 48000 | 41000 | 0 | 89000 |  | 1305655 | 4450
CO # | CHANGE ORDERS
CO#1 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#2 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#3 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#4 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#5 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#6 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#7 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#8 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
CO#9 |  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | 0
0 | CONTRACT TOTAL |  | 1394655 | 48000 | 41000 | 0 | 89000 |  | 1305655 | 4450
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN
GOTO PAYAPP
INPUT NEW
PERCENT
COMPLETES
GOTO PAYAPP FORM
GOTO DETAIL BREAKDOWN