## Project Summary
OWP Job #2012 - Exxel 8th Ave Apartments - Project Financial Summary
Metric | Value | Notes
Contract Value | 1394655 | Original contract
Billed Revenue (AR) | 1391455 | Total invoiced to Exxel Pacific
Total Direct Expenses | 858180.7 | PR + AP + GL
JCR Net Profit | 533274.3 | Revenue - Expenses
JCR Profit Margin | 38.3% | Before payroll burden & G&A
Retainage Held | 69572.75 | 5% of revenue
Payroll (PR) | 439953.72 | 51.3% of expenses
Accounts Payable (AP) | 408537.07 | 47.6% of expenses
General Ledger (GL) | 9689.91 | 1.1% of expenses
Labor-to-Material Ratio | 1.05 | PR / (AP+GL)
Project Duration | ~17 months | Jan 2013 - Jun 2014
Units | 163 | Apartments
Building Type | Mid-rise multifamily | 5+ stories, Seattle WA
Trade | Plumbing (Division 22)
GC | Exxel Pacific, Inc.
Total Unique Workers | 28 | 18 roughin + 10 finish
Total Labor Hours | 14607 | All cost codes

## Labor by Phase
Labor Cost by Phase - Budget vs Actual
Cost Code | Phase | Budget | Actual | Variance ($) | Variance (%) | Hours | Avg $/Hr
120 | Roughin Labor | 139800 | 177291.75 | 37491.75 | 26.82% | 9319.5 | 19.0237
130 | Finish Labor | 31000 | 34658.38 | 3658.38 | 11.8% | 1840.75 | 18.8284
111 | Garage Labor | 14600 | 19353.5 | 4753.5 | 32.56% | 872 | 22.1944
141 | Water Main/Insulation | 41000 | 15756 | -25244 | -61.57% | 800 | 19.695
142 | Mech Room | 3525 | 9784 | 6259 | 177.6% | 379 | 25.8153
145 | Tub/Shower Labor | 19800 | 6781 | -13019 | -65.75% | 338 | 20.0621
101 | Takeoff & Purchase | 12150 | 6161.5 | -5988.5 | -49.29% | 172.5 | 35.7188
100 | Supervision | 8100 | 6023 | -2077 | -25.64% | 165 | 36.503
112 | Canout Labor | 11700 | 5424 | -6276 | -53.64% | 238 | 22.7899
011 | DS & RD Labor | 12500 | 3752.5 | -8747.5 | -69.98% | 183 | 20.5055
110 | Underground Labor | 5800 | 3184.25 | -2615.75 | -45.1% | 145.5 | 21.8849
140 | Gas Labor | 3300 | 2168 | -1132 | -34.3% | 104 | 20.8462
113 | Foundation Drain | 2700 | 984 | -1716 | -63.56% | 50 | 19.68
| TOTAL | 305975 | 291321.88 | -14653.12 | -4.789% | 14607.25 | 19.9436

## Material by Phase
Material Cost by Phase - Budget vs Actual
Cost Code | Phase | Budget | Actual | Variance ($) | Variance (%)
220 | Roughin Material | 12000 | 22695.31 | 10695.31 | 89.13%
039 | DS & RD Material | 17900 | 12833.2 | -5066.8 | -28.31%
212 | Canout Material | 13130 | 8579.19 | -4550.81 | -34.66%
211 | Garage Material | 11970 | 6599.03 | -5370.97 | -44.87%
245 | Tub/Shower Material | 0 | 2278.99 | 2278.99 | N/A
213 | Foundation Material | 2700 | 1789.12 | -910.88 | -33.74%
210 | Underground Material | 4300 | 1635.51 | -2664.49 | -61.96%
| TOTAL | 62000 | 56410.35 | -5589.65 | -9.016%

## Other Costs
Subs, Overhead & Other Costs
Cost Code | Category | Type | Budget | Actual | Variance ($)
601 | Engineering/Plans | Subcontractor | 22000 | 15682.03 | -6317.97
603 | Permits & Licenses | Overhead | 10900 | 9741.88 | -1158.12
130OH | Overhead 1 (Payroll) | Burden | 0 | 22289.38 | 22289.38
604 | Backcharges | Overhead | 0 | 1837.5 | 1837.5
600 | Subcontractor | Subcontractor | 1000 | 186 | -814
607 | Other Expenses | Overhead | 25600 | 70.71 | -25529.29
| TOTAL |  | 59500 | 49807.5 | -9692.5

## Per-Unit Metrics
Per-Unit Estimating Benchmarks (163 Units)
Metric | Total | Per Unit | % of Revenue
Revenue | 1391455 | 8536.5337 | 100%
Total Direct Cost | 858180.7 | 5264.9123 | 61.68%
JCR Net Profit | 533274.3 | 3271.6215 | 38.32%
Labor (PR) | 439953.72 | 2699.1026 | 31.62%
Material (AP+GL) | 418226.98 | 2565.8097 | 30.06%
Roughin Labor | 177291.75 | 1087.6794 | 12.74%
Roughin Material | 22695.31 | 139.235 | 1.631%
Finish Labor | 34658.38 | 212.6281 | 2.491%
Garage Labor | 19353.5 | 118.7331 | 1.391%
Water Main/Insulation Labor | 15756 | 96.6626 | 1.132%
Mech Room Labor | 9784 | 60.0245 | 0.7031%
Tub/Shower Labor | 6781 | 41.6012 | 0.4873%
Engineering/Plans | 15682.03 | 96.2088 | 1.127%
Permits & Licenses | 9741.88 | 59.7661 | 0.7001%
Supervision | 6023 | 36.9509 | 0.4329%
Canout Labor | 5424 | 33.2761 | 0.3898%
Underground Labor | 3184.25 | 19.5353 | 0.2288%
DS & RD Labor | 3752.5 | 23.0215 | 0.2697%
Gas Labor | 2168 | 13.3006 | 0.1558%
Foundation Drain | 984 | 6.0368 | 0.07072%
Labor Hours per Unit
Phase | Total Hours | Hours/Unit | % of Total
Roughin | 9319.5 | 57.1748 | 63.8%
Finish | 1840.75 | 11.2929 | 12.6%
Garage | 872 | 5.3497 | 5.97%
Water Main/Insulation | 800 | 4.908 | 5.477%
Mech Room | 379 | 2.3252 | 2.595%
Tub/Shower | 338 | 2.0736 | 2.314%
Canout | 238 | 1.4601 | 1.629%
DS & RD | 183 | 1.1227 | 1.253%
Takeoff & Purchase | 172.5 | 1.0583 | 1.181%
Supervision | 165 | 1.0123 | 1.13%
Underground | 145.5 | 0.89264 | 0.9961%
Gas | 104 | 0.63804 | 0.712%
Foundation Drain | 50 | 0.30675 | 0.3423%
TOTAL | 14607.25 | 89.615

## Budget Variance
Budget Variance Analysis - Top Savings & Overruns
TOP OVERRUNS (Over Budget)
Phase | Budget | Actual | Overage ($) | Overage (%) | Impact
120 - Roughin Labor | 139800 | 177291.75 | 37491.75 | 26.82% | Biggest $ risk — 64% of labor hours
220 - Roughin Material | 12000 | 22695.31 | 10695.31 | 89.13% | Material usage underestimated
142 - Mech Room Labor | 3525 | 9784 | 6259 | 177.6% | Worst % overrun — complex manifolds
111 - Garage Labor | 14600 | 19353.5 | 4753.5 | 32.56% | Below-grade coordination delays
130 - Finish Labor | 31000 | 34658.38 | 3658.38 | 11.8% | Punch list on 163 units adds up
245 - Tub/Shower Material | 0 | 2278.99 | 2278.99 | N/A | Unbudgeted — missed in estimate
604 - Backcharges | 0 | 1837.5 | 1837.5 | N/A | Unbudgeted — GC backcharges
TOP SAVINGS (Under Budget)
Phase | Budget | Actual | Savings ($) | Savings (%) | Impact
141 - Water Main/Insulation | 41000 | 15756 | 25244 | 61.57% | Est too conservative or scope change
607 - Other Expenses | 25600 | 70.71 | 25529.29 | 99.72% | Budget not used — may be misallocated
145 - Tub/Shower Labor | 19800 | 6781 | 13019 | 65.75% | Scope possibly reduced
011 - DS & RD Labor | 12500 | 3752.5 | 8747.5 | 69.98% | Less design work than expected
601 - Engineering/Plans | 22000 | 15682.03 | 6317.97 | 28.72% | Franklin Eng efficient
112 - Canout Labor | 11700 | 5424 | 6276 | 53.64% | Crew efficiency
101 - Takeoff & Purchase | 12150 | 6161.5 | 5988.5 | 49.29% | Efficient procurement

## Crew Analysis
Crew Composition & Wage Rate Analysis
Worker | Employee Code | Role/Tier | Est. Gross Rate ($/hr) | Primary Phases
Gerard, Jeffrey S | GE69 | Superintendent | 36.5 | Supervision, Takeoff, Roughin
Quintanilla, Esteban R | QU35 | Lead Journeyman | 31 | Roughin, Mech Room, Garage
Sanders, Allen O | SA54 | Lead Journeyman | 29 | Finish
Waites, Thaddeus Z | WA35 | Lead Journeyman | 28 | Finish, Roughin
Castro Hernandez, Carlos E | CA75 | Journeyman | 28 | DS&RD, Roughin
Veley, Nathaniel S | VE45 | Journeyman | 27 | Roughin, Underground, Canout
Palma Vides, Hugo | PA46 | Journeyman | 27 | Roughin, DS&RD
Cortes Mendiola, Victor H | CO71 | Journeyman | 24 | Roughin, Garage
Sepulveda Gonzalez, Alfredo | SE64 | Journeyman | 24 | Roughin, Garage
Lima Romero, Melvin A | LI49 | Journeyman | 20 | Roughin, Underground
Rivera, Jorge A | RI87 | Journeyman | 18 | Roughin, Tub/Shower
Meza Fuentes, Erick A | ME98 | Finish Lead | 20 | Finish
Castaneda Martinez, Gustavo | CA74 | Journeyman | 27 | Roughin
Castro Hernandez, Jose A | CA77 | Journeyman | 15 | Roughin, Tub/Shower
Castaneda Juarez, Edgar D | CA72 | Finisher | 14.5 | Finish
Garcia, Jordan X | GA70 | Finisher | 14 | Finish
Spears, Gregory M | SP17 | Apprentice | 13 | Roughin
Holmes, Anthony R | HO14 | Apprentice | 13 | Roughin, DS&RD
Monico Brambila, Jesus S | MO54 | Apprentice | 13 | Roughin
Soto Cruz, Jovani | SO78 | Finisher | 16 | Finish
Soto Serna, Cesar E | SO79 | Finisher | 13 | Finish
Vaughan, Tyler J | VA86 | Finisher | 16 | Finish
Wilson, Garret A | WI46 | Finisher | 13 | Finish
Ramos Garcia, Jose M | RA54 | Finisher | 13 | Finish
Gonzalez Hernandez, Josue | GO56 | Plumber | 12 | Roughin, Finish
Chavarria Lopez, Omar A | CH04 | Plumber | 12 | Roughin, Tub/Shower
Vega Arriaga, Jorge | VE25 | Plumber | 12 | Roughin
Rivera, Eli P | RI84 | Plumber | 12 | Roughin, Tub/Shower
Rate Tier Summary
Tier | Rate Range | Count | Use For Estimating
Superintendent | $33-38/hr | 1 | 1 per project, full duration
Lead Journeyman | $28-31/hr | 4 | 1-2 per crew, lead pipe fitting
Journeyman | $20-27/hr | 8 | Core installation crew
Apprentice | $12-16/hr | 7 | Support, material handling
Helper/Plumber | $12-14/hr | 8 | Assist journeymen

## Bidding Insights
Key Estimating Insights for Future Bidding
# | Insight | Recommendation
1 | Roughin labor is the #1 cost risk — 64% of hours, 27% over budget | Estimate ~57 roughin hours/unit min. Add 15-20% contingency on mid-rise multifamily.
2 | Labor-to-material ratio is nearly 1:1 ($440K vs $418K) | Use 50/50 split as sanity check on future plumbing bids.
3 | Mech room was 178% over budget ($9,784 vs $3,525) | Budget mech rooms at 2-3x initial estimate. Complex manifolds and circ pumps are always underestimated.
4 | Garage/below-grade was 33% over budget | Add 25-35% contingency for underground/garage work. Coordination with concrete pours is unpredictable.
5 | Roughin material was 89% over budget ($22.7K vs $12K) | Double material budget for roughin. Waste/rework factor is higher than other phases.
6 | Finish labor went 12% over on 163 units | Budget ~11.3 hrs/unit for finish. Punch lists compound at scale — add $25/unit buffer.
7 | Water Main/Insulation was 62% UNDER budget | Tighten this estimate by 40-50%. Current budgeting is too conservative.
8 | Tub/Shower was 66% UNDER budget | Reduce tub/shower labor estimate by ~50%. Standardized units on multifamily go fast.
9 | Per-unit cost benchmark: $5,265 direct cost / $8,537 revenue | Use $5,000-$5,500/unit as base cost for similar Division 22 scope. Target $8,000-$9,000/unit revenue.
10 | 28 unique workers, peak crew of 12-15 during roughin | Plan workforce at ~12-15 for roughin, ~6-8 for finish. Superintendent was part-time — budget full-time for larger projects.
11 | Blended gross wage rate: $19.94/hr; fully loaded: $30.12/hr | Use $30/hr as blended burdened rate for estimating. Adjust for prevailing wage projects.
12 | Engineering came in 29% under ($15.7K vs $22K budget) | Lock in engineering fees early. Franklin Engineering was the primary — build relationship pricing.
13 | Permits = $9,742 (89% of budget) — very predictable | Use ~$60/unit for permits on Seattle multifamily plumbing.
14 | Retainage of $69,573 (5%) held throughout project | Factor 5% retainage into cash flow. 17-month project = significant capital tied up.
15 | Billing was across 8 invoice numbers over 13 months | Monthly progress billing. Ensure pay apps are submitted promptly to minimize float.

## Vendor Summary
Key Vendors & Supplier Spend
Vendor | Type | Key Materials/Services | Notes
Rosen Supply Company, Inc. | Material Supplier | Pipe, fittings, valves — primary supplier | Multiple POs across all phases
Ferguson Enterprises, Inc. | Material Supplier | Fixtures, specialty items, water heaters | Second largest supplier
Keller Supply Company | Material Supplier | Fittings, parts, specialty items | Third supplier
Manor Hardware & Construction Supply | Material Supplier | Tub/shower units, hardware | Tub/shower phase only
Franklin Engineering | Engineering Sub | Engineering plans, shop drawings | $15,682 — 4 invoices
R.A. Brown Backflow Testing | Testing Sub | Backflow prevention testing | $186 — single test
Patchworks, Inc. | Backcharge Sub | Drywall/patching repairs | $1,838 — backcharges from GC
DRSi | Engineering Sub | Design/review services | $69 — minor
Bank of America CC | Credit Card | Permits, misc purchases | Multiple small charges
Capital One Credit Card | Credit Card | Permits, misc supplies | Multiple small charges
American Express 3-41000 | Credit Card | Misc expenses | Small charges