## Report Record
JCR TEST LABELS — JOB 2106
Report-level fields from the v4 schema (v2.2 with extensions).
Field | Value
job_number | 2106
job_name | Chinn, 6220 Roosevelt
report_date | 2026-04-03
project_start_date | Jul 2026 (expected)
project_end_date | pending project-attribute input
general_contractor | Chinn Construction, LLC
owner | TBD
location | 6220 Roosevelt Way NE, Seattle, WA
project_type | Multi-family apartments (pre-construction)
units | 146
contract_original | 0
contract_final | 0
billed_to_date | 49275
retention_amount | 0
line_items_count | 298
cost_code_count | 6
job_totals_revenue | -49275
job_totals_expenses | 45726.76
job_totals_net | -3548.24
job_totals_net_due | -49275
job_totals_retainage | 0

## Line Items
LINE ITEMS — 298 TRANSACTIONS
Every transaction line parsed from the JDR PDF.
cost_code | description | source | ref_number | document_date | posted_date | number | name | regular_hours | overtime_hours | doubletime_hours | other_hours | regular_amount | overtime_amount | actual_amount | check_number | net_due | retainage
100 | Supervision | PR | 27 | 04/01/26 | 04/03/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13807 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 548 | 08/27/25 | 08/29/25 | GE69 | Gerard, Jeffrey S | 4 | 0 | 0 | 0 | 276 | 0 | 276 | 53641 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 262 | 09/17/25 | 09/19/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 33658 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 433 | 09/24/25 | 09/26/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43665 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 1.5 | 0 | 0 | 0 | 90 | 0 | 90 | 13674 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 1 | 0 | 0 | 0 | 60 | 0 | 60 | 13674 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0.25 | 0 | 0 | 0 | 15 | 0 | 15 | 13674 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23680 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23680 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 372 | 10/15/25 | 10/17/25 | BA70 | Barnhart, Joseph N | 1.75 | 0 | 0 | 0 | 119 | 0 | 119 | 33673 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 33688 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33688 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33688 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 3.25 | 0 | 0 | 0 | 195 | 0 | 195 | 33689 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0.5 | 0 | 0 | 0 | 30 | 0 | 30 | 33689 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 105 | 0 | 105 | 33689 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 3 | 0 | 0 | 0 | 180 | 0 | 180 | 33689 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 521 | 10/22/25 | 10/24/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43697 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 522 | 10/22/25 | 10/24/25 | GE70 | Gerard, Jordan E | 2 | 0 | 0 | 0 | 120 | 0 | 120 | 43698 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 53704 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 53704 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 53704 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 688 | 10/29/25 | 10/31/25 | GE70 | Gerard, Jordan E | 1.25 | 0 | 0 | 0 | 75 | 0 | 75 | 53705 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 75 | 11/05/25 | 11/07/25 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 13709 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 235 | 11/12/25 | 11/14/25 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 23715 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 352 | 11/19/25 | 11/21/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 33721 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43726 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43726 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43726 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43726 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43726 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 62 | 12/03/25 | 12/05/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13730 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 0.75 | 0 | 0 | 0 | 45 | 0 | 45 | 13731 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 2.5 | 0 | 0 | 0 | 150 | 0 | 150 | 13731 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 23734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23734 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 200 | 12/10/25 | 12/12/25 | GE70 | Gerard, Jordan E | 0.75 | 0 | 0 | 0 | 45 | 0 | 45 | 23735 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33738 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 33738 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 33738 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33738 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 33738 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 2 | 0 | 0 | 0 | 120 | 0 | 120 | 33739 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 105 | 0 | 105 | 33739 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 105 | 0 | 105 | 33739 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43746 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 43746 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 4 | 0 | 0 | 0 | 276 | 0 | 276 | 43746 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43746 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 105 | 0 | 105 | 43747 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 105 | 0 | 105 | 43747 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 2 | 0 | 0 | 0 | 120 | 0 | 120 | 43747 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 4 | 0 | 0 | 0 | 240 | 0 | 240 | 43747 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13750 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 0 | 0 | 103.5 | 0 | 103.5 | 13750 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 23754 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 23754 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 3 | 0 | 0 | 0 | 207 | 0 | 207 | 23754 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 148 | 01/07/26 | 01/09/26 | GE70 | Gerard, Jordan E | 3 | 0 | 0 | 0 | 177 | 0 | 177 | 23755 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 1.5 | 0 | 0 | 0 | 103.5 | 0 | 103.5 | 33758 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 33758 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33758 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33758 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 43763 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 2.75 | 0 | 0 | 0 | 162.25 | 0 | 162.25 | 43764 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 2.75 | 0 | 0 | 0 | 162.25 | 0 | 162.25 | 43764 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 53768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 53768 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13772 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 13772 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13772 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 13772 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 73 | 02/04/26 | 02/06/26 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 103.25 | 0 | 103.25 | 13773 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23777 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 23777 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 103.25 | 0 | 103.25 | 23778 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 2 | 0 | 0 | 0 | 118 | 0 | 118 | 23778 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 467 | 02/25/26 | 02/27/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 43787 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 13791 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 2 | 0 | 0 | 0 | 138 | 0 | 138 | 13791 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 13791 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 13791 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 64 | 03/04/26 | 03/06/26 | GE70 | Gerard, Jordan E | 1 | 0 | 0 | 0 | 59 | 0 | 59 | 13792 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 208 | 03/11/26 | 03/13/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 23795 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 1 | 0 | 0 | 0 | 69 | 0 | 69 | 33799 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 33799 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 1.75 | 0 | 0 | 0 | 103.25 | 0 | 103.25 | 33800 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 2.5 | 0 | 0 | 0 | 147.5 | 0 | 147.5 | 33800 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 1 | 0 | 0 | 0 | 59 | 0 | 59 | 33800 | 0 | 0
101 | Takeoff & Purchase Labor | PR | 494 | 03/25/26 | 03/27/26 | GE69 | Gerard, Jeffrey S | 0.5 | 0 | 0 | 0 | 34.5 | 0 | 34.5 | 43803 | 0 | 0
601 | Engineering/Plans | AP | 427 | 11/21/25 | 11/24/25 | 1940RE | Robison Engineering, Inc. | [6 empty] | 41300 | 1448-002-1 | 0 | 0
601 | Engineering/Plans | AP | 583 | 11/21/25 | 11/24/25 | 1940RE | Robison Engineering, Inc. | [6 empty] | -41300 | 1448-002-1A | 0 | 0
601 | Engineering/Plans | AP | 584 | 11/21/25 | 11/24/25 | 1940RE | Robison Engineering, Inc. | [6 empty] | 30200 | 1448-002-1 R1 | 0 | 0
995 | Payroll Burden | PR | 548 | 08/27/25 | 08/29/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 136.07 |  | 0 | 0
995 | Payroll Burden | PR | 262 | 09/17/25 | 09/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 102.05 |  | 0 | 0
995 | Payroll Burden | PR | 433 | 09/24/25 | 09/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 68.03 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 44.37 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 29.58 |  | 0 | 0
995 | Payroll Burden | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 7.4 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 372 | 10/15/25 | 10/17/25 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 0 | 0 | 58.67 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 68.03 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 96.14 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 14.79 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 51.77 |  | 0 | 0
995 | Payroll Burden | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 88.74 |  | 0 | 0
995 | Payroll Burden | PR | 521 | 10/22/25 | 10/24/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 522 | 10/22/25 | 10/24/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 59.16 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 34.02 |  | 0 | 0
995 | Payroll Burden | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 17.01 |  | 0 | 0
995 | Payroll Burden | PR | 688 | 10/29/25 | 10/31/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 36.98 |  | 0 | 0
995 | Payroll Burden | PR | 75 | 11/05/25 | 11/07/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 17.01 |  | 0 | 0
995 | Payroll Burden | PR | 235 | 11/12/25 | 11/14/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 17.01 |  | 0 | 0
995 | Payroll Burden | PR | 352 | 11/19/25 | 11/21/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 62 | 12/03/25 | 12/05/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 21.33 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 71.1 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 98.12 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 200 | 12/10/25 | 12/12/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 21.33 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 98.12 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 56.88 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 49.77 |  | 0 | 0
995 | Payroll Burden | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 49.77 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 98.12 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 130.82 |  | 0 | 0
995 | Payroll Burden | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 49.77 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 49.77 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 56.88 |  | 0 | 0
995 | Payroll Burden | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 113.76 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 49.06 |  | 0 | 0
995 | Payroll Burden | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 98.12 |  | 0 | 0
995 | Payroll Burden | PR | 148 | 01/07/26 | 01/09/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 83.9 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 49.06 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 76.91 |  | 0 | 0
995 | Payroll Burden | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 76.91 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  | 0 | 0
995 | Payroll Burden | PR | 73 | 02/04/26 | 02/06/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 48.94 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 48.94 |  | 0 | 0
995 | Payroll Burden | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 55.93 |  | 0 | 0
995 | Payroll Burden | PR | 467 | 02/25/26 | 02/27/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 65.41 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.35 |  | 0 | 0
995 | Payroll Burden | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 32.71 |  | 0 | 0
995 | Payroll Burden | PR | 64 | 03/04/26 | 03/06/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 27.97 |  | 0 | 0
995 | Payroll Burden | PR | 208 | 03/11/26 | 03/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
995 | Payroll Burden | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.63 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 49.77 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 71.1 |  | 0 | 0
995 | Payroll Burden | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 28.44 |  | 0 | 0
995 | Payroll Burden | PR | 494 | 03/25/26 | 03/27/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 16.63 |  | 0 | 0
995 | Payroll Burden | PR | 27 | 04/01/26 | 04/03/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 33.26 |  | 0 | 0
998 | Payroll Taxes | PR | 548 | 08/27/25 | 08/29/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 262 | 09/17/25 | 09/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 433 | 09/24/25 | 09/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 6.89 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 4.59 |  | 0 | 0
998 | Payroll Taxes | PR | 31 | 10/01/25 | 10/03/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 182 | 10/08/25 | 10/10/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 372 | 10/15/25 | 10/17/25 | BA70 | Barnhart, Joseph N | 0 | 0 | 0 | 0 | 0 | 0 | 9.1 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 387 | 10/15/25 | 10/17/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 14.92 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 388 | 10/15/25 | 10/17/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 13.77 |  | 0 | 0
998 | Payroll Taxes | PR | 521 | 10/22/25 | 10/24/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 522 | 10/22/25 | 10/24/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 687 | 10/29/25 | 10/31/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 688 | 10/29/25 | 10/31/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 5.74 |  | 0 | 0
998 | Payroll Taxes | PR | 75 | 11/05/25 | 11/07/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 235 | 11/12/25 | 11/14/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 352 | 11/19/25 | 11/21/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 536 | 11/26/25 | 11/28/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 62 | 12/03/25 | 12/05/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 12/03/25 | 12/05/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 11.48 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 199 | 12/10/25 | 12/12/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 200 | 12/10/25 | 12/12/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 3.44 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 340 | 12/17/25 | 12/19/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 341 | 12/17/25 | 12/19/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 21.11 |  | 0 | 0
998 | Payroll Taxes | PR | 528 | 12/24/25 | 12/26/25 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 8.03 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 9.18 |  | 0 | 0
998 | Payroll Taxes | PR | 529 | 12/24/25 | 12/26/25 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 18.36 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 32 | 12/31/25 | 01/02/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 7.92 |  | 0 | 0
998 | Payroll Taxes | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 147 | 01/07/26 | 01/09/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 15.84 |  | 0 | 0
998 | Payroll Taxes | PR | 148 | 01/07/26 | 01/09/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 13.54 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 7.92 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 293 | 01/14/26 | 01/16/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 484 | 01/21/26 | 01/23/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 |  | 0 | 0
998 | Payroll Taxes | PR | 485 | 01/21/26 | 01/23/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 12.41 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 597 | 01/28/26 | 01/30/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 72 | 02/04/26 | 02/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 73 | 02/04/26 | 02/06/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 7.9 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 204 | 02/11/26 | 02/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 7.9 |  | 0 | 0
998 | Payroll Taxes | PR | 205 | 02/11/26 | 02/13/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 9.03 |  | 0 | 0
998 | Payroll Taxes | PR | 467 | 02/25/26 | 02/27/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 10.56 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 63 | 03/04/26 | 03/06/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 64 | 03/04/26 | 03/06/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 4.51 |  | 0 | 0
998 | Payroll Taxes | PR | 208 | 03/11/26 | 03/13/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
998 | Payroll Taxes | PR | 326 | 03/18/26 | 03/20/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 7.9 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 11.28 |  | 0 | 0
998 | Payroll Taxes | PR | 327 | 03/18/26 | 03/20/26 | GE70 | Gerard, Jordan E | 0 | 0 | 0 | 0 | 0 | 0 | 4.51 |  | 0 | 0
998 | Payroll Taxes | PR | 494 | 03/25/26 | 03/27/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 2.64 |  | 0 | 0
998 | Payroll Taxes | PR | 27 | 04/01/26 | 04/03/26 | GE69 | Gerard, Jeffrey S | 0 | 0 | 0 | 0 | 0 | 0 | 5.28 |  | 0 | 0
999 | Sales | AR | 428 | 11/24/25 | 11/24/25 | 2106CC | Chinn Construction, LLC $6220 Roosevelt | [6 empty] | -32850 | 038507 | 0 | -1642.5
999 | Sales | AR | 429 | 11/24/25 | 11/24/25 | 2106CC | Chinn Construction, LLC $6220 Roosevelt | [6 empty] | 32850 | 038508 | 0 | 1642.5
999 | Sales | AR | 430 | 11/24/25 | 11/24/25 | 2106CC | Chinn Construction, LLC $6220 Roosevelt | [6 empty] | -32850 | 038509 | 0 | -32850
999 | Sales | AR | 404 | 01/20/26 | 01/20/26 | 2106CC | Chinn Construction, LLC $6220 Roosevelt | [6 empty] | -16425 | 038529 | 0 | -16425

## Cost Code Summaries
COST CODE SUMMARIES — 6 CODES
code | description | category | original_budget | current_budget | plus_minus_budget | actual_amount | net_due | retainage | regular_hours | overtime_hours | doubletime_hours | other_hours
100 | Supervision | Labor | 0 | 0 | 69 | 69 | 0 | 0 | 1 | 0 | 0 | 0
101 | Takeoff & Purchase Labor | Labor | 0 | 0 | 9913.25 | 9913.25 | 0 | 0 | 151 | 0 | 0 | 0
601 | Engineering/Plans | Overhead | 0 | 0 | 30200 | 30200 | 0 | 0 | 0 | 0 | 0 | 0
995 | Payroll Burden | Burden | 0 | 0 | 4780.75 | 4780.75 | 0 | 0 | 0 | 0 | 0 | 0
998 | Payroll Taxes | Burden | 0 | 0 | 763.76 | 763.76 | 0 | 0 | 0 | 0 | 0 | 0
999 | Sales | Revenue | 0 | 0 | 49275 | -49275 | -49275 | 0 | 0 | 0 | 0 | 0

## Worker Wages
WORKER NOMINAL WAGES — 3 WORKERS
Per-worker wage data derived from PR line items in the JDR.
Worker (Last, First) | Reg Hours | OT Hours | DT Hours | Other Hours | Reg Amount | OT Amount | Nominal Rate ($/hr) | Tier
LEAD/SUPERVISOR
Gerard, Jordan E | 53.75 | 0 | 0 | 0 | 3204.75 | 0 | 59.6233 | LEAD/SUPERVISOR
Barnhart, Joseph N | 1.75 | 0 | 0 | 0 | 119 | 0 | 68 | LEAD/SUPERVISOR
Gerard, Jeffrey S | 96.5 | 0 | 0 | 0 | 6658.5 | 0 | 69 | LEAD/SUPERVISOR

## Derived Fields
DERIVED FIELDS — 36 CALCULATIONS
All derived values computed from parsed data.
Field | Value | Formula / Logic
cost_by_source_pr_amount | 15526.76
cost_by_source_ap_amount | 30200
cost_by_source_gl_amount | 0
direct_cost | 45726.76
net_profit | 3548.24
pr_pct_of_revenue | 0.3151
ap_pct_of_revenue | 0.61289
direct_cost_pct_of_revenue | 0.92799
total_labor_hours | 152
pr_src_cost_per_hr | 102.1497
fully_loaded_wage | 138.6268
burden_multiplier | 1.3571
straight_time_rate | 65.6727
total_workers | 3
nominal_wage_percentiles | {'p10': 61.3, 'p25': 63.81, 'p50': 68.0, 'p75': 68.5, 'p90': 68.8}
burden_total | 5544.51
material_spend_total | 0
material_budget_total | 0
material_codes_tracked | 0
material_codes_over_budget | 0
material_codes_under_budget | 0
largest_material_overrun | None
largest_material_savings | None
material_vendor_count | 1
top_vendor_spend | Robison Engineering, Inc.: $30,200 (100% of AP)
phases_over_budget | 5
phases_under_budget | 0
largest_overrun | 601 Engineering/Plans: $30,200 vs $0 budget (+$30,200)
largest_savings | 100 Supervision: $69 vs $0 budget ($69)
total_jtd_cost | 45726.76
total_budget | 0
overall_pct_budget_consumed | 0
total_over_under_budget | -45726.76
labor_unit_cost_per_hr | 65.6727
revenue_per_labor_hour | 324.1776
material_price_variance | 0

## Reconciliation
RECONCILIATION — PER COST CODE
Parsed line item sums vs. cost code summary totals from the PDF.
Cost Code | Description | PDF Total | Parsed Sum | Difference | Status
100 | Supervision | 69 | 69 |  | PASS
101 | Takeoff & Purchase Labor | 9913.25 | 9913.25 |  | PASS
601 | Engineering/Plans | 30200 | 30200 |  | PASS
995 | Payroll Burden | 4780.75 | 4780.75 |  | PASS
998 | Payroll Taxes | 763.76 | 763.76 |  | PASS
999 | Sales | -49275 | -49275 |  | PASS

## Reconciliation Log
RECONCILIATION LOG
Audit log of any reconciliation events / adjustments / re-parses.
Date | Event Type | Source | Description | Before | After | Operator
2026-04-27 | initial_parse | parse_2106.py | Initial Sage JDR parse for Job #2106. Parsed lines: 298. Cost codes: 6. Workers: 3. | (no prior parse) | 298 line items | OWP Estimating