## 01 Overview
OWP #2106 · 6220 Roosevelt
Chinn Construction, LLC · 146 units · Pre-construction
Forecast at Completion (Revised Basis)
Revised contract value | 0
Revised budget (expenses) | 0
Forecast net profit | 0
Forecast margin | 0%
Progress to Date
Work complete (billed) | 49275
Retention held | 0
Earned less retention | 49275
Balance to finish | -49275
Percent complete | 0%
Transaction Totals by Source
Source | Dollars
GL | 0
AP | 30200
PR | 15526.76
AR | -49275
PROJECT TEAM · KEY PLAYERS
Pre-construction · early takeoff phase. Subcontract pending — final BID submitted Dec 4 2025 ($3,042,140 / 147u) to Chinn. Tri-State Plumbing also bidding.
ROLE | VALUE
General Contractor | Chinn Construction, LLC
Owner | Phoenix Property Co (per Master Project List Projects Bid tab)
Architect | Weber Thompson
MEP / Plumbing Engineer | Emerald City Engineering (GC's bridge MEP) + Robison Engineering, Inc. (OWP's 3rd-party plumbing design-build engineer · $30,200 design fee booked)
OWP Estimator | Jeffrey S. Gerard / Jordan E. Gerard / Joseph N. Barnhart (takeoff team)
OWP Signatory | Richard Donelson
Site Address | 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood)
Insurance | Standard (COI) — non-Wrap (per project team grid)
Status | ACTIVE · pre-construction (early takeoff phase)
Latest BID submitted | $3,042,140 (Dec 4 2025 · 147u)
AR Billed to date | $49,275 (takeoff phase)
Direct Cost (sunk) | $45,727
Net Profit (takeoff) | $3,548 (7.2% margin)
Active Crew | 3 OWP estimating leads (Gerard family + Joseph Barnhart) · 152 hrs

## 02 Job Info
JOB #2106 · CHINN 6220 ROOSEVELT · KEY PLAYERS & METADATA
Pre-construction · early takeoff phase. Sage shows $49,275 billed against $45,727 sunk design+takeoff cost ($3,548 carrying margin so far). Subcontract not yet executed — final BID submitted Dec 4 2025 to Chinn for $3,042,140 (147 units). Target field start Jul 2026. Tri-State Plumbing also bidding per Master List notes.
IDENTITY
Job Number | 2106
Job Name | Chinn 6220 Roosevelt
Project Type | 146-unit (147 in latest bid) multifamily · Roosevelt neighborhood Seattle
Site Address | 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood)
Permit | Pre-permit (no permit applied for yet)
Status | ACTIVE · pre-construction (early takeoff phase)
Scope of Work | Design Build Plumbing Systems (typical Chinn engagement pattern)
SCHEDULE
Project Start | Jul 2026 (target)
Expected End | Q3 2028 (estimated)
Duration (est.) | 24 months
Schedule Note | Pre-construction · target field start Jul 2026 · ~24 months to TCO (Q3 2028 expected)
Subcontract Execution | Pending — target Jul 2026
FINANCIAL POSTURE (PRE-CONSTRUCTION · TAKEOFF PHASE)
Original Contract | Not yet executed
Latest BID submitted | $3,042,140 (Dec 4 2025 · 147 units)
AR Billed to Date | $49,275 (4 progress billings · takeoff phase)
Direct Cost (sunk) | $45,727
Net Profit (takeoff phase) | $3,548 (7.2% margin)
Retainage | $0 (no field billing yet)
Insurance | Standard (COI) — non-Wrap (per project team grid)
Lien Position | Standard subcontract — pending execution
Warranty | 1-yr standard plumbing (post-completion)
Contract on File | Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147u)
SCOPE
Plumbing Units | 146 units (current data.json) · 147 units (latest BID Dec 2025) ⚠ scope evolved
Total Fixtures | TBD (no fixture schedule yet — pre-design-development)
Floors | TBD
Fixture Counts | TBD
PROJECT TEAM — GENERAL CONTRACTOR (Chinn)
General Contractor | Chinn Construction, LLC
GC Project Manager | TBD (Chinn) — primary contact pending subcontract execution
GC Superintendent | TBD
GC Project Engineer | TBD
Chinn engagement count | OWP's 8th Chinn engagement (after #2009 Greenwood, #2010 Old Town, #2011 Phinney Ridge, #2023 Legacy Apts, #2041 Luna California Ave, #2070 Beacon Crossing, #2071 1405 Dexter, #2096 Sundowner). Strong recurring relationship.
PROJECT TEAM — OWP STAFF
OWP Roughin Foreman | TBD · pre-construction (target start Jul 2026)
OWP Trim Foreman | TBD
OWP Estimator (takeoff) | Jeffrey S. Gerard / Jordan E. Gerard / Joseph N. Barnhart (takeoff team)
OWP Signatory | Richard Donelson
PROJECT TEAM — OWNER & DEVELOPMENT
Owner of Record | Phoenix Property Co (per Master Project List Projects Bid tab)
Developer | Phoenix Property Co
PROJECT TEAM — DESIGN
Architect | Weber Thompson
Structural Engineer | TBD
MEP / Plumbing Engineer | Emerald City Engineering (GC's bridge MEP) + Robison Engineering, Inc. (OWP's 3rd-party plumbing design-build engineer · $30,200 design fee booked)
Civil Engineer | TBD
Landscape Architect | TBD
BID HISTORY (from OWP Master Project List)
Bid Date | Type | GC | Units | Price | Note
2024-08-08 | BUDGET | Exxel Pacific | 146 | $2,800,000 | Original Exxel budget bid
2024-08-08 | BUDGET | Compass | 146 | $2,800,000 | Compass also bid same date
2024-08-16 | BUDGET | Chinn | 146 | $2,800,000 | Chinn enters · matches base budget
2024-12-11 | BUDGET | Chinn | 147 | $2,988,000 | Unit count grew by 1 · price up to $2.99M
2025-02-24 | BUDGET | Chinn | 147 | $2,937,000 | Re-bid · price came down 1.7%
2025-05-06 | BUDGET | Chinn | 147 | $2,968,000 | Re-bid · price up 1.0%
2025-12-04 | BID | Chinn | 147 | $3,042,140 | FINAL BID · $3.04M · Tri-State also bidding
AP VENDOR PROFILE (CURRENT — TAKEOFF PHASE)
Top Vendor | Robison Engineering, Inc. ($30,200 / 3 invoices / 100% of AP)
Total AP Spend | $30,200
Active Vendors | 1 unique vendor (Robison Engineering only — typical for design-build takeoff phase)
Concentration Note | Single-vendor (100%) is normal for early design phase. Will diversify when field phase begins (Ferguson, Keller, Rosen, etc. typical for Chinn jobs based on closed-portfolio data).
DOCUMENT META (current)
Pay Apps (filed) | 4 progress billings (parsed from JDR AR)
Executed COs | 0 (subcontract pending)
CORs | 0
RFIs | 0
Submittals | 0 (pre-construction)
POs | 0
Permit Count | 0 (pre-permit)
Notes | Project hasn't reached document-generation phase. Only the OWP estimating team + Robison Engineering have touched the file (takeoff + design coordination).
DATA SOURCES
JDR PDF | 2106 Job Detail Report (Sage Timberline · Apr 3 2026 run)
Parsed Data | 2106_data.json (6 cost codes, 298 line items, 3 workers)
Dashboard Arrays | 2106_dashboard_arrays.json (16 arrays)
Master Project List | OWP Project List with Schedule - UPDATED 04-01-26.xlsx (Schedule r102, Projects Bid r319-404 = 7-bid history)
GDrive Folder | Not yet created
GDrive Status | No GDrive Job Book folder created yet (project hasn't reached active stage). All team data sourced from OWP Master Project List + JDR identity + AP vendor scan.
RISK FLAGS / WATCH ITEMS
Subcontract not yet executed | OWP has $45.7k of sunk design+takeoff cost. Final BID submitted Dec 2025; await Chinn award decision. If Chinn picks Tri-State, OWP has to absorb the $45.7k or write off.
Tri-State competition flag | Master List notes (Dec 2025): 'I've heard that Tri-State is bidding'. Chinn award decision pending.
Bid drift (146 → 147 units) | Project added 1 unit between Aug 2024 (146u @ $2.8M) and Dec 2024 (147u @ $2.99M). Final BID Dec 2025 = 147u @ $3.04M. data.json still reflects 146 — will update at subcontract execution.
Robison Engineering relationship | OWP's 3rd-party plumbing design-build engineer (vs Franklin on most other jobs). Same engineer as #2118 Edmonds Behar and #2114 Holland Ballard Blossom — a recurring 3rd-party design partnership.
Chinn closed-job track record | Chinn = 7 closed jobs in OWP closed portfolio with strong margin profiles (#2009/2010/2011 Greenwood/Old Town/Phinney Ridge averaged 30-40% margins). Likelihood of award = HIGH if pricing is competitive.

## 03 Contract
Contract Summary
Item | Original | Revised | Delta
Base construction contract | 0 | 0 | 0
Executed change orders (net) | 0 | 0 | 0
Total contract value | 0 | 0 | 0
Executed Change Orders
CO # | Description | Amount

## 04 SOV-PayApps
Schedule of Values / Pay Application History
Pay App | Period End | This Period | Completed to Date | Retention Held | Previous Billed | Current Balance

## 05 Change Orders
Change Order Log
# | Type | Description | Amount | Status

## 06 Cost Codes
Cost Code Detail (Revised Basis)
Code | Description | Original | Revised | Actual | Variance | Net Due | % Complete
100 | Supervision | 0 | 0 | 69 | -69 | 0 | 0%
101 | Takeoff & Purchase Labor | 0 | 0 | 9913.25 | -9913.25 | 0 | 0%
601 | Engineering/Plans | 0 | 0 | 30200 | -30200 | 0 | 0%
995 | Payroll Burden | 0 | 0 | 4780.75 | -4780.75 | 0 | 0%
998 | Payroll Taxes | 0 | 0 | 763.76 | -763.76 | 0 | 0%
TOTAL |  | 0 | 0 | 45726.76 | -45726.76 | 0 | 0%

## 07 Cost Categories
Cost Category Rollup
Category | # Codes | Revised Budget | Actual | Variance | % Complete
Labor | 2 | 0 | 9982.25 | -9982.25 | 0%
Material | 0 | 0 | 0 | 0 | 0%
Overhead | 1 | 0 | 30200 | -30200 | 0%
Burden | 2 | 0 | 5544.51 | -5544.51 | 0%
TOTAL | 5 | 0 | 45726.76 | -45726.76 | 0%

## 08 BVA
Budget vs Actual — Flag list
Revised budget is canonical basis. Flags: OVER >10%, CRITICAL >50%, ON ±10%, UNDER <-10%.
Code | Description | Revised | Actual | Variance | % Var | Status
100 | Supervision | 0 | 69 | -69 | 0% | UNBUDGETED
101 | Takeoff & Purchase Labor | 0 | 9913.25 | -9913.25 | 0% | UNBUDGETED
601 | Engineering/Plans | 0 | 30200 | -30200 | 0% | UNBUDGETED
995 | Payroll Burden | 0 | 4780.75 | -4780.75 | 0% | UNBUDGETED
998 | Payroll Taxes | 0 | 763.76 | -763.76 | 0% | UNBUDGETED

## 09 Vendor Analysis
Vendor Spend (AP source)
Vendor | Spend ($) | Invoices | % of Total AP
Robison Engineering, Inc. | 30200 | 3 | 100%
TOTAL AP | 30200 | 3

## 10 Crew Roster
Crew Roster (PR source)
Worker | Hours | Labor $ | Avg $/hr | Tier
Gerard, Jeffrey S | 96.5 | 6658 | 68.9948 | LEAD/SUPERVISOR
Gerard, Jordan E | 53.8 | 3205 | 59.5725 | LEAD/SUPERVISOR
Barnhart, Joseph N | 1.8 | 119 | 66.1111 | LEAD/SUPERVISOR

## 11 Wage Tiers
Wage Tier Distribution
Tier | # Workers | Hours | Labor $ | % of Hours
LEAD/SUPERVISOR | 3 | 152 | 9982 | 100%
JOURNEYMAN | 0 | 0 | 0 | 0%
APPRENTICE/HELPER | 0 | 0 | 0 | 0%
OT-ONLY | 0 | 0 | 0 | 0%

## 12 Productivity
Productivity Metrics
Total labor hours (to date) | 152
Active workers | 3
Hours per unit (to date) | 1
Revenue per labor hour (billed) | 324.18
Percent complete | 0%

## 13 Benchmarks
Portfolio Benchmarks (vs. closed jobs)
Metric | This Job | Portfolio Median | Delta
Forecast margin % | 0% | 34% | -34%
Roughin labor share (code 120) | 0% | 45% | -45%
Top vendor concentration | 100% | 38% | 62%
Hours per unit | 1.0411 | 95 | -93.9589

## 14 Predictive Signals
Predictive Signals (pre-construction project)
Signal | Status | Notes
Engineering/Plans (601) unbudgeted | ⚠ WATCH | No revised budget but $30,200 actual spend — needs CO or budget transfer
Top vendor concentration (Robison Engineering,) | ⚠ WATCH | 100% of AP ($30,200) — high, monitor
Retention aging | ✓ OK | $0 held · 0.0% of billed · standard range
Forecast margin | ⚠ WATCH | 0.0% forecast margin — monitor

## 15 Reconciliation
JDR Reconciliation
Source | Reported | Calculated | Delta
Total expenses (from code totals) | 45726.76 | 45726.76 | 0
Revenue billed (AR ·-1) | -49275 | 49275 | -98550
AP source total |  | 30200 | —
PR source total |  | 15526.76 | —
GL source total |  | 0 | —

## 16 Metric Registry
Metric Registry
Metric | Source Tab | Definition
Forecast margin % | 01 Overview | Forecast net profit / Revised contract value
Percent complete | 01 Overview | Billed to date / Revised contract value
Roughin labor share | 06 Cost Codes | Code 120 revised / Total labor revised budget
Top vendor concentration | 09 Vendor Analysis | Largest single vendor AP spend / Total AP
Hours per unit | 12 Productivity | Total PR hours to date / Unit count
BVA status codes | 08 BVA | OVER / CRITICAL / UNDER / ON / UNBUDGETED on revised basis

## 17 Change Log
Workbook Change Log
Date | Version | Note
2026-04-24 | v1.0 · pre-construction | Initial build for #2106 pre-construction project. 17-tab JCR schema on revised budget basis.
2026-04-27 | v1.1 · enriched | Enriched Job Info tab with 12-section sectioned layout (identity / schedule / financial posture / scope / project team — 4 sub-sections / bid history (7 entries) / AP vendor profile / document meta / data sources / risk flags). Added Project Team block to Overview. Sourced from OWP Master Project List (Schedule r102 + Projects Bid 7-bid history) + Sage JDR identity + AP vendor scan. No GDrive Job Book yet — will be created at subcontract execution (target Jul 2026).