## Overview
Job #2106 · Chinn 6220 Roosevelt
Cortex JCR Summary • Chinn Construction, LLC (Owner: Phoenix Property Co)
PROJECT OVERVIEW
Project Job # | 2106
Project Name: | Chinn 6220 Roosevelt
General Contractor | Chinn Construction, LLC (Owner: Phoenix Property Co)
Location | 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood)
Project Duration | Jul 2026 (target field start) – Q3 2028 (estimated) (~24 months · pre-construction)
Status | ACTIVE · pre-construction (early takeoff phase)
CONTRACT VALUE |  | FORECAST NET PROFIT |  | DIRECT COST |  | LABOR HOURS
$49,275 |  | $3,548 |  | $45,727 |  | 152
$0 orig + $0 COs |  | 7.2% margin |  | 92.8% of revenue |  | 3 workers
COST BREAKDOWN
Category | Budget | Actual | Variance | % Budget | % of Cost
Labor | 0 | 9982 | -9982 | 0 | 0.2183
Material | 0 | 0 | 0 | 0 | 0
Overhead | 0 | 30200 | -30200 | 0 | 0.66046
Burden | 0 | 5544 | -5544 | 0 | 0.12124
TOTAL | 0 | 45726 | -45726 | 0 | 1
PROJECT PROFILE
Plumbing Units | 146 | Total Fixtures | TBD | Fixtures / Unit | TBD
GC | Chinn Construction, LLC | Owner | Phoenix Property Co | Insurance | Standard COI
Status | ACTIVE · pre-construction (early takeoff phase) | Duration | ~24 months · pre-construction | Permit | Pre-permit
NARRATIVE
Pre-construction project — early takeoff phase. OWP submitted final BID Dec 4 2025 to Chinn for $3,042,140 (147 units, +1 from initial 146-unit scope). Tri-State Plumbing also bidding per Master List notes. To date OWP has billed $49,275 against $45,727 sunk design+takeoff cost = $3,548 carrying margin (7.2%). Subcontract pending Chinn award decision. OWP's 8th Chinn engagement (after Greenwood, Old Town, Phinney Ridge, Legacy Apts, Luna California, Beacon Crossing, 1405 Dexter, Sundowner). Robison Engineering is the 3rd-party plumbing design-build engineer (same partnership as #2118 Edmonds Behar and #2114 Holland Ballard Blossom). Field start target Jul 2026.
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Budget vs Actual
Budget vs Actual — All Cost Codes
Code | Description | Orig Budget | Rev Budget | Actual | Variance | % Used
LABOR
100 | Supervision | 0 | 0 | 69 | -69 | 0
101 | Takeoff & Purchase Labor | 0 | 0 | 9913 | -9913 | 0
OVERHEAD
601 | Engineering/Plans | 0 | 0 | 30200 | -30200 | 0
BURDEN
995 | Payroll Burden | 0 | 0 | 4781 | -4781 | 0
998 | Payroll Taxes | 0 | 0 | 764 | -764 | 0
TOTAL Direct Cost |  | 45727 | 45727 | 45727
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Cost Breakdown
Cost Breakdown — Category Deep Dive
A. CATEGORY SHARE OF DIRECT COST
Category | # Codes | Budget | Actual | Variance | % Budget | % of Cost
Labor | 2 | 0 | 9982 | -9982 | 0 | 0.2183
Overhead | 1 | 0 | 30200 | -30200 | 0 | 0.66044
Burden | 2 | 0 | 5545 | -5545 | 0 | 0.12126
B. LARGEST OVERRUNS (Actual > Revised Budget)
Code | Description | Rev Budget | Actual | Overrun | % Over
601 | Engineering/Plans | 0 | 30200 | 30200 | 0
101 | Takeoff & Purchase Labor | 0 | 9913 | 9913 | 0
995 | Payroll Burden | 0 | 4781 | 4781 | 0
998 | Payroll Taxes | 0 | 764 | 764 | 0
100 | Supervision | 0 | 69 | 69 | 0
C. LARGEST SAVINGS (Actual < Revised Budget)
Code | Description | Rev Budget | Actual | Savings | % Under
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Material
Material Spend Analysis
0 material cost codes • $0 JDR material • 1 AP vendors
A. MATERIAL BY COST CODE
Code | Description | Rev Budget | Actual | Variance | % Used | % of Mat
B. VENDORS BY SPEND (AP)
Vendor | # Invoices | Total Spend | % of AP
Robison Engineering, Inc. | 3 | 30200 | 1
TOTAL | 3 | 30200 | 1
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Crew & Labor
Crew & Labor — Per-Worker Breakdown
Worker | Hours | Gross Pay | $/Hour | Tier
Gerard, Jeffrey S | 96.5 | 6658 | 68.9948 | Senior
Gerard, Jordan E | 53.8 | 3205 | 59.5725 | Senior
Barnhart, Joseph N | 1.8 | 119 | 66.1111 | Senior
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Crew Analytics
Crew Analytics — Tier Distribution & Wages
A. TIER DISTRIBUTION
Tier | # Workers | Hours | Gross Pay | % of Hours
Senior | 3 | 152.1 | 9982 | 100.0%
B. WAGE STATISTICS
Blended labor rate ($/hr) | 65.63
Foreman labor rate ($/hr) | 69
Burden multiplier | 1
Min wage ($/hr) | 59.62
Max wage ($/hr) | 69
Avg hours per worker | 50.7
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Productivity
Productivity — Phases by Hours
Phase | Code | Hours | % of Total | Hours/Unit
Supervision | 100 | 1 | 0.7% | 0.01
Takeoff & Purchasing | 101 | 151 | 99.3% | 1.03
TOTAL |  | 152
PRODUCTIVITY RATIOS
Revenue per unit | $338
Direct cost per unit | $313
Hours per unit | 1.04
Revenue per hour | $324
Profit per hour | $23
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## PO Commitments
PO Commitments — Vendor Concentration
Per-PO records live in GDrive. This tab summarizes commitments by vendor concentration.
# | Vendor | # Invoices | Total Spend | % of AP | Tier
1 | Robison Engineering, Inc. | 3 | 30200 | 100.0% | Top 5
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Billing & SOV
Billing & Statement of Values
STATEMENT OF VALUES — SUMMARY
Original Contract | $0
Net Change Orders | $0
Final Contract | $0
Retainage Held | $0
Net Paid to OWP | $49,275
PAY APPLICATION HISTORY
Pay App # | Date | This Period | Retainage | Net | Cumulative | % Contract
1 | 01/20/26 | 16425 | -16425 | 16425 | 16425 | 33.3%
2 | 11/24/25 | 32850 | -1642 | 32850 | 49275 | 100.0%
3 | 11/24/25 | 32850 | 1642 | 32850 | 82125 | 166.7%
4 | 11/24/25 | 32850 | -32850 | 32850 | 114975 | 233.3%
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Insights
Key Insights — 10 Themes
# | Theme | Insight
1 | MARGIN PROFILE | Net profit of $3,548 on $49,275 revenue = 7.2% margin (takeoff phase only). Direct cost $45,727 absorbs 92.8% of revenue.
2 | VENDOR CONCENTRATION | Robison Engineering, Inc. = $30,200 (100.0% of all AP) across 3 invoices. Single-vendor design-engineering relationship — Robison handles plumbing design as 3rd-party engineer.
3 | CREW PROFILE | 3 workers (all OWP estimating leads — Gerard family + Joseph Barnhart) for 152 hours = 51 avg hrs/worker. Pre-construction · no field crew yet.
4 | DESIGN-BUILD PATTERN | Code 601 Engineering/Plans = $30,200 (Robison Engineering, 3 invoices). Code 101 Takeoff = $9,913 (150 hrs of Gerard family takeoff). Code 999 AR = -$49,275 (4 progress billings). OWP follows the same design-build subcontract pattern as #2061 Alta Columbia City and #2118 Edmonds Behar.
5 | BUDGET DELIVERY | No revised expense budget yet — pre-construction. Actual direct cost $45,727 booked against Sage code structure. Field budget will populate at subcontract execution (target Jul 2026).
6 | CONTRACT GROWTH | Subcontract not yet executed. OWP submitted final bid Dec 4 2025: $3,042,140 / 147 units (Chinn). Bid history: 6 BUDGET iterations Aug 2024 → May 2025 ($2.80M-$2.97M), final BID Dec 2025 = $3.04M.
7 | BURDEN RATIO | Burden codes 995 + 998 = $5,545 on $9,982 labor base = 55.5%. In line with OWP's typical 48-50% labor burden (takeoff-only phase).
8 | PROJECT SCALE | 146 units (146 BUDGET → 147 BID per Master Project List Dec 2025). 6220 Roosevelt Way NE, Roosevelt neighborhood Seattle WA. Phoenix Property Co owner; Weber Thompson architect; Emerald City MEP bridge engineer; Robison plumbing design-build engineer.
9 | PRODUCTIVITY | Blended labor rate $65.63/hr (high — Senior-only crew on takeoff). Revenue/hour $324. Profit/hour $23.
10 | CO PROFILE | 0 COs (pre-construction). 0 RFIs / 0 ASIs. No GDrive Job Book folder yet — will be created when project advances to field phase (target Jul 2026).
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Benchmark KPIs
Benchmark KPIs — Industry Reference Points
KPI | This Project | OWP Median | Industry Reference | Status
Gross Margin | 7.2% | 32-38% | 30-40% | INFO
Revenue per unit | $338 | $10-15k | $8-20k | INFO
Direct cost per unit | $313 | $7-10k | $6-15k | INFO
Top vendor % of AP | Pending vendor agg | <35% | <40% | INFO
Burden ratio | 56% | 48-50% | 40-55% | WATCH
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Reconciliation
Reconciliation — Data Source Cross-Check
Check | Expected | Actual | Delta | Status
Contract: hero block vs JDR | $0 | $0 | — | OK
Billed: hero block vs JDR | $49,275 | $49,275 | — | INFO
Direct cost: meta vs costCats | $45,727 | $45,727 | — | OK
Worker count: dashboard vs meta | 3 | 3 | — | OK
AP vendor count vs JDR | Source aggregate | 1 | — | INFO
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit

## Vendors
Vendor Analysis
# | Vendor | # Invoices | Total Spend | % of AP | Notes
1 | Robison Engineering, Inc. | 3 | 30200 | 100.0% | Concentration flag
SOURCES
Job #2106 — Chinn 6220 Roosevelt • GC: Chinn Construction, LLC • Status: ACTIVE · pre-construction (early takeoff phase)
Canonical source: 2106_data.json (Sage Timberline JDR · Apr 3 2026 run)
Dashboard arrays: 2106_dashboard_arrays.json (mirrors index.html PROJECTS['2106'])
Project profile: 146 units · 6220 Roosevelt Way NE, Seattle, WA (Roosevelt neighborhood) · ~24 months · pre-construction
Design team: Weber Thompson (architect), Emerald City (GC bridge MEP), Robison Engineering (OWP design-build engineer)
Contract: Subcontract NOT yet executed — final BID submitted Dec 4 2025 ($3,042,140 / 147 units)
Billing: $49,275 billed across 4 progress billings (takeoff phase). $0 retention.
Permit: Pre-permit